## EDL Data
# | Year | Date | Vessel | Division | MCIA # | Hours | System | Subsystem | Work Order # | Delay Log Notes | Work Order Title | Work Order Notes / Findings | Contributing Factors
1 | 2017 | 2017-01-01 | Sugar Island | Hopper | None | 105.85 | Piping / Hoses | Deck Discharge Pipe | None | pipe broken | No Work Order entered | No Work Order entered into Delay Log
2 | 2017 | 2017-01-12 | Sugar Island | Hopper | None | 46.74 | Piping / Hoses | Hose Reel Repair | None | None | No Work Order entered | No Work Order entered into Delay Log
3 | 2017 | 2017-01-14 | Alaska | Hydraulic | None | 37.61 | Ladder Pump | Pump Leak | 4191620 | Ladder pump discharge elbow leak | UWP Discharge Elbow (5C-1140) | No findings
4 | 2017 | 2017-02-03 | Illinois | Hydraulic | None | 69.24 | Main Pump | Engine/Motor | 4192535 | Turbo Stbd eng | Remove STBD turbo on pump engine | Bearings failed in turbo. Hrs on enginbe at time of failer 26330. Crew removed hand rail and secured area. removed turbo from engine and cleaned up all parts so MSI could install new turbo.
5 | 2017 | 2017-02-18 | Illinois | Hydraulic | None | 291.83 | Cutter | Motor (Cutter Shaft) | 4192979 | None | Troubleshoot STBD cutter motor | After open canister and letting it air out found that the buss bars on the stabd cutter motor where burned off and laying in the floor of the canister called terry wrigth he call CR with Keystone siad they migth could repair in place tect from keystone came out and looked at motor and said that they couldn't be fixed in place so plan was made to pull stabd motor and send to shop for repairs also megged port motor showed ground. 353 hrs on both motors sent installed at the SHEP porject.
6 | 2017 | 2017-03-11 | Alaska | Hydraulic | None | 649.58 | Other | Other | 1727123 | Cutter | Spud Sheaves Inspection | Wrong WO# entered into EDL. EDL WO refers to: "Spud Sheaves Inspection: SHEAVES SHOW SIGNS OF WEAR CENTER HAS 1/8 AND BREAST HAVE 1/16" on 01/15/2017.
7 | 2017 | 2017-03-27 | 54 | Mechanical | None | 45.2 | Main / Aux. Generators | Main Generator Eng | 1699399 | None | Work Order not found | Work Order not found
8 | 2017 | 2017-03-29 | 55 | Mechanical | None | 25.93 | Tagline | Tagline Winch | 4194401 | fire; burnt up | Replace tagline motor | WE FOUND THAT THE BLOWER MOTOR WAS WIRED WRONG AND WASN'T CURCLATING AIR FOR COOLING THE MOTOR .... KEYSTONE ELECTRIC WAS HERE AND FIXED THE PROBLEM
9 | 2017 | 2017-03-30 | 55 | Mechanical | None | 33.52 | Crane Boom | Boom Winch | 4194405 | crack in fishplate of boom hoist support structure | Weld cracks in structure for boom hoist foundation | WE FOUND THAT WE HAD 70% OF THE TRIANGLE JOIST BRACKET WAS CRACK. Welded it up and added stiffness.
10 | 2017 | 2017-04-14 | 55 | Mechanical | None | 154.72 | Tagline | Tagline Winch | 4195045 | bucket falling; tagline motor burnt up | Replace tagline motor #2 | MOTOR BURNED UP WHILE DREDGING, NO KNOWN REASON. THIS IS THE SECOND MOTOR IN THREE WEEKS. HAD KEYSTONE TO TEST ELECTRICAL CIRCUIT, RESISTOR BANKS ON FOUND NOTHING ABNORMAL. PULLED MOTOR AND REPLACED WITH SPARE MOTOR THAT KEYSTONE DELIVERED. ENGINEER AND CHIEF ENGINEER REPLACED CONTACTOR DUE TO CONTACTS PITTED
11 | 2017 | 2017-04-19 | Illinois | Hydraulic | None | 80.26 | Cutter | Gear Box (Cutter Shaft) | 4195518 | troubleshooting and disassembly | Ladder Hoist Winch brake inspection | Wrong WO# entered into EDL. EDL WO refers to: "Ladder Hoist Winch brake inspection" on 4/21/2017.
12 | 2017 | 2017-04-21 | Dodge Island | Hopper | None | 27.24 | Piping / Hoses | Pump Room Discharge Pipe | 4067460 / 4067458 | blew discharge piping in pumproom- dumping remainder of load 234 | Stbd dredge pump discharge piping repair | 4067460: Stbd dredge pump discharge piping repair: The pipe blew out at the top of the spool piece between the discharge "WYE" and the overboard blocking valve. A doubler was installed completly around the pipe from the cast "WYE" to the flange for the valve. The pump room was cleared of sand and water on the upper, mid and lower levels. 4067458: claen up pump room from blow out on discharge Y-pipe: first we bailed the water into bucket s so the water did n't get too high into the motor controler there was about 1.5 -2" of water in the upper pump room we removed 7 dirk slings of sand from the pump room and had to dig sand out of the pump. there valve stack sand was put in a DOT drum, we had to remove the impeller and other items from the pump room as there was 5" of sand underneath these/around these items. We fresh water washed the areas and blew the valve stack areas down with air so we did n't damage it. The welder put some doubler on but the pipe was thin and we put more doubler on so this won't happen again.
13 | 2017 | 2017-04-23 | Illinois | Hydraulic | None | 150 | Cutter | Gear Box (Cutter Shaft) | 4195427 | reassembly | Reassemble cutter gearbox | Cleaned up all parts, and gears before assemblling gear box. installed new o-ring material in split line between housing peaces. Used Loctite 574 sealent between split lines and beqring end covers,installsuper nut studs and super nuts torquen all bolts to spect. Filled box with new oil .
14 | 2017 | 2017-04-24 | Terrapin Island | Hopper | None | 62.51 | Other | Hopper | 1699368 | going inside to fix link on No. 7 hopper door | Work Order not found | Work Order not found
15 | 2017 | 2017-05-02 | 54 | Mechanical | None | 46.92 | Spud System | Spud Structure | 1949226 | Stbd spud repairs | Replace Stbd Spud Brake Band | Stbd spud winch lower brake band broke at the clevis connecting point. Brake band removed and replaced with on hand new band.
16 | 2017 | 2017-05-03 | Liberty Island | Hopper | None | 51.07 | Main Engine / Propulsion | Other | 0846068 | weakend strainer in lower engine room; off project | Repair to hold in Engine Room between main engines | No findings.
17 | 2017 | 2017-05-12 | Illinois | Hydraulic | None | 45.67 | Cutter | SCR Drive / MG Set | None | None | No Work Order entered | No Work Order entered into Delay Log
18 | 2017 | 2017-05-15 | Padre Island | Hopper | None | 65.64 | Other | Other Mechanical | 1987294 | inspecting tanks | Port #1 Slope Void | Source of water was a 3/8" hole in shell plating in way of frame 35 about 3' outboard of head log.
19 | 2017 | 2017-05-19 | Texas | Hydraulic | None | 220 | Main Pump | Bearings/Shafts | 4196302 / 4196456 | replace bearings; rebuild main pump | Spring bearing insert and shaft replacement | WO# 4196302: Water got inside the oil tank fro the spring bearing and the spring bearing insert got wipe out From the drawing: Shaft sleeve ID - 19.440 + .005 - .000. Shaft hub OD - 19.438 +/- .002". Meaning the shaft sleeve fit is 0" to .009" loose. Shaft joirnal Dia. is 14.250" + .001 - .000. Shaft jounal is 14.250" Bearing insert is 12.266 WO# 4196456: Tear down Main Pump: INNER SHELL WORN; BACK LINER WORN
20 | 2017 | 2017-05-26 | Terrapin Island | Hopper | None | 60.13 | Main Engine / Propulsion | Other | 4176910 | clutch | Astern Clutch Smoking | The center plate appears to be hung up and not centering and the friction plates are dragging. Had Mate sail to dock for tie up so work could be performed. Secured engine and Locked out. Started dissasembled of Astern Clutch. Removed the Piston and Pressure plate and first friction disc. Could not remove the center disc. Had to unbolot the unit cage and then drive out the drive studs. Once studs were out removed the Center plate. Found the center plate to be cracked. Cleaned all parts. Checked the Thrust of the High speed shaft on the gearbox and found to be .007 checked the quill shaft and found to be .002 checked the up / down movement of the high speed shaft and it was .005 Installed the clutch drive studs back in the cage and mounted the cage, torqued the nuts. Installed the Inner wear plate. installed the inner friction disc with shims. Installed spare used but good Center plate, moves freely on the drive studs Replace the outer friction disc with a used but good spare. Installed new hardware on the disc. Installed outer friction disc. Installed pressure plate. Installed piston, and secured with 4 nuts. Took feeler gauge measurments of gaps on friction disc. Have not gotten to the .080 to .090 gaps as called for on the print. but these numbers are for all new equipment. Both of the friction disc are used and worn down some. Tested operation of the Clutch with 90 psi air. All looks good Installed the rest of the nuts and torqued. Installed air supply from clutch control panel and operated the clutch with full pressure of 125 psi. System operates as it should. Disassembled the unit to try and get closer on the gap tolerances. Fricion disc gaps: Checked timing of wabco system-see wabco work order
21 | 2017 | 2017-05-31 | Liberty Island | Hopper | None | 118.09 | Main Engine / Propulsion | Other | 4196753 | Port M/E vibration issues - to Lyons shipyard for repairs | Port Main Engine Alignment | Converted to SO# 1700636: found the right aft foot jacking bolt was striped. Found the shims needed replacing. Found all foundation hardware needed replacing.
22 | 2017 | 2017-06-15 | 55 | Mechanical | None | 33.39 | Main / Aux. Generators | Main Generator Eng | 4197291 | Main eng oil cooler; fuel taken during down time | Replace Oil Cooler | FOUND IF YOU DON'T HAVE TANK ON THE RIGHT WAY THE TANK WILL HIT THE COPPER TUBES. WE TURNED TANKS AROUND AND GRIND ON THE EDGE OF TANK
23 | 2017 | 2017-06-19 | Liberty Island | Hopper | None | 79.61 | Main Engine / Propulsion | Other | None | M/E malfunction | No Work Order entered | No Work Order entered into Delay Log
24 | 2017 | 2017-07-08 | 55 | Mechanical | None | 48.26 | Spud System | Walking Mechanism | 4198364 | None | Stern Spud, prime hydraulic pump | WHEN DREDGE LAYS FOR AWHILE THE HYD PUMP LOSES ITS PRIME
25 | 2017 | 2017-07-11 | Terrapin Island | Hopper | None | 38.22 | Dredge Pump | Impeller | 4177229 | impeller swap | Replace stbd dredge pump impeller | 5 Shims used on the impeller The total duration of the job was 36 hours. It requried 4 hours to remove the front door. It did not appear to have been greased when it was installed The overhead hoist would not raise. The front door and spool piece had to be installe with traditional rigging adding to the length of the job. The pump shell was reinforced with NORDBAK which added 6 hours to the taks.
26 | 2017 | 2017-07-12 | Alaska | Hydraulic | None | 70.06 | Main Pump | Pump rebuild | 1727700 | Pump Job - 36 hours | Port M/E Radial Bearing disassembly / inspection | Wrong WO# entered into EDL. EDL WO refers to: "Port M/E Radial Bearing disassembly / inspection" on 11/13/2017.
27 | 2017 | 2017-08-05 | Alaska | Hydraulic | None | 30.95 | Main Pump | Pump rebuild | 4201675 | pump job | Rebuild Main Pump | enginge side liner have wear may be need to replaced on the next pump work inner shell is in good condicions wear are 1 1/2 deep by the engien side and trancition pice D3 5 13/16 WAS THE ONLY MEASUREMENT TAKEN AND F1.100
28 | 2017 | 2017-08-17 | Illinois | Hydraulic | None | 27.24 | Swing System | Winch System | 4199603 | Swing winch drive not working | Swing winch drive not working | found that the joystick hade a bad spot replace found a plc card was going bad locking system on start up replace found that the 2 of the amp chips was bad replace them found that a ESC isolator card for ARM FEBK to drive had a broken pin to replace that card we haft to have Bill English come here to set up that card Bill came here to set up the card
29 | 2017 | 2017-08-31 | Padre Island | Hopper | None | 98.99 | Dredge Pump Engine | Dredge Pump Engine | N/A | overheating | No Work Order entered | No Work Order entered into Delay Log
30 | 2017 | 2017-09-08 | 55 | Mechanical | None | 58.02 | Main Hoist | Closer | 4200447 | hoist motor out | Change #2 hoist motor | OLD MOTOR WENT BAD BECAUSE OF MOISTURE
31 | 2017 | 2017-09-17 | Padre Island | Hopper | None | 46.57 | Piping / Hoses | Lower Drag Arm | 1987956 | sail to wilmington to replace broken lower port DA | Crane and Truck service for port lower D/A | Converted to SO# 1702817: Crane and Truck service for port lower D/A: No findings.
32 | 2017 | 2017-09-19 | Alaska | Hydraulic | None | 110.73 | Main Pump | Pump rebuild | 1727560 | None | Swap front door and liner / main pump | during the swap front door liner we find the inter shell was wear so bad we have the desicion to be change for a new one MAIN PUMP YARDAGE SINCE LAST REBUILT 930,000 AS OF MIDNIGHT 9/8/30 BY MONDAY OR TUESDAY SHOULD BE AROUND 1.3 MIL
33 | 2017 | 2017-10-21 | 54 | Mechanical | None | 55.33 | Main / Aux. Generators | Main Generator | 4201397 | standing by for main gen | Align Main Generator | Converted to SO# 1703226: Align Main Generator
34 | 2017 | 2017-11-02 | Alaska | Hydraulic | None | 77 | Main Pump | Pump rebuild | 1727498 | None | Main Dredge Pump Rebuild | back door liner, shell, front liner, final .070 engineers were sent to do a s / j and help with measurements once we have measurements we will add to finding runner will need to be changed before 1/2 way of job SPI came on site to inspect wear issues MAIN PUMP YARDAGE SINCE LAST REBUILT 900,000 AS OF MIDNIGHT 7/30 BY 8/4 SHOULD BE AROUND 1.2 MIL
35 | 2017 | 2017-11-06 | 55 | Mechanical | None | 26.31 | Buckets | Repair bucket | None | None | No Work Order entered | No Work Order entered into Delay Log
36 | 2017 | 2017-11-06 | Liberty Island | Hopper | None | 34.66 | Jet Pump | Pump Bearing | None | None | No Work Order entered | No Work Order entered into Delay Log
37 | 2017 | 2017-11-06 | Texas | Hydraulic | None | 73.08 | Main Pump | Pump rebuild | N/A | None | No Work Order entered | No Work Order entered into Delay Log
38 | 2017 | 2017-11-12 | Alaska | Hydraulic | None | 59.52 | Main Pump | Bearings/Shafts | 1703521 | Port Side | Work Order not found | Work Order not found
39 | 2017 | 2017-11-15 | Sugar Island | Hopper | None | 25.34 | Other | Other Mechanical | None | None | No Work Order entered | No Work Order entered into Delay Log
40 | 2017 | 2017-11-20 | Alaska | Hydraulic | None | 58.82 | Main Pump | Bearings/Shafts | 1727700 | overheating pedistal bearing | Port M/E Radial Bearing disassembly / inspection | Wrong WO# entered into EDL. EDL WO refers to: "Port M/E Radial Bearing disassembly / inspection" on 11/13/2017.
41 | 2017 | 2017-12-01 | Alaska | Hydraulic | None | 26.4 | Main Pump | Pump rebuild | 1727454 | front liner on main pump went bad; tow into Houma | Main pump liner change out | AFTER 1.5 MILLION yd LINER IS WORN THROUGH 6" X 16" HOLE SHELL SHOWING SIGNS OFF WEAR ADDED NORDVAC IN THIN SPOTS,SHELL 1 1/2" THICK IN TRANSTION .040 LINER / RUNNER CLEARNCE AFTER LINER INSTALL
42 | 2017 | 2017-12-15 | Alaska | Hydraulic | None | 144.79 | Cutter | Motor (Cutter Shaft) | 1727765 | None | Cutter Motor #1 (PORT) removal | The STBD cutter motor failed during digging operations. The STBD cutter motor showed damage to the brushes, brush holders and the commutator during the visual inspect of the motor. When the crew bypassed the motor to operate on the port cutter motor the port cutter motor failed.
43 | 2017 | 2017-12-28 | Alaska | Hydraulic | None | 30.79 | Generator | Main Generator Eng | 1704231 | main gen sparked flames, change 4 cutter teeth | Work Order not found | Work Order not found
44 | 2017 | 2017-12-29 | Sugar Island | Hopper | None | 36.31 | Other | Other Mechanical | 4063904 | lost compass heading; crack in bottom plate wing void | Fabricate Steel Box | Wrong WO# entered into EDL. EDL WO refers to: "Fabricate Steel Box" on 12/29.
45 | 2018 | 2018-01-05 | Terrapin Island | Hopper | None | 73.3 | Main Engine / Propulsion | Tail Shaft | 4178593 | Stbd M/E down due to leaking stern tube | STBD Stern tube - water | Investigate the water leaking from fwd seal and water in head tank Found water spraying from the fwd mechanical seal faces. Secured the engine and inspected the clamping ring. The ring did not appear to have moved. The head tank is full of water and cannot drain down. The tube is filling up faster than we can drain out. Secured the fwd seal cooling water inlet and out let to check if the chamber had developed and leak and was filling the tube. Once secured we could still not drain the water down. The Chief engineer made the descision that it was not safe to continue to operate the stbd tail shaft. and locked out the stbd main engine and the contontrol air to the bridge. Ingaged the air by-pass to the shaft brake and installed some anti locking ring ring supports. so that ring cannot slip back. Maintenance Mangers were informed as well as Regulatory bodies.
46 | 2018 | 2018-01-11 | Alaska | Hydraulic | None | 84.71 | Main Pump | Pump rebuild | 1727803 | None | Rebuild Main Pump | MAIN PUMP YARDAGE SINCE LAST REBUILT 1,221,465 0.95 in the bottom and sides and 0.40 in the top think it's a small humo in the liner casting have all measurements and will get in the system with some help only replaced ss liner @ 1,221,465
47 | 2018 | 2018-01-21 | Ellis Island | Hopper | None | 92.61 | Piping / Hoses | Pump Room Suction Pipe | N/A | Stbd slope tank flooded 15 feet of water in tank vessel at anchor ocsw | No Work Order entered | No Work Order entered into Delay Log
48 | 2018 | 2018-01-31 | Ellis Island | Hopper | None | 40.39 | Main Engine / Propulsion | Gearbox | N/A | None | No Work Order entered | No Work Order entered into Delay Log
49 | 2018 | 2018-02-01 | Alaska | Hydraulic | None | 86.73 | Cutter | Bearings/Shafts | 1727880 | None | Remove tail shaft and install | No findings.
50 | 2018 | 2018-02-02 | Ellis Island | Hopper | None | 421.95 | Main Engine / Propulsion | Gearbox | N/A | high speed aft clutch bearing failure | No Work Order entered | No Work Order entered into Delay Log
51 | 2018 | 2018-02-07 | Illinois | Hydraulic | None | 60.76 | Main Pump | Engine/Motor | 4204577 | Main Engine | Troubleshoot PORT pump engine | Had air box fire on port pump engine around # 20 cylinder shut engine down wait a cpulpe hrs before open and inspecting engine though that the turbo went out, started to take it apart but stoped after inspecting engine more and talking to MSI, MSI sent to mechanics out to trouble shoot engine. They inspected the turbo and siad it looked fine, found the rings stuck on # 20 cylinder and changed it out. They said that being the rings where stuck that a peace of carbon ember passed thourg and cought some oil on fire in the air box causing a flare up. It was only around # 20 cylinder so changed it out and the injector.
52 | 2018 | 2018-02-09 | Dodge Island | Hopper | None | 35.88 | Dredge Pump | Other | 4068750 | Stbd dredge pump repairs | Stbd dredge engine troubleshoot | Possible wrong WO? Converted to SO# 1705244: The engine shut down on high jacket temperature. The thermostats were replaced and the engine put back into service. The engine started to overheat and the expansion tank overflowed. The water pump was checked for failure and found to be fully operational. The engine was filled back up with water and restarted. A large bang was heard and the engine shut back down. The source of the noise was found to be in cylinder #7. The injector crab hold down bolt had failed and the injector hit the valve cover. The injector was removed and water was found in the cylinder. The head was removed and inspected for signs of failure; no visible signs of failure were evident. The piston head was inspected for visible signs of failure none was evident. The power assembly (piston, rod, bearing & liner) were removed from the engine. The crank shaft was inspected for damage and minor scuffing was found on the crank bearing area. The cylinder bore was cleaned and the new power assembly was installed along with new head and injector, injector hold down bolt and injector crab. The engine was refilled with water and the oil and filters were changed. The engine water was added at the water pump inlet to help purge any entrapped air from the engine. The engine was test ran at various RPM under load and injector cut out test were performed and #9 injector was found to be operating erratically. The injector was replaced and the engine was test ran again all injectors were firing normally and exhaust temps were within 15 degrees of each other and jacket water temperature was stable at ~185 degrees. The engine was returned to service and is operating properly at this time.
53 | 2018 | 2018-02-11 | Alaska | Hydraulic | None | 91.93 | Cutter | Motor (Cutter Shaft) | 1727914 | wash out to check cutter motor | Cutter Motor #2 (STBD) Removal | The STBD cutter motor had 2 internal power jumpers fall and land on the aramature. The armature is damaged and the motor is being removed and sent in for overhaul. The dredge will setup to run on one cutter motor
54 | 2018 | 2018-02-16 | Alaska | Hydraulic | None | 65.62 | Cutter | Motor (Cutter Shaft) | 1727917 | None | Cutter Motor #2 (STBD) installation | No findings.
55 | 2018 | 2018-02-23 | Alaska | Hydraulic | None | 67.8 | Main Pump | Pump rebuild | 1727908 | None | Rebuild Main Pump | MAIN PUMP YARDAGE SINCE LAST REBUILT TODAYS DATE 2/11/18 YD'S @ 900,000 LOOKING FOR 1.5 INSPECTION TO DAY LOOKED GOOD .095 front door clearnce
56 | 2018 | 2018-02-23 | Liberty Island | Hopper | None | 40 | Jet Pump | Other | 0847436 | repairs to jet pump pipe and stern tubes while at dock | Replace PORT and STBD inboard stern tube clamp ring seals | Converted to SO# 1705317: CORIN REPLACED THE FWD ORING SEALS ON THE CLAMP RINGS FOR PORT AND STBD STERN TUBES. AFTER SEVERAL DAYS OF WORKING SEALS WERE CHECKED AND FOUND LEAKING AGAIN. FACES NEED TO BE MACHINED TO ELIMINATE LEAKAGE. MAINTENANCE MANAGER MADE AWARE OF THIS. VERBAL CONVERSATION ON 3-7-18 ABOUT LEAKAGE AND REPAIRS TO BE MADE NEXT DRY DOCKING OR WHEN NEEDED BEFORE THAT. JRM
57 | 2018 | 2018-02-26 | Liberty Island | Hopper | None | 72.89 | Generator Engine | Other | 0847488 | Generator not operating in safe parameters, since initial failure; many electronic systems have shown to be potenially compromised with mulitple fuses failing and vital systems not operating consistently | Troubleshooting issues with PORT Gen not coming up to rated engine speed: | AFTER SEVERAL DAYS OF GONG THROUGH ENGINE AND ELMINATING THE SIMPLEST THINGS WE WERE ABLE TO NARROW DOWN THE ISSUE TO THE SWITCH BOARD IN CONTROL ROOM. LOAD SHARING MODULE WAS PUTTTING OUT A ERRATIC SIGNAL FROM THE OUTPUT OF THE PWM. (PULSATING WIDTH MODULE) THIS SIGNAL WAS CAUSING AN ISSUE WITH THE ENGINE RPM'S. ALSO FOUND NOT OPERATING CORRECTLY WAS THE FREQUENCY POTENTIOMETER. IT WAS FOUND MAXED OUT COMPLETLEY AND READING 10K. UNIT SHOULD HAVE BEEN READING NO MORE THAN 5K. AFTER MAKING THE ADJUSTMENTS (SLIMMER) TO THE POT WE WERE THEN ABLE TO START THE ENGINE AND RUN UP TO RATED ENGINE SPEED. PWM WAS CHECKED AGAIN WITH THE METER AND THE SIGNAL WAS STEADY. 68.5% BEFORE PUTTING GEN ONLINE SUGGESTIONS WERE MADE TO AGAIN CHECK THE PMG STATOR AFTER CHECKING THE VOLTAGE ACROSS PM1 AND PM4 WHICH THE OUTPUT SHOULD BE 240V. VOLTAGE READING 227V AS BEFORE WHEN WE CHECKED IN MAY. MEGGERING THE STATOR REVEALED DEAD SHORT THIS TIME AND NOT A LOW SHORT CIRCUIT. DECISION WAS MADE TO REPLACE STATOR WITH SPARES ON BOARD. SPARES ON BOARD ARE FOR THE ORIGINAL GEN SETS ON BOARD. PORT GEN IS OF THE NEW MODEL AND THESE PARTS ARE NOT INTERCHANGEABLE. NEW GEN PURCHASED SITTING IN THE NORFOLK YARD HAS THE STATOR NEEDED AND WILL BE REMOVED FROM THAT GEN AND SHIPPED TO US. CORRECT SPARES WILL BE ORDERED TO REPLACE INVESTGATION CONTINUES TO FIND OUT WHAT EXACTLY CAUSED THE GEN FAILURE. EARLY INDICATIONS POINT TO A BAD INPUT CARD THAT PUTS OUT FREQUENCY, VOLTAGE, WATTAGE, AMPERAGE. CHRIS SLIMMER HAS SOME OF THE TREND DATA. ATTACHED ALSO YOU WILL FIND THE TREND DATA ALONG WITH QUOTE FOR NEW AND REMAN STATOR FROM KATO. 3/2/18 JRM GENERATORS RUNNING IN LOCAL POSITION. 3/8/18 JRM
58 | 2018 | 2018-03-04 | Ellis Island | Hopper | None | 43.89 | Other | Electrical | N/A | Multidrive malfunction | No Work Order entered | No Work Order entered into Delay Log
59 | 2018 | 2018-03-05 | Illinois | Hydraulic | None | 24.01 | Spuds / Xmas Tree | Wires | N/A | Stern | No Work Order entered | No Work Order entered into Delay Log
60 | 2018 | 2018-03-23 | Alaska | Hydraulic | None | 25.63 | Main Pump | Pump rebuild | 1728032 | None | Rebuild Main Pump | MAIN PUMP YARDAGE SINCE LAST REBUILT TODAYS DATE 3/18/18 YD'S @ 1 million LOOKING FOR 1.5 INSPECTION TO DAY LOOKED GOOD .065 clearnce only front linner was replaced 1730416 full pump wet part rebuild to be done post Whiskey / except runner
61 | 2018 | 2018-03-25 | Ellis Island | Hopper | None | 123.37 | Bow Thruster Engine | Other | N/A | bow thruster 1 down | No Work Order entered | No Work Order entered into Delay Log
62 | 2018 | 2018-04-02 | Carolina | Hydraulic | None | 91.61 | Main Pump | Bearings/Shafts | 4206218 | None | Port Thrust Bearing Seal | Work Order cancelled on 7/24/2018
63 | 2018 | 2018-04-03 | 53 | Mechanical | 246 | 29.52 | Main / Aux. Generators | Main Generator | 4206415 | None | Troubleshoot Main Generator #2 | Main generator voltage was fluctuating. Would not stay in parallel. GLDD electrician attended dredge, generator would not stay in parallel. Found transformer set faulty. Replaced with onboard spare. Adjusted voltage output.
64 | 2018 | 2018-04-11 | Ellis Island | Hopper | None | 35.4 | Dredge Pump | Clutch | N/A | None | No Work Order entered | No Work Order entered into Delay Log
65 | 2018 | 2018-04-17 | Alaska | Hydraulic | None | 46.52 | Suction / Discharge Pipe | Dredge Pipeline | 1706604 | broken spool piece on Vosta | Work Order not found | Work Order not found
66 | 2018 | 2018-04-21 | 53 | Mechanical | 240 | 59.1 | Electrical/Electronics | PLC | 4206760 | Holding brake wont release | Repair closing drive line reactor | Converted to SO# 1707010: Labor to repair line reactor in ASEA SCR drive cabinet. Part brought in and repaired at Globaltech's shop on 4/23/2018; reinstalled.
67 | 2018 | 2018-04-30 | Padre Island | Hopper | 242 | 83.43 | Dredge Pump | Pump Bearing Assembly | 1988925 | line shaft bearing coupling | Port dredge pump line shaft hub (pump end) was found with broken gear teeth | As found condition. -Pump side hub and barrel sleeve found to have broken teeth all the way around. - coupling had 4 draghead bolts instead of sheer pins. Parts have been on order and under PO 1706376. Due to high cost of parts the bolts have been sent to be reverse engineered so they can be purchased elsewhere. -After failure, line shaft bearing foundation bolts found to be loose. Could be root cause of failure -Hub gap is 6 7/8". Supposed to be 6" This indicates the line shaft has been adjusted aft beyond normal range. Shaft gets adjusted aft to maintain the impeller to suction liner gap to 1/8". This Could be root cause of failure. -Line shaft found to be 60thou high in comparisan to the gearbox output shaft. Within Tollerance. -Engine side door to impeller is 2" gap -Liner sits inside the stuffing box 1". Chief had to put 5 rings instead of 6. This caused the hp pump gland to leak sand excessively causing premature wear to liner and stuff box. Corrective action. Replace pump side hub and barrel sleeve(hub cover) and plates. Shim backside of the impeller. Between Impeller and shaft with crush rings. MPW stated we can shim the shaft up 1" with crush rings. Stack up 7 crush rings in total of just less then 1". Adjust position of Coupling hub gap to 6" Adjust impeller clearance to 1/8"
68 | 2018 | 2018-05-01 | Ellis Island | Hopper | None | 75.89 | Generator Engine | Other | N/A | None | No Work Order entered | No Work Order entered into Delay Log
69 | 2018 | 2018-05-02 | Carolina | Hydraulic | 243 | 514.2 | Cutter | Gear Box (Cutter Shaft) | 4038139 | None | Open and Inspect Cutter Gearbox failure | Work Order cancelled on 7/24/2018:
70 | 2018 | 2018-05-17 | 53 | Mechanical | None | 401.61 | Crane Boom | Boom / Gantry Structure | 4207327 | Boom Collapse | DR53 boom recovery - FLNG - Teichman Group | Converted to SO# 1707524: No findings
71 | 2018 | 2018-05-21 | Padre Island | Hopper | None | 34.46 | Dredge Pump | Pump Bearing Assembly | 1989070 | None | PS dredge Pp (Falk) Coupling: renew drive shaft hub & sleeve | Mechanical failure of drive teeth of the prime mover end Wrong parts in spares & uninventoried No shear pins available No gasket & seal kit available No economy bushings available Shear pin hardware kit not needed - we have no shear pins
72 | 2018 | 2018-05-22 | Liberty Island | Hopper | None | 532.27 | Main Engine / Propulsion | Propeller | None | None | No Work Order entered | No Work Order entered into Delay Log
73 | 2018 | 2018-05-31 | Terrapin Island | Hopper | None | 163.67 | Other | Other Mechanical | 1708024 | inbound for trunnion repairs at Lyons Shipyard | Work Order not found | Work Order not found
74 | 2018 | 2018-06-01 | 55 | Mechanical | 248 | 54.42 | Electrical/Electronics | PLC | 1708167 | electrical problem | Work Order not found | Work Order not found
75 | 2018 | 2018-06-01 | Texas | Hydraulic | None | 77.31 | Idler / Spud Barge | 177 | None | None | No Work Order entered | No Work Order entered into Delay Log
76 | 2018 | 2018-06-11 | Terrapin Island | Hopper | None | 94.77 | Trunnion Hoist | Other | 1708024 | inbound for repairs | Work Order not found | Work Order not found
77 | 2018 | 2018-06-21 | Padre Island | Hopper | None | 46.07 | Dredge Pump | Other | 1989237 | coupling | Renew PS dredge PP Drive Coupling using new | Pump shaft Hub/Sleeve has appeared to have failed - possibly more B4 starting it was discussed that the entire coupling would be renewed - using in-stock spares Gasket & Seal kit was not in-stock Replacement bolts (28) were not in-stock Upon dis-assembly alignment was in XS of 100/1000's-in incorrect Upon disassembly: Shaft(end)-to-Shaf(end) clearance was 6-7/8 in. Finished it was 6-in. Final alignment: RADIAL (12) 0, (3) +3, (6) 10, (9) +5 RUNOUT (12) 0, (3) -10, (6) -6, (9) +4
78 | 2018 | 2018-07-02 | Liberty Island | Hopper | 254 | 99.47 | Main Engine / Propulsion | Other | N/A | engine shutdown on code red, turbo | No Work Order entered | No Work Order entered into Delay Log
79 | 2018 | 2018-07-03 | Carolina | Hydraulic | 253 | 116.52 | Idler / Spud Barge | GL-10 | None | port connection pin | No Work Order entered | No Work Order entered into Delay Log
80 | 2018 | 2018-07-05 | Texas | Hydraulic | None | 42.2 | Spuds / Xmas Tree | Winch / Hoist System | 0791116 | spud winches won't start | Drive Field Loss troubleshooting | Replaced tw burn wires and two fuses
81 | 2018 | 2018-07-08 | Ellis Island | Hopper | None | 135.95 | Other | Electrical | N/A | to anchor to assess INGETEAM system failure | No Work Order entered | No Work Order entered into Delay Log
82 | 2018 | 2018-07-10 | Liberty Island | Hopper | None | 47.98 | Main Engine / Propulsion | Other | 0848100 | pump out at reduced RPM and reduced density; port M/E turbo overheating | Troubleshoot issues with PORT M/E turbo inlet temps high | No findings as of 7/10/18 jrm S/R CREATED FOR TECHS TO COME OUT 0848103
83 | 2018 | 2018-07-11 | Carolina | Hydraulic | None | 101.51 | Ladder Pump | Gearbox (Ladder Pump) | 4038173 | Gear box cooling system not working | Ladder Pump (UWP Gear box bearing replacement) | Bad bearing on output shaft Thrust. Removend top on uwp gear box. Inspected H/S & intermediate bearings in box ,Looked ok. Removed L/S shaft & sent cmmc to have Thrust bearing changed on shafting. After inspection of bearing we had on hand ! Was determined that bearing was not useable. Having new bearing over nighted from timken to cmmc. After feather inspection on H/S & intermediate bearing we have on hand it was found bearing were not useable. ( bad pitting in rollers) Started inspection on shafting on uwp found coupling at thrust bearing had lots of were and needed to be changed out. After L/S shaft came back from cmmc installed in box. After install checked measurements between coupling & was out of tolerance. Add shimming material between shift 1 & 2 to bring thrust back with in tolerance, Add 1" of shimming to shafting. After changing # 2 shaft and checking alignment on thrust bearing. Tested run gear box & watch temps on bearings, Looked ok.
84 | 2018 | 2018-07-28 | Ellis Island | Hopper | None | 379.92 | Other | Other Mechanical | N/A | Secure from dredge operations in preparation for yard period | No Work Order entered | No Work Order entered into Delay Log
85 | 2018 | 2018-07-29 | Illinois | Hydraulic | None | 114.9 | Ladder Pump | Motor / Engine | 0309370 | trip off; oil seal blew out; underway to rockaway 1413; arr 1645 | Ladder pump motor #006 installation | Meg test on spare replacement # 006 motor prior to installation = 250 meg @ 500 vdc Flushed all oil circulation pipes and flushed out vacuum tank. Replaced the oil filter on the circulation pump system.
86 | 2018 | 2018-08-07 | Liberty Island | Hopper | None | 70.89 | Main Engine / Propulsion | Other | 0848286 | Oil in cooling water | Troubleshoot STBD dredge pump prelube motor tripping out | After wiring up motor to check for proper rotation new motor would not start. Upon further investigation it was found that the auxillary contacts were welded together and damage by loose screw (ARC DAMAGE TO CONTACT) New contact installed and rotation verified.
87 | 2018 | 2018-08-08 | Carolina | Hydraulic | None | 55.68 | Cutter | Motor (Cutter Shaft) | 4038240 | change out port blower | Port Cutter Motor Blower (change out) | Port cutter motor tripped out. watch engineer looked into port cutter motor tripping out. Did'nt see anythang wrong. Reseat drive and told leaverman to try it. at that point sow sparking inside of canister & a red glowing inside of blower drive box. immadiately killed all power going to cutter drive and lock out. opened blower drive cabinet and found that MOV for blower motor was burned out. found one and changed out. Checked fues in drive found (2) bad changed out. Open cutter canister to check blower motors. found lower blower motor bearings were bad. At this time started towing dredge inside for repair's. Remoived top off cutter canister to remove blower moter. Removed old motor and installed new. checked rotation on motor, was good. Cleaned gasket area and resealed.And installed top back on caister.
88 | 2018 | 2018-08-11 | Texas | Hydraulic | 258 | 137.87 | Spuds / Xmas Tree | Winch / Hoist System | 0791277 | busted port breast winch | Port Stern Winch Removal | * All bearing cap bolts were replaced on port winch and torque to 600 ft/lbs / 40% yield of grade B7 stud during recent repair installation. * Pillar block feet torque value - * . The gears are rough and not to a set pattern. Maintenece dept and crew agreed to run to wear for establishing a set pattern.
89 | 2018 | 2018-08-12 | Carolina | Hydraulic | None | 63.5 | Cutter | Motor (Cutter Shaft) | 4038342 | replace cutter motor | Air Compressor Set #2, change bad oil sample | Wrong WO# entered into EDL. EDL WO refers to: "Air Compressor Set #2, change bad oil sample" on 12/29.
90 | 2018 | 2018-08-17 | Carolina | Hydraulic | None | 38.5 | Spuds / Xmas Tree | Walking Spud | 4209697 | weld crack in GL-10 spud | Repair crack in spud | 14 INCH crack running horizonally at bouful plate just above sheaves Drilled a 1" hole in spud at crack location Put nipple in and welded Air arced crack out and put holes at end of crack Welded the root pass with a solid wire and the rest wit a flux core wire
91 | 2018 | 2018-08-17 | Padre Island | Hopper | None | 31 | Generator Engine | Other | 1989653 | Generator Timing issue | SB Genset Engine needs tech support to correct engine not operating correctly | Converted to SO# 1710522: Reset Fuel Camshaft timing & torque drive gear to shaft Timing gear has been slipping on tapered shaft connection Run engine with electrical load, test. Then put genset in STBY
92 | 2018 | 2018-08-19 | Illinois | Hydraulic | None | 94.92 | Cutter | Gear Box (Cutter Shaft) | 4209827 | underway 1622; anchor 2011 | cutter gearbox oil seal replacement (Stbd input pinion) | FOUND LEAKING SEAL TO BE PITTED ON BOTH IT'S TWO LAPPED MATING SURFACES, AND CONTAMINATED WITH DIRT AND DEBRIS. REPLACED WITH NEW OIL SEAL. ---- (Mechanical Seal, High Speed Shaft, Cutter Gearbox Single Spring Type T- 8-1V0, (Per Drawing No. Ga-119282-1, Gldd Dwg # 110-02-23594) P/N M192780 Shaft Diameter: 6.500" Seal Size: 7.500" 0.006" radial movement measured for the starboard pinion shaft. Thrust end-play measurement 0.005" for the starboard pinion shaft.
93 | 2018 | 2018-08-24 | Carolina | Hydraulic | None | 48.2 | Idler / Spud Barge | GL-10 | 4038551 | Spud roller | Cutter motor (Speed control not reading) | Wrong WO# entered into EDL. EDL WO refers to: "Cutter motor (Speed control not reading)" on 12/17.
94 | 2018 | 2018-08-30 | Illinois | Hydraulic | None | 420.29 | Main Pump | Engine/Motor | 4210011 / 0309395 | None | Dredge Pump Rebuild / Thrust Shaft Replacement | WO# 4210011:SS LINER (NO NUMBER), INNER SHELL (140362-3-1 1676099) & ES LINER (150417-2-1 1687395) ALL HAD SIGNIFICANT WEAR. TOTAL YARDS ON ALL THREE WET END PARTS: 96" 4 VANE IMPELLER (140225-3-1 1675685) HAD SIGNIFICANT WEAR AND NEEDS TO BE SCRAPT TOTAL YARDS: 1,063,792 CY, LBI PROJECT 475,701 CY, SHEP PROJECT 355,517 CY, CAPE MAY PROJECT 815,771 CY, MOREHEAD CITY PROJECT 129,649 CY, AVALON PROJECT 5,210,782 CY, PHILLY TO THE SEA PROJECT TOTAL : 8,051,212 CY. NEW PARTS: SS LINER: 160304 1693774 ES LINER: 170046-9-1 1697652 INNER SHELL: 150431-1-1 1687394 96" 4 VANE IMPELLER: 150346-1-1 1686365 WO# 0309395: SPARE REPLACEMENT SHAFT SURFACE AREA WHERE THE SLEEVE COVERS WAS PITTED WITH RUST, AND DETERIORATED APPROXIMATELY 25% OF IT'S LENGTH., SET THRUST CLEARANCE TO 0.30"
95 | 2018 | 2018-09-06 | Padre Island | Hopper | None | 24.91 | Piping / Hoses | Lower Drag Arm | 1989760 | None | Lower Dragarm, STBD replace | Work on lower starboard dragarm began at 0800 6 September. Draghead, dragarm, jet lines, hoses removed. New equipment installed. Complet @ 0300 7 August
96 | 2018 | 2018-09-15 | 54 | Mechanical | 263 | 123.72 | Spud System | Spud Structure | 4210372 | broken gear box | Investigate and repair STBD spud gear box: | Converted to SO# 1712686: During initial investigation, it was noticed there was a cracked tooth on the input shaft as viewed through the access plate. Neeed Accounting te re activate Chalmers and Kubeck to create PO - RG 9/17
97 | 2018 | 2018-09-22 | Illinois | Hydraulic | None | 84.87 | Swing System | Winch System | 0309411 | None | Inspect and repair Synch motor soft start / excter field | Converted to SO# 1712789: Findings from Chris Slimmer -- I received a call from the Illinois crew on Saturday night Sept 22nd 2018. The MG motor starter had faulted. Working with Van on the phone Saturday night it was determined that there was a problem with the synchronous field controller, and that the controller would need parts and an operational check. Due to impending weather, the dredge was towed in. I worked with the Benshaw emergency service line on Sunday, and a survey of the pictures provided by the Illinois crew showed a cracked SCR pack, and a heated up and corroded wire on the B phase of the 250VAC power supply to the field SCR’s. I changed my travel destination to arrive Monday evening in New York. Monday morning I was able to get a quote from Steiner Electric via Benshaw for a field service tech to attend to the field controller repair. A tech was scheduled to travel Tuesday morning to NYC and the Illinois. Tuesday morning using information from Chief Craig, I purchased wire and other hardware to initiate replacement of the faulty wire prior to the arrival of the Benshaw tech. Once on the Illinois, it was found that the B phase feed wire, terminal strip and SCR pack showed signs of excessive heat. Most likely this was caused due to a loose connection on the SCR pack heating up and the heat migrating thru the incoming wire and terminal block. This wire was replaced from the 250VAC fuses in the back of the cabinet to the forward control compartment. Upon arrival of the Benshaw tech, he removed and replaced all three SCR packs, and checked all of the controller wiring. He also checked the 2400 VAC starter section of the system. Due to some issues with the fit of the new parts and finding a miss wiring issue, we did not test the starter until after 7PM Tuesday night. While the MG motor ramped up correctly, the field power was not working correctly. Due to the late hour, and the fact that the Illinois was not returning to work until Thursday or later, we left the Illinois at 8PM to resume fault finding Wednesday. The Benshaw tech and myself arrived at the Illinois at 8AM. The tech removed one of the replacement SCR packs to check the I/O arrangement. Inspection of the old and new SCR packs found a change in connection pattern, a switch in the cathode and gate wires on one side of the packs. After the wiring was changed, we fired up the 2400VAC and tested the starter. After the soft start ran the motor up, and across the line, the field controller brought the field up to 37A. We fired up the swing and cutter systems, and both worked correctly. We ran the MG motor for around an hour. Checking of the heat inside the field controller cabinet showed around 115F on the SCR packs after running an hour. The Benshaw tech deemed this a normal temp, and we shut the MG starter down. We did complete one more start sequence to check the MG starter one more time, all worked well. The Benshaw tech left the Illinois at 11AM. As to corrective action to prevent this fault from occurring again, I would recommend a standard job to check tightness of the SCR connections once a year. And a bi-annual check of the heat balance between the three phases inside the field cabinet.
98 | 2018 | 2018-09-26 | Texas | Hydraulic | None | 53.9 | Ladder Pump | Pump Leak | 0791412 | Replace rubber hose behind UWP |  | Max5 B03 rubber spool replacement: ** Hole worn in short expansion hose * Elbow worn thru line and epoxied for reinstall. 88 Patched and deferred to drydocking for replacement,
99 | 2018 | 2018-10-16 | Illinois | Hydraulic | None | 179.52 | Suction / Discharge Pipe | Dredge Pipeline | 4211146 | None | Repair/Replace collapsed suction pipe | FOUND SUCTION PIPE, ATTACHED TO MOUTH PIECE COLLASPED. REPLACED 8' SECTION. FOUND NEXT 21' TO ONLY BE 1/8" THICK ON BOTTOM. LINNED INSIDE BOTTOM THIRD WITH 1" PIPE. ALL LADDER PIPE WAS SUPPOSED TO BE SOUNDED BY SHIPYARD 4 MONTHS AGO. THEY REPORTED NOTHIG LESS THAN 1/2".
100 | 2018 | 2018-10-17 | Terrapin Island | Hopper | None | 224.43 | Main Engine / Propulsion | Other | 4180731 | None | Investigate noise coming from No.1 left cylinder M/E (Stbd) | During morning rounds C/E heard soming coming from the No. 1 left fuel pump area, Had 1st Engineer listen and he heard soming from the valve train area. Engine was shut down and the valve cover was removed and found the intake valve bridge was broken. The dry sump inspection coveres were removed for inspection of cam shafts. Found damage on No. 1 left exhaust lobe, considerable wear for 16 hours of operation, found exhaust cam lobe damage on No. 6 Left found exhaust cam lobe damage on No. 4 Right. Notified Mike Kraljevic and Spencer Garret of Waymore Power and it was decided not to try and run theengine again until what is causing the problem found. The decision was made to pull the cylinder heads on No. 1 & 6 left and No. 4 Right and send them to Waymore Power for inspection to find out if this was a component problem with the rebuilt heads. Sent a total of 5 heads, heads had been removed during the origianl problem. Fuel Pump Supports removed from 1 & 6 left and 4 right. 10-18-19 Crew removed the jacket water piping in prep for cam shaft removal. Unbolted right side cam sections 1-2 and 3-4 to allow for removal, Had to remove fuel pump support on No. 5 right 10-19-18 Crew pulled cam sections 1 - 2 and 3-4 right. Installed new cam section for 3-4 right (P/N: 2160219) and installed cam section 1-2 right. Torqued the stud bolts and installed cam shaft ballancer housing and ballance, torqued the studs and insatlled cover and overspeed trip assembly. INstalled fuel pump supports on the right side and started removing the left side fuel pump supports removed the left side cam shaft ballancer and housing. Started removing all exhaust bolts from cylinder heads in prep for the change out of all heads by Waymore Power Note: Conferance call with Mike K and Waymore and C/E today. No smoking gun found but there is some issue with maybe the valve clips and the rotators, so the decision was made that Waymore will rebuild 15 new heads with know vendor parts and have them shipped down to Albany for replacment of heads on Stbd MAin ENgine. One head will be taken from the Terrapin stock and rebuilt with new parts brought by Waymore Power.) 10-20-18 Pulled reaminder of heads from left bank Pulled out cam section 1-2, 3-5, 5-6 on left bank. Sections 1-2, 5-6 will be changed out and will reuse section 3-4 Heads removed from right bank Cleaned all parts in prep for rebuild 10-21-18 Cleaning Exhaust and intake flanges Lapping liner / head seats on block Continued preping for cam, head change when Waymore Power arrives 10-22-18 Waymore Power arrived in Afternoon Lowerd parts into engine space started to install oil, drain, and push rod jumpes onto hew heads. 10-23-18 Waymore power working on Engine, Installing left bank cam sections, ( all but section 1-2) Part is being shipped from Canada Waymore taking readings on all new heads, ( not rebuilt yet) waiting on Parts from Waymore chainging out bad lifters and rollers on left bank 10-24-18 Waiting on parts from Canada 10-25-18 Parts arrived from Canada and spare heads are being built and installed. Waymore got all heads installed and water ready Terrapin crew finished up install of cam sec 1-2 left and installed balancer and closed up. Crew installed after cooler cover and all jacket water piping. Waymore left for the day, Crew continued and installed and torqued the valve train and started to fill engine with water. water started to pour from No. 3 head, inspection forund that a freeze plug had been left out. Pulled head and prepped for intallation of a spare head. 10-26-18 Crew pressure tested spare head on Port side, all ok. Moved head to stbd side and installed Springs and new valve rotators. Cleaned and inspected dry sump Installed head and connected exhaust / intake piping. Waymore completed head install and torqued. Waymore set fuel pump timing and valve lash. Engine was pre lubed and all looked good. Engine was started and a few exhaust / fuel leaks were noted. Engine was shut down and repaired exhaust and fuel leaks Engine was restarted and let run for 1 hour. Engine was shut down and cam / and rollers inspected. All ok Dredge left the dock and back to work. 1800 Engine was secured and an inspection was done on the cams and rollers, All looks good. repaired Air intake leak at No. 7 left and tightend crab bolts on all heads (exhaust) 1930, engine back on line
101 | 2018 | 2018-10-20 | Ellis Island | Hopper | None | 45.89 | Dredge Pump | Other | N/A | dredge pumps clutch out during pump out | No Work Order entered | No Work Order entered into Delay Log
102 | 2018 | 2018-10-22 | Alaska | Hydraulic | None | 46.13 | Generators | Main Generator | 4211171 | ECM Main Gen | Troubleshoot and Repair generator EMDEC | Converted to SO# 1714014: During normal operations of the main generator all inputs to the EMDEC disappeared and the engine went to idle and the generator breaker tripped. Power supply batterries were changed with new batterries and the engine was started and placed online. The generator ran for 4 hours and then the EMDEC failed again and tripped the engine offline.
103 | 2018 | 2018-10-24 | Illinois | Hydraulic | None | 36.62 | Ladder | Ladder Winch | 0309443 | Ladder hoist computer | Ladder hoist drive troubleshooting: | 1.Replaced micro logix processor, Backup battery, Memory module and installed program. 2. Replaced Avtron CPU board and System board. 3. Configured networking IP Addresses for Avtron, Allen Bradley panel view and Micro Logix processor. 4. Verified Avtron parameters.
104 | 2018 | 2018-10-27 | Alaska | Hydraulic | 235 | 122.54 | Suction / Discharge Pipe | Dredge Pipeline | 1728360 | None | Change 34" suction pipe | No Description / No findings.
105 | 2018 | 2018-10-29 | Dodge Island | Hopper | None | 116.77 | Dredge Pump Engine | Gearbox | 4069836 | None | Stbd dredge pump gear box - investigae and disassembly | The Starboard Dredge Pump Gearbox input shaft & bearing failed. The shaft was cut in two and the heat melted out the seal assembly and damaged the clutch as well. Jake from MSI came out to assist in the replacement of the failed gear assembly. The reduction gear and input gear were replaced and the clutch was replaced at this time also.
106 | 2018 | 2018-11-05 | Liberty Island | Hopper | None | 72.99 | Other | Electrical | N/A | automation reset to correct skimmer issues | No Work Order entered | No Work Order entered into Delay Log
107 | 2018 | 2018-11-07 | Ellis Island | Hopper | None | 73.54 | Dredge Pump | Impeller | N/A | replace impeller with 80 inch trimmed impeller | No Work Order entered | No Work Order entered into Delay Log
108 | 2018 | 2018-12-12 | Carolina | Hydraulic | None | 36.52 | Ladder Pump | Bearings/Shafts | 4038336 | change 20 cutter teeth | UWP Thrust bearing (repair leaks or change out) | Found thrust bearing leaking oil from seal on gland seal end of thrust bearing. Also leaking at split line on same end. Changed out thrust bearing with one we have on hand. front seal looked like it was starting deterge where both services meet.
109 | 2018 | 2018-12-27 | Terrapin Island | Hopper | None | 29.84 | Other | Hopper | 4180999 | No. 6 bottom door reach rod pulled away from cyl. rod | # 6 hopper door cylinder and reach rod assembly - replace | found # 6 cylinder connecting yoke pulled off cylinder Completed at EPIC shipyard by the yard workers. No shipboard labor used.
110 | 2018 | 2018-12-28 | Liberty Island | Hopper | None | 84.36 | Other | Other Mechanical | N/A | Dock - Pascagoula | No Work Order entered | No Work Order entered into Delay Log
111 | 2018 | 2018-12-30 | 55 | Mechanical | None | 24.16 | Main Hoist | Holder | 4212279 | Holding friction will not disengage, Rep. Holding br. | Weld holder brake cylinder bracket back down | LAST NIGHT WHILE THE OPERATOR WAS DIGGING THE BRACKET THAT HOLDS THE TWO CYLINDERS FOR THE DIGGING BRAKES PULLED OFF THE DECK. THIS IS FOR THE HOLDER DRUM. WELD BRACKETS THAT THE TWO CYLINDER FOR THE DIGGING BRAKES BOLT TO. REMOVE ALL LINKAGE AND CYLINDERS. CUT THE LITTLE WELD THAT WAS LEFT AND WELD BACK IN PLACE. PUT EXTRA WELD AND GUSSETS FOR MORE STRENGTH.
112 | 2019 | 2019-01-01 | Alaska | Hydraulic | None | 95.14 | Ladder Pump | Motor/Engine | 1728433 | Oil leak | Ladder Pump Motor (1250 HP) removal | The output seal from the motor to the pump failed discharging oil into the water. Oil system was secured and spilled oil was cleaned up. ECM services, USCG and DSHEM were notified of the spill and the clean up. Motor removed and new motor installed
113 | 2019 | 2019-01-04 | Ellis Island | Hopper | None | 35.54 | Trunnion Hoist | Other | None | none | No Work Order entered | No Work Order entered into Delay Log
114 | 2019 | 2019-01-06 | Illinois | Hydraulic | None | 49.55 | Main Pump | Pump rebuild | 4212137 | None | Dredge Pump Rebuild | ALL WET END PARTS FOUND TO HAVE SIGNIFICANT WEAR. PUMP DOOR HAD SOME DAMAGE DUE TO SEVERAL HOLES IN THE LINER. REPAIRED ALL WEAR BY BUILDING BACK UP WITH WELD. IMPELLER (150346-1-1 1686365), WAS NEW WHNE INSTALLED BUT HAD AN AREA ON THE BACK SIDE THAT WAS WORN PRETTY GOOD. WE REPLACED IT. TOTAL YARDS PUMPED: 2,853,903 CYS. SS LINER (160304 1693774), ES LINER (170046-9-1 1697652), INNER SHELL (150431-1-1) TOTAL YARDS PUMPED: 2,853,903 CYS. NEW PARTS INSTALLED: ES LINER: 170119-1-1 169986 SS LINER: 160314-6-1 1693432 INNER SHELL: 160174-1-1 1691594 IMPELLER: (170046-8-1 1697652) 97" 4 VANE
115 | 2019 | 2019-01-13 | Dodge Island | Hopper | None | 129.65 | Main Engine / Propulsion | Other (repairs) | 4070010 | None | Repair gear train failure | the engine was found to have multiple teeth failures on the #2 idler gear and on the main drive gear. the drive tube and counterbalance weight had to be removed to change the drive gear. The counterbalance weight had to be removed prior to the removal of the drive tube due to clearances between the drive hub and the flywheel. a total of eight heads were replaced along with the drive gear and #2 idler gear. For complete details see NRE report (attached) (*RAM Team - did not see any attachments in WO)
116 | 2019 | 2019-01-24 | Liberty Island | Hopper | None | 140.2 | Drag Head | Other | 0848934 | Parted PORT Draghead wire; at port for replace | Repair dragarm calbes due to gimbal failure | 65' cable pulled out from both junction boxes. damaged 12' cables to horizontal and vertical sensors. Also replaced upper pipe verticle sensor.
117 | 2019 | 2019-01-24 | Terrapin Island | Hopper | None | 46 | Main Engine / Propulsion | Propeller | 4181088 | Removing 3 foot shell form STBD pump, replacing impellor and fix pump | Replace STBD dredge pump impeller and remove UXO | A UXO was dug up and it did extensive damage to the dredge pump impeller. completed by: S. Taylor S. Caffy J. Allen A. Pittman J. Bradford J. Gager J. Sinclair
118 | 2019 | 2019-01-26 | Carolina | Hydraulic | None | 26.11 | Main Pump | Bearings/Shafts | 4038374 | Change thrust bearing | R&R thrusting bearing assembly | We found the bearing to have 0.072 in. of vertical movement in the front bearing. The shaft looks to be bent 0.065 in.
119 | 2019 | 2019-01-27 | Dodge Island | Hopper | None | 58.27 | Main Engine / Propulsion | Other (repairs) | 4069968 | Main Engine | Repairs to PORT Generator | The end bell NTN brand bearing with a pressed metal cage had a cage failure. This caused a bind from uneven bearing balls and the outer bearing race broke, and the exciter bottomed out causing the exciter to drop the load. There was grease in the bearing and no sign of overheating. I recommend that a KATO bearing be used. DCB A double shielded NTN 63317C3 Bearing was ordered by MSK and installed. It was the same bearing previously used. DCB
120 | 2019 | 2019-02-06 | Liberty Island | Hopper | None | 82.7 | Generator Engine | Other | 0848946 | Failure STBD Gen Eng; swapping generators | Ships crew to remove STBD Gen set (kato) due to electrical failure | Generator has extensive damage to the stator assembly. The generator had a complete failure 02-09-19 New kato generator installed. signed off by ABS and USCG. departed Talleyrand (Jacksonville, Fl.) pier side in route to Mayport dredging project.
121 | 2019 | 2019-02-12 | Dodge Island | Hopper | None | 29.72 | Main Engine / Propulsion | Other (repairs) | 4070060 | Air in Jacket Water | Port M/E - Troubleshoot and Repair | 2/11/19 The Port Main Engine started getting LOW JACKET WATER PRESSURE alarms. After bleeding air from the system, the condition returned several times. The engine cooling water system was pressurized using potable water supply pressure, followed by a cylinder test cock blow down. This exposed a leak somewhere in the #12 cylinder power assembly after witnessing water being ejected from the #12 cylinder test cock. The cylinder head was removed to try to identify the leak. The head, head gasket & grommets appeared ok, so we replaced the power assembly using the short pack method to insure the problem would be corrected. A Blade assembly was used (even though #12 Cylinder is a fork) because we could not confirm during off hours that the EMD power pack was compatible with the NRE Assembly. DCB
122 | 2019 | 2019-02-17 | Ohio | Hydraulic | None | 95.92 | Main Pump | Pump rebuild | 4173127 | Continue maintenance program, change liner pump number one | Fix Pump no.1 leak | 1-clean up still ok 2-front door & liner ok 3-impeller ok 4-rotate suction side liner 90 degree
123 | 2019 | 2019-02-18 | 55 | Mechanical | None | 95.27 | Main / Aux Gen | Main Generator Eng | 4213134 | None | Mechanic to troubleshoot M/E | Converted to SO# 1719081: Provide the labor, material and equipment as required to accomplish the following: 1. Inspect engine to locate reason for brass shavings to found in oil filter / oil sump 2. After fault is located, provide GLDD with material and labor cost for repairs
124 | 2019 | 2019-02-26 | 53 | Mechanical | 286? | 123.75 | Main Hoist | Holder | N/A | Holder motor repair | No Work Order entered | No Work Order entered into Delay Log
125 | 2019 | 2019-03-06 | Illinois | Hydraulic | None | 35.41 | Ladder Pump | Pump rebuild | 1578760 | Change runner out change 15 cutter teeth 5 bosses broke off 1 no good | Work Order not found | Work Order not found
126 | 2019 | 2019-03-14 | Carolina | Hydraulic | None | 40.2 | Spuds / Xmas Tree | Walking Spud | 4038414 | None | A/C switch Gear Room (trouble shut not coming on) | Wrong WO# entered into EDL. EDL WO refers to: "A/C switch Gear Room (trouble shut not coming on" on 3/1
127 | 2019 | 2019-03-24 | 53 | Mechanical | None | 101.08 | Main / Aux Gen. | Main Generator | 4213939 | Generator issues | Cat Tech to diagnose engine hunting issue Cat #2 | Converted to SO# 1720533: Replaced actuator on Engine #2. Deepsea and Woodward out of adjustment, Pan america and Cat came to make adjustments
128 | 2019 | 2019-03-31 | 53 | Mechanical | None | 35.03 | Main Hoist | Closer Wire | None | Change jackline in 18yd bucket/change becket inside 18yd bucket (found broken ear on becket), cut back closer and holder hoist cables. Change tagline cable due to broken wires @ drum | No Work Order entered | No Work Order entered into Delay Log
129 | 2019 | 2019-03-31 | Ellis Island | Hopper | None | 31.76 | Drag Head | Other (repairs) | N/A | none | No Work Order entered | No Work Order entered into Delay Log
130 | 2019 | 2019-04-02 | Texas | Hydraulic | None | 49.47 | Cutter | Motor | 0791490 | None | Cutter motor removal | Motor is shot needs replacement.
131 | 2019 | 2019-04-09 | Liberty Island | Hopper | None | 167.7 | Jet Pump | Other | None | Drag Head blown out; unable to cont using jets | No Work Order entered | No Work Order entered into Delay Log
132 | 2019 | 2019-04-09 | Terrapin Island | Hopper | None | 28.08 | Other | Other mechanical | 4181401 | Hit by fishing vessel | Inspection | Possible wrong WO? 4-5-19: Low lube oil pressure alarm, investigated and found oil leaking out Int. Pinion & Shaft oil seal. (Seal failure) Had bridge pull back engine and clutch out, oil still leaking considerably. Engine secured and decision made to inspect shafts for bearing issues. Started to pull clutch assembly out to allow for checks. Inspected internals and no problems noted, disassembled clutch assembly to allow for inspection of seal area and shaft bearings. Attempted to remove clutch splined hub, could not get to move. New pulling jig made. 4-6-18: Pulled the Clutch splined hub. put pry bar on clutch adapter and attempted to move the shaft, considerable play in shaft, .030 up and down play. Passed along info to maintenance manager. Pulled the clutch adapter and pulled out the shaft seal, once seal out you could see the outermost bearing had failed. roller cage broken. Tried to pull off bearing, shaft started to pull out of box. Inspection inside box showed the Pinion and spider gear has moved apart, moved shaft inward to mesh gears, but it looks like the inner bearing on the spider shaft has moved out of the bearing bore, not completely in bore. Shaft could be turning in the bearing or the bearing could be turning in the bore. Decision made to attempt to split box in place and do a more thorow inspection 4-7-19: Crew prepping for box top removal. 4-8-19: Box prepped for complete removal 4-9-18: Box removed from vessel and put on truck to Dana for repair.
133 | 2019 | 2019-04-19 | Texas | Hydraulic | None | 47.21 | Cutter | Cutter canister (cutter shaft) | 0791491 | None | Cutter motor installation | Final torque on foundation bolts was 2700Psi.
134 | 2019 | 2019-04-24 | 53 | Mechanical | None | 149.93 | Main Hoist | Holder | 4213300 | Troubleshoot holder | Remove and Replace Holding Motor | At this time, the Motor is not going to be changed out
135 | 2019 | 2019-04-26 | Texas | Hydraulic | 298 | 79.09 | Cutter | Motor | 0791516 | None | Cutter motor removal | Motor was going dead ground.
136 | 2019 | 2019-05-01 | Texas | Hydraulic | None | 25.35 | Cutter | SCR Drive/MG Set | 4214929 | None | Rebuild D-32 DC Motor (#7) | Converted to SO# 1722436: Notes: 1. Motor removed due to failure from overload/ overheating 2. #7 was replaced by #3
137 | 2019 | 2019-05-05 | 53 | Mechanical | None | 45.96 | Spud System | Spud Structure | 1193339 | Cracked / Broken Stern Spud | Remove Stern Spud | spud is out and on the dock at BAE
138 | 2019 | 2019-05-12 | Ellis Island | Hopper | None | 190.34 | Drag Head | Other (repairs) | N/A | Hull ruptured from STBD Draghead casualty. Anchor for Inspection | No Work Order entered | No Work Order entered into Delay Log
139 | 2019 | 2019-06-09 | Illinois | Hydraulic | None | 83.23 | Cutter | Motor (Cutter Shaft) | 0309607 | None | Cutter motor (PORT) removal and installation of spare | No findings.
140 | 2019 | 2019-06-15 | Terrapin Island | Hopper | None | 35.58 | Dredge Pump Engine | Other | 4181774 | Crank case High temp – Port Drag-arm down | Low engine speed / turbo change / replace cyl head | Investigate problem with engine only being able to attain 800 rpm. Bridge had said the engine would not go over 800 RPM's Inspected air connection to governor, all ok verified 60 pri to speed control (full speed request) , all ok Noticed all cylinder temps running 1150 deg and no air inlet pressure (turbo boost) Secured engine and pulled the air intake elbow backl from the turbo inlet and found the rotor to be dragging and hanging up. Turbo needs to be pulled Turbo changed out and system engine filled with water Had to fabricate oil fitting to turbo, fitting on turbo removed was NPT, and replacement turbo used a SAE-ORB fitting. ran oil pump and verified lube oil to turbo, all ok cranked engine and checked all pressure, all ok. Turbo had a water cooling leak, engine was shut down and water drained to allow for repair. Repaired made and engine filled with water and started, all ok.
141 | 2019 | 2019-06-25 | Liberty Island | Hopper | None | 27.9 | Drag Head | Other | 0849330 | Norfolk | Retrieve broken STBD draghead on end of lower dragarm pipe | There were no gussets at either flange of the recently installed new lower drag arm pipe. This is why the draghead was ripped off the end of the pipe. Bringing the draghead onboard went well. we were able to bring the arm onboard by swing in the draghead davit slowly and getting the broken draghead to clear the bulwark.
142 | 2019 | 2019-07-02 | Ellis Island | Hopper | None | 26.52 | Main Engine / Propulsion | Other (repairs) | 4271273 | none | Troubleshoot and repair SME clutched in, not coming up to speed | SME randomly lost speed, still clutched in, low speed clutch. Speed would not return to normal levels. Speed would respond fine from MaK panel, and locally. Would work in NFU. Checked cabeling to and from governor, and signal was getting to governor. Finally found on the 24VDC side inside Woodward governor panel that there were 2 1 amp diodes cracked. 24 VDC on the incoming, 8VDC coming out. Site was able to find some at a local electrical supply, and get them to the dredge. ETO replaced, tested all SAT. Spares on hand in cabinet.
143 | 2019 | 2019-07-02 | Liberty Island | Hopper | None | 72.1 | Gimbal Hoist | Other | 0849382 | Fixing PORT side pad eyes | Replace PORT and STBD dragarm gimbal lifting padeyes | Provide the labor, material and equipment as required to accomplish the following: 1. Remove and replace with new (owner provided) both the port and stbd dragarm gimbal lifting pad eye. 2. Work to be completed to satisfaction of owners rep Mark Hayes.
144 | 2019 | 2019-07-05 | Illinois | Hydraulic | None | 100.17 | Main Pump | Pump rebuild | 4214253 | None | Dredge Pump Rebuild | Found two holes thru inner shell and some wear to door liner. Replaced both inner shell and door liner. NEW SHELL: 170233-3-1 1699547 SS LINER: 170233-2-1 1699547 OLD SHELL HAD 2.9 MILLION YARDS OLD LINER HAD 1.25 MILLION YARDS
145 | 2019 | 2019-07-13 | 54 | Mechanical | None | 31.79 | Electrical/Electronics | PLC | 4251678 | PLC lost memory | troubleshoot main crane PLC | Crane would start and run but cab controls would not work, PLC lost it's memory
146 | 2019 | 2019-07-16 | 53 | Mechanical | None | 41.92 | Spud System | Spud Wires | 1193483 | STBD spud wire broke | Port Spud bottom wire change | wire replaced
147 | 2019 | 2019-07-20 | 55 | Mechanical | None | 26.48 | Main / Aux Gen | Main Generator | 1725905 | Change governor | Work Order not found | Work Order not found
148 | 2019 | 2019-07-29 | 54 | Mechanical | None | 32.97 | Spud System | Spud Structure | 4218307 | Stern Spud brake band foundation mount | Repair foundation / brake band support for stern spud | new plate with original clevis was installed, and found to be a little off alinement causing band not to fully apply to drum, this is causing the brake to slip and will have to run a while to break in band, also found the brake air cylinder sticking. Replaced with spare and found we did not have a air cylinder problem, it just needs to be properly adjusted so spring can push cylinder rod back into cylinder. brake system is operating good, but some minor adjustments needed, will be done at downtime op.
149 | 2019 | 2019-07-30 | 55 | Mechanical | None | 927.37 | Main / Aux Gen | Main Generator Eng | 4219354 | Shutdown | EMD Shutdown | 1. With engine running, verify good fuel pressure 2. If good fuel pressure, verify governor has proper amount of oil 3. Next check the electronic wire connector at governor, look for bad or broke wire connection at governor 4. Check fuel rack operation, Couldn't find any issues reset breaker Notes: 1. Bean have this problem haven’t found cause
150 | 2019 | 2019-08-02 | Padre Island | Hopper | None | 30.18 | Generator Engine | Other (repairs) | 1726429 | Rear Seal | Derrick #65 - annual crane inspection | Wrong WO# entered into EDL. EDL WO refers to: "Derrick #65 Annual crane inspection" on 3/17/2017.
151 | 2019 | 2019-09-01 | 58 | Mechanical | None | 315.49 | Main Hoist | Closer | 4218790 | Closing sheave damaged | Remove and replace sheaves at boom point | Converted to SO# 1727611: 1. Requirements: Provide all parts, services and labor to: A. Remove and install owner furnished boom point sheave (X 2). B. Remove and install owner furnished sheave bearings (X 4) C. Remove and install owner furnished sheave seals (X 4) 2. Notes: A. Removal and replacement will require crane service to remove sheave pin and sheave. B. Removal and replacement will require aerial work platform to remove/install securing nut, grease lines, thread cover and pin securing block. C. Welding service will be required to remove/install pin securing block. D. After installation grease the bearings through the shaft grease points to insure that the bearings are receiving grease. 3. Quality assurance. A. Pin securing nut must be torqued to 1,800 - 2,000 lb-ft.
152 | 2019 | 2019-09-10 | Texas | Hydraulic | None | 34.09 | Ladder Pump | Pump rebuild | 4219360 | None | Ladder Pump (Universal) Rebuild | Broken pump shell
153 | 2019 | 2019-09-13 | Carolina | Hydraulic | None | 60.51 | Main Pump | Bearings/Shafts | 4218765 | Main pump #2 thrust bearing getting hot | Main pump thrust bearing (change oil in system) | Changed oil in thrust bearings. Had water from main pumps to get into thrust bearing. Removed oil and cleaned inside of tanks. pumped in new oil. run system oil looks good.
154 | 2019 | 2019-09-13 | Texas | Hydraulic | None | 498.2 | Spuds / Xmas Tree | Walking Spud | 4219453 | None | Repair lower spud gate | Converted to Service Req: Repair lower spud gate Provide the labor, material and equipment as required to accomplish the following: 1. repair are replace lower spud gate 2 gouge out and weld 100% padeye on top gate STBD side
155 | 2019 | 2019-09-29 | 55 | Mechanical | None | 90.25 | Spud System | Spud Winch | 4219808 | None | Replace Intermediate Shaft STBD Spud | Found shaft broke at 2230 on 9/29/19 Removed old shaft Made work orders Contacted machine shop. After installation of new shaft listed below is the Tolerances recorded 3 O’clock 0.003 6 O’clock 0.003 9 O’clock 0.003 Outboard bearing gap (prior to operational test) 12 O’clock 0.000 3 O’clock 0.003 6 O’clock 0.003 9 O’clock 0.003 Gear Backlash 0.010 Tooth contact was within 0.002 of being parallel Inboard bearing temp during operational test stayed around Ambient temp. Outboard bearing temp during operational test stayed around Ambient temp.
156 | 2019 | 2019-09-29 | 58 | Mechanical | None | 70.25 | Electrical/Electronics | MCC/Switch Gear | 4219814 | Swing Tripped out. Blower motor for A/C to drive room burnt out; further inspection shows burn up electrical components in swing drive cabinet. | Troubleshoot and repair swing drive VFD | A burned up rectifier was found after the a/c to the drive room failed. Rectifier obtained from Marinex construction. Rectifier was replaced. Engine started and drive breaker charged and closed, breaker tripped open after 5 seconds. Troubleshooting was conducted point to point to see why the breaker tripped. The dynamic braking module has to be ‘healthy’, if the timer doesn’t get this signal, then the Under Voltage relay trips the breaker. Dynamic Braking Module was replaced (had a spare from Marinex onboard). Breaker stays closed. Voltage was present on the a/c buss to the rectifier and d/c voltage on the buss out of the rectifier, however there appeared to be no power at the VFD controller for either swing motor and the display panels on the doors would not light up. Traced out where the controllers got their power from, there is a small fuse in the very rear of the rectifier assy that was checked. That fuse was blown, it happens sometimes in brand new equipment. Fuse replaced and powered up the controllers and cleared faults. Capt Phil went up to test them and only #1 swing would operate, looked in the cabinet and Run Relay 2 was not energized. Swapped relays between #1 and #2 with the same results, relays tested good. Capt Phil said he didn’t think the brakes were releasing. Looked at both accumulators the one for #2 was secured, aligned air. Run Relay #2 came on and we were able to successfully swing the crane. Failed rectifier assembly Failed Bonitron dynamic braking module Failed fuse in rectifier assy.
157 | 2019 | 2019-09-30 | 53 | Mechanical | None | 33.59 | Crane Swing | Drive (motor, gear box) | 1193566 | Swing tripped | Troubleshoot crane swing | 9-29-19 0930hr, #1 swing will swing both directions when used alone #2 swing will swing slightly to Stbd and not at all to the port When used together the drive trips off. FIFO shows Field loss and Motor II T faults 1200hr, Changed bridge interface board out, no change 1230hr, Found shorted field wire in #1 swing peckerhead, no change 1300hr, Changed microprocessor board out, no change 1330hr, Checked SCRs all good, still no change 1400hr, Checked connections in #2 peckerhead, all connections good, no change 1500hr, Changed out #3 input card, and #5 input card, no change 1530hr, Changed out #10 imput and #11 output card, no change 9-30-19 Function tested SCRs in swing #1 all good Had to reprogram memory chip on the Avtron drive #2 swing back working at 1715 hours
158 | 2019 | 2019-10-03 | Ellis Island | Hopper | None | 273.39 | Other | Other Mechanical (repairs) | N/A | Servicing articouple pads at dock | No Work Order entered | No Work Order entered into Delay Log
159 | 2019 | 2019-10-09 | Carolina | Hydraulic | None | 201.88 | Generators | Main Generator (Eng Rm) | 4219654 | None | Replace wires on drag barge | Wrong WO# entered into EDL. EDL WO refers to: "Replace wires on drag barge" on GL148 deck barge. wires worn out chain bridal broke Calibrated upon completion of wires
160 | 2019 | 2019-10-11 | 53 | Mechanical | None | 59.72 | Spud System | Walking Mechanism | 1193606 | None | Remove stern walking ram to be sent out | No findings.
161 | 2019 | 2019-10-19 | 53 | Mechanical | None | 51.7 | Crane Boom | Boom Winch | 4795201 1730274 | Boom issue; won’t boom down | Replace air cylinder on boom brake | not needed at the moment, will be done in future
162 | 2019 | 2019-10-20 | Sugar Island | Hopper | None | 50.24 | Jet Pump Eng / Deck Gen. | Heat Exchanger | None | None | No Work Order entered | No Work Order entered into Delay Log
163 | 2019 | 2019-10-23 | Illinois | Hydraulic | None | 33.49 | Main Pump | Engine/Motor | 1730667 | None | Work Order not found | Work Order not found
164 | 2019 | 2019-10-24 | Terrapin Island | Hopper | None | 29.1 | Main Engine / Propulsion | Other | 4182054 | Engineers working on STBD Main Engine. Update: anchored in Alpha Anchorage to let engineersdo repairs on STBD cam shaft | Replace no. 1&2-R secion camshaft | Cam lobe Fuel pump #2 and cam lobe fuel pump #4 worn out. replace section no.1 and no.2-R camshaft.
165 | 2019 | 2019-10-30 | Sugar Island | Hopper | None | 147.28 | Jet Pump Eng / Deck Gen. | Other | None | None | No Work Order entered | No Work Order entered into Delay Log
166 | 2019 | 2019-10-31 | Ellis Island | Hopper | 319 | 614.48 | Other | Hopper | None | STBD #5 Hopper door let go from brackets | No Work Order entered | No Work Order entered into Delay Log
167 | 2019 | 2019-11-06 | 58 | Mechanical | 320 | 142.57 | Crane Swing | Drive (motor, gear box) | 1730905 | none | Work Order not found | Work Order not found
168 | 2019 | 2019-11-18 | Terrapin Island | Hopper | None | 77.43 | Hydraulics | Other | 4182079 | Aft Ram sprung leak | Repair V4 Pilot operated valve (Aft closing cylinder) | Pilot rod bushing clearance bigger than spec. and causes the seal to break.
169 | 2019 | 2019-11-23 | Padre Island | Hopper | None | 52.84 | Other | Other Mechanical | N/A | Hole | No Work Order entered | No Work Order entered into Delay Log
170 | 2019 | 2019-12-08 | Illinois | Hydraulic | None | 94.08 | Main Pump | Pump rebuild | 4796036 | Tow to Atlantic City and perform main pump job | Dredge Pump Rebuild | FOUND ALL WET END PARTS TO BE IN GOOD CONDITION. CHANGED 84" IMPELLER TO 96" IMPELLER.
171 | 2019 | 2019-12-10 | Alaska | Hydraulic | 377 | 143.58 | Spuds/Xmas Tree | Sheaves | 4796445 | None | Make necessary repairs to the sheave housing and assembly / tree | Converted to SO# 1732665: No findings
172 | 2019 | 2019-12-11 | Carolina | Hydraulic | 326? | 85.5 | Cutter | Motor (Cutter Shaft) | None | Replace PORT cutter motor | No Work Order entered | No Work Order entered into Delay Log
173 | 2019 | 2019-12-21 | 58 | Mechanical | None | 59.57 | Main / Aux Gen. | Main Generator Eng | 4796635 | none | Troubleshoot and repair #2 main engine | Converted to SO# 1733173: 12/21/19 - technician arrived, removed valve cover, inspected head and liner - no issues. During inspection technician suspected that after cooler was leaking and during the start up, hydraulically locked #4 cylinder pushing the injector up through the valve cover. 12/22/19 - technician and crew to remove after cooler to take it to the shop to clean, inspect and pressure test after cooler. 12/23 - after cooler tested good. technician's brought after cooler and complete head rebuild kit for #2 ME. Found blown head gasket. Replaced all consumable parts and valve cover. All valves set and injector timing set. Technician's tested engine and hooked up to analyzer, all readings in normal range at idle and full speed.
174 | 2019 | 2019-12-22 | Illinois | Hydraulic | None | 92 | Ladder Pump | Gland Seal | 0309740 | Underway 2200 | Ladder Pump Motor #6 CAT seal replacement | Found ladder pump motor # 3 Cat duo-cone oil seal to have failed and leaking excessively.
175 | 2019 | 2019-12-25 | Carolina | Hydraulic | None | 144.89 | Cutter | Motor (Cutter Shaft) | None | None | No Work Order entered | No Work Order entered into Delay Log
176 | 2019 | 2019-12-29 | Alaska | Hydraulic | None | 59.14 | Cutter | SCR Drive / MG Set | 4796684 | None | Troubleshoot fault in Synchronous Motor Sync Control | Troubleshoot possible causes for Open Field Fault Code 40; sent board to be repaired
177 | 2020 | 2020-01-01 | 55 | Mechanical | None | 24.5 | Main / Aux. Generators | Main Generator | None | Crane Drive trip out, troubleshoot electrical crane | No Work Order entered | No Work Order entered into Delay Log
178 | 2020 | 2020-01-01 | Carolina | Hydraulic | None | 174.2 | Cutter | SCR Drive / MG Set | 1733897 | troubleshoot, replace SCR drive | Work Order not found | Work Order not found
179 | 2020 | 2020-01-01 | Illinois | Hydraulic | None | 194.5 | Swing System | Winch System | 0309750 | None | SWING MOTOR INSTALLATION | No findings
180 | 2020 | 2020-01-03 | Carolina | Hydraulic | None | 32.22 | Cutter | Motor (Cutter Shaft) | 4038564 | Replace PORT cutter motor | Port cutter motor ( Removal ) | After trouble shooting drives for cutter motors. found that port cutter fields and arm. field we're over heating. Checked both blowers for rotation & flow coming out of motor, both we're ok. Removed motor and placed on crane barge.
181 | 2020 | 2020-01-05 | 53 | Mechanical | Deferred | 31.35 | Spud System | Spud Winch | 4796836 | troubleshoot and repair motor on port spud | Technician to diagnose the port spud two speed valves | Converted to SO# 1733646: No Findings. Provide labor to inspect and diagnose the following. 1. inspect port spud winch hydraulic system. A. The port spud will function as designed in low speed. B. When in high speed it is almost like the spud is free falling when go lowering the spud. you can not feel or hear the pump engaging. The winch will not lift the spud more than a quarter turn before it stalls out. 2.All inspections will be down with a GLDD rep onsite. 3. Vender to provide any required test equipment. 4. All reports are to be submitted in writing to GLDD on site at the time if the test or inspection.
182 | 2020 | 2020-01-07 | Texas | Hydraulic | None | 70.9 | Swing System | SCR Drive | None | None | No Work Order entered | No Work Order entered into Delay Log
183 | 2020 | 2020-01-07 | Terrapin Island | Hopper | Deferred | 44.51 | Trunnion Hoist | Other | 418315 | Port trunnion slide being taken off | Work Order not found | Work Order not found
184 | 2020 | 2020-01-23 | Carolina | Hydraulic | None | 48.22 | Cutter | SCR Drive / MG Set | 4038575 | port cutter drive | Cutter SCR drive ( Trouble shoot port drive not starting ) | Started trouble shooting port drive SCR blower motor not starting. Found that we were not getting power to close contactor. Checked power coming from OEM 9600 to close contactor, not getting command power. Next day we had tech. come out to help with trouble shooting. Check program on OEM 9600, looked good. We had blowed (2) fuses on field, when power up system. we Meg field wire back to motor, Meg good 34 meg. After checking prints trouble shooting more found that there was a missing jumper wire going from # 33over to # 34 terminal. Added jumper between the two terminal, SCR blower started working. Now we're not load unbalance not clearing. Found that a wire on reset not making good contact. Removed wire, cut and cleaned up end. reinstalled working ok. When checking system found that current unbalance board (Port side) had a burned spot on board. Had one on hand, changed out. found (3) relays in question, changed out also. After repairs we're made drive cleared and we got SCR ready lights. system started and running ok.
185 | 2020 | 2020-01-28 | Carolina | Hydraulic | 331 | 124.44 | Cutter | Bearings/Shafts | 4038583 | cutterhead coupling broke | Tailshaft, Cutter Installation | Received cutter tail shaft on 01/31/20 at 9:30 along side of dredge. Crew started removing protective coating from taper for cutter and bearing area. Also cleaning coupling mating surface. Removed key from shaft and checked fit in coupling, fit good. Reinstalled on shaft with bolts to hold in place. Finish cleaning shaft at 2 pm. Started rigging shaft for install with single and double to lift or lower eather end of shaft as needed.( Prior to this crew had lifted cutter platform 3' to alow shaft to go under for install ). When swinging shaft around in front of platform, we couldn't position shaft to line up with Thordon bearing properly. ( Had to move Derick to line up Crane straight with ladder to line up shaft with Thordon bearings ). Used (2) Derick to install shaft. First Derick placed shaft in front of platform allowing 1/3 of shaft to pass under platform. used other Derick to rig end of shaft to hold in place. Removed single wire from first Derick. Started shaft into Thordon bearing pulling with 3 ton leaver hoist. When rigging came up to bearing. lowered rigging and reposition, Repeated as needed. Pulled shaft up to journal bearing till taper for coupling was past bearing so coupling could be cold fitted. Started fitting coupling. Using (3) 2 ton chain fall's we rigged coupling to line up onto shaft. after rigging coupling had to roll shaft to match up key to coupling. Used a 3 ton leaver hoist to pull coupling onto shaft. After pulled up installed end plate on shaft to finish pulling coupling up into place. Removed end plate, with coupling in place we measure distances around front & back of coupling. On front of coupling, TOP 0.116, BOTTOM 0.118, STBD side 0.068, PORT side 0.115. On back side of coupling, TOP 0.003, BOTTOM 0.006, STBD side 0.008, PORT side 0.003. Marked back of coupling and add 0.040 for install of coupling. When finished we started removing coupling for heating. Had to rig hyd. jacks to push coupling back off of shaft. With coupling off we pulled it close to thrust bearing. Coupling was still over shaft by 3". we used shimming material to rap around shaft to help deflect heat off shaft. Also used water on shaft to keep cool. With coupling in place started heating with 4 rosebud torches. We heated in (3) steps, couldn't get torches on inside of coupling. We heated till out side was 475 degree and stop to let heat expand into coupling. This was done (3) times to let heat get up to 300 degree in center of coupling. we installed coupling on to shaft and placed end plate on shaft and tighten up all bolt's. ( When installing coupling on shaft coupling went past mark on shaft, pulled back and installed plate). Removed end plate to check for proper fit. Found that coupling had moved ford on shaft, we had 0.090 between end plate and coupling. ( should be 0.040 ) Talk to maintenance managers decision was made to leave in place. Installed end plate bolts and torque bolts to 950 ft lb. Installed wire in bolt's & tied together. Pulled coupling and shaft up to thrust bearing coupling to install bolts. pulled bolt up with 1" air gun. Torque coupling bolts to 10,000 ft lb. using criss-ross pattern. Installed top on journal bearing. Pulled down bearing top evenly on both side. Checked clearance between shaft & top bearing 0.020. Installed water ring on thrordon bearing with new seal. Installed all hoses for bearing's. Run service water and checked for any leak's. Found broken brackets on service pipe, repaired as needed. Run cutter system to make sure everything working ok. Run for (1) HR. look's ok. Next day installed cutter & run for (1) HR. looked ok.
186 | 2020 | 2020-03-07 | Alaska | Hydraulic | None | 48.8 | Main Pump | Pump Leak | 1728652 | Leak on rock box | Rebuild Main pump / replace front liner / | Hunting island to date 3/9/2020 yd 1,056,557 PUMP GAP .130 installed new transition and elbow ( max 5 ) changed before corpus 4,213,985yd + 1,056,557 = 5,288,542 Suction side liner Req#1731000 changed pre hunting lasted 1,056,557 / changed again 3/9/2020 / REQ# 1731285 inner shell Req #1730991 yds 1,056,557 to date changed pre hunting back liner Req #1567519 yds 1,056,557 to date changed pre hunting Runner 97" installed before Tybee Req# 1730502 tybee 1.4 m yd + hunting 1,056,557 = 2,456,557 yd next Available parts ES liner REQ# 1731285 SS liner REQ# 1731357 inner shell REQ# 1731285 REQ# 1584840 runner as per Bernie Garza 1-front door have damage for the hole on the line also we find damage wear the liner set round gasket and we add Nordbak patch material ( need service req ) 2- outer shell have damage wear the back door liner set and we have to rebuild with Nordbak (need service req) 3-transition peise have wear on the bottom need hard surface / NEXT PUMP JOB / NEW TRANSITION ON 187 4- shell adjuster bolt need to be change with new one all thread 5- need new rock box liner have some damage wear betwene the rock box and front door / NEW BOX ON 187
187 | 2020 | 2020-03-10 | Dodge Island | Hopper | Deferred | 45.8 | Dredge Pump Engine | Other | None | Throttle Issues | No Work Order entered | No Work Order entered into Delay Log
188 | 2020 | 2020-03-11 | 55 | Mechanical | None | 44.94 | Main / Aux. Generators | Main Generator Eng | None | electrical problem with main engine cooling water pump | No Work Order entered | No Work Order entered into Delay Log
189 | 2020 | 2020-03-11 | Ellis Island | Hopper | Deferred | 29.1 | Drag Head Hoist | Brake Assembly | None | None | No Work Order entered | No Work Order entered into Delay Log
190 | 2020 | 2020-03-23 | Dodge Island | Hopper | Deferred | 26.3 | Dredge Pump | Other | 4070790 | Wiring Harness | Stbd dredge engine troubleshoot engine speed control | The speed control output wire was bypassed from the speed control block to the ECM 40 pin connector. (no change) The white wire from the speed sensor was bypassed to the 40 pin connector from the pickup. (no change) The speed control block signal was tested by replacing the unit with one from spares to test signal output (no change) The secondary ECM was turned off at the breaker in the Black Box and the secondary Speed/Timing sensor was disconnected. This allowed the engine to come up to pump out speed (1500 RPM)
191 | 2020 | 2020-04-27 | Texas | Hydraulic | None | 42.03 | Main Pump | Engine/Motor | 0792089 | BOTH MAIN PUMP ENGINES SHUT DOWN DUE TO MAIN PUMP BEARING FAILURE | Troubleshoot main pump failure | No findings
192 | 2020 | 2020-05-01 | Texas | Hydraulic | None | 40.91 | Main Pump | Bearings/Shafts | 0792090 | Repairing Main pump bearing shaft - underway for dig site at 19:50-arrived at dig site at 01:00.hauling gears malfunctioning. | Spring bearing failure | Bearing was replaced. Shaft alignment was in spec, verified by Tim R. & Chief Manny. Stuffing box sleeve was replaced due to wear. Bearing clearance was "0.022" Shaft was cleaned up and polished, now free of any markings or grooves.
193 | 2020 | 2020-05-13 | Carolina | Hydraulic | 347 | 101.66 | Cutter | SCR Drive / MG Set | None | Cutter drive running high temp | No Work Order entered | No Work Order entered into Delay Log
194 | 2020 | 2020-05-14 | 54 | Mechanical | 366 | 29.91 | Crane Boom | Boom Winch | 4799710 | Shut down. Inspect boom hoist drum assembly. Realign gears and replace bolts | Inspect boom Hoist gear set | A NOISE IS DETECTED WHEN BOOM IS BEING LOWERED Converted to SO# 1733646:Provide the labor, material and equipment as required to accomplish the following: 1. Perform an inspection on boom bull and pinion gears 2. Check to verify proper wear on gears 3. Inspect gear back lash 4 Diagnose why gears are making unusual noise when boom is being lowered.
195 | 2020 | 2020-06-03 | Carolina | Hydraulic | 355 | 47.29 | Ladder Pump | Shaft | None | None | No Work Order entered | No Work Order entered into Delay Log
196 | 2020 | 2020-06-19 | Carolina | Hydraulic | 354 | 143.19 | Main Pump | Bearings/Shafts | None | None | No Work Order entered | No Work Order entered into Delay Log
197 | 2020 | 2020-07-26 | Texas | Hydraulic | None | 67.1989 | Ladder Pump | Pump Leak | 4801646 | None | fix pump leak ladder pump (CHS) | Found gasket off the steel lip of the pump shell . We slacked all bolts to be able to line up gasket . Crew said this gasket was in place when they did the pump job inside Charleston SC. Probable cause of gasket getting out of place dredge is being having lots of rams and chokes .
198 | 2020 | 2020-08-07 | Carolina | Hydraulic | None | 46.0775 | Electrical System | PLC / Automation | 4038753 | None | PLC shutdowns ( losing readings on screens ) | Started trouble shooting PLC system for lose of transmitting between components and PLC. • Tested cables • Pull out extra cable from chief office • Labeled cable and devices in chief office and Control room. • Helped Slimmer trace cables on mechanical side. • Pulled out cable in survey rack (In survey Office) that were extra. • Helped Slimmer move Survey router to back of rack. Out of sight out of mind. • One thing that stands out, there is a blue cat 5 cable ran from the survey rack to the chief office. This is the cable I believe might of caused all the issue because if they plugged it into the MR30 in the chief office it might of given them the issue. I did pull a bunch cables out of the chief office but this one still there because we don’t know the purpose it was installed. If I don’t have an answer by the end of the day I’m cutting the end. This way they need to put an end on it before plugging it into anything. Carolina Main switch in survey office next to lever room. Port 20 goes to Chief’s Office Meraki MR30 AP Port 31 goes to 8 port switch in Control Room Control room 8 port switch • Port 1 Uplink to main switch • Port 2 Thin Client in control room • Port 3 Printer in control room • Port 4 To MR30 in Engineer Control Room • Port 5 To Meraki MR74 in living Connex on back of dredge • Port 6 – 8 Ports disabled Meraki MR30 AP • Port 1 – 4 Ports disabled Chief Room Meraki MR30 • Port 1 Thin client in Chief Office • Port 2 Printer in Chief Office • Port 3 & 4 Ports disabled
199 | 2020 | 2020-08-18 | 53 | Mechanical |  | 23.9997 | Crane Swing | Swing Circle (rollers, etc.) | None | down for swinging bush repairs | No Work Order entered | No Work Order entered into Delay Log
200 | 2020 | 2020-08-20 | Ellis Island | Hopper |  | 201.77 | Main Engine / Propulsion | Gearbox | None | Gearbox Troubleshooting | No Work Order entered | No Work Order entered into Delay Log
201 | 2020 | 2020-08-22 | Texas | Hydraulic | None | 40.0625 | Cutter | Motor | 792338 | tow dredge in for repairs- Cutter mottor cooler | Canister H/E (Port) Radiator Swap Out | * Radiator tube at bottom appeared to have cracked and was spraying water out. *Swapped out only the radiator because blower units were good condition and were the upgraded Predator style.
202 | 2020 | 2020-08-22 | Carolina | Hydraulic | 361 | 27.0664 | Cutter | Bearing / Shaft | 4038781 | lost service water | Service water piping ( flush sand & rock out of line's on ladder) | Started troubling service water on ladder. Found that All pipe's wear filled with sand. Followed pipe back into bow hole< gland seal pump room. Removed hose going from dredge over to ladder. turned service water pump on and flush sand from line. Installed rubber hose back to ladder. No water to ladder still. Removed cooling water flanges and orifice from shaft bearings. Removed cooling water line's from uwp gearbox cooler. Turn service water on, only got water uwp gearbox cooler. uwp gearbox cooler also plug. Removed 3" flanged blank at end of line by gearbox. turn service water back on. sand flushed out to this point. Shaft cooling water closes to gearbox cleared also. Cleaned flanged blank and installed a new gasket & put back togeather. Turned service water back on and off a coupler time to get next cooling water line to clear. At this time we removed all lines going to gland seal on uwp & flushing for uwp. turned water back on still plugged. Superated pipe at flange by thrust bearing & turned water back on pipe flushed out. installed pip back togeather & finished flushing out pipe's to flushing at uwp. Run water to pipe's wear completely clean. Puy all back togeather. Repeated the same step's to clean cooling water out to head section of ladder. At head section we cut out a 3" tee to clean out sand in pipe. we then used the wash down pump for cutter to back flush pipe to help clean out. After cleaning had welder install new tee back into pipe. Cooling water to cutter motor's was also plugged. When we got to cooler we used long hose to back flush then several times to get them clean.
203 | 2020 | 2020-08-23 | 54 | Mechanical | None | 117.2964 | Main Hoist | Holder | 4251786 | going to S I yard for repairs | Replace Holder brake Linkage | Holder drum brake linkage was found damaged
204 | 2020 | 2020-08-28 | Texas | Hydraulic | None | 31.6697 | Ladder Pump | Pump Rebuild | 4802045 | pump shell cracked - change pump shell | Replace under water pump shell | Crack in pump shell Replace pump shell
205 | 2020 | 2020-08-29 | Ellis Island | Hopper | None | 201.77 | Main Engine / Propulsion | Gearbox | None | Gearbox Troubleshooting | No Work Order entered | No Work Order entered into Delay Log
206 | 2020 | 2020-09-03 | 53 | Mechanical | No | 27.0581 | Main / Aux. Generators | Main Generator | None | None | No Work Order entered | No Work Order entered into Delay Log
207 | 2020 | 2020-09-24 | Alaska | Hydraulic | 368 | 243.1528 | Main Pump | Bearings / Shafts | 4802724 | thurst bearing temp high | Disassemble the Main Pump Thrust Bearing | The thrust shoes were wiped. Bearing disassembled sump cleaned, thrust collar was honed, new shoes installed. Thrust was set to .030 and checked after cap of bearing was installed. Refilled the sump. Test ran the bearing UNSAT. Bearing wiped at low speed. Bearing being disassembled along with spring bearing to remove the pump shaft and send to a machine shop.
208 | 2020 | 2020-10-13 | Liberty Island | Hopper | 375 | 130.53 | Main Engine / Propulsion | Other | 850561 | M/E shutdown; troubleshooting | TROUBLESHOOT PME and SGE AUTOMATION | Converted to SO/ PO#1748827: Requirements: Troubleshoot electronic controls shut down. The dredge was down for 13-daies PORT MAIN ENGINE IS SHUTTING DOWN WHILE IN OPERATION, CARTER CATERPILLAR TO COME ON AND TROUBLESHOOT THE CAT ELECTRONIC CONTROL MODUAL FOR THE ENGINE AND ALL ASSOCIATED AUTOMATION INPUT AND OUTPUTS FOR THE ENGINE SHUT DOWNS. STARBOARD MAIN GENERATOR SEEMS TO BE EFFECTING THE OPERATION OF THE PORT MAIN ENGINE AS WELL. WILL ALSO NEED TO LOOK AT STBD. GENERATOR CONTROLS. WE ARE HAVING TROUBLE KEEPING THE PME RUNNING, THE ENGINE CONTINUES TO SHUT DOWN FOR UNKOWN REASONS. WE ARE GETTING SUMMARY SHUT DOWNS FROM THE MMS PANEL. THE STBD GENERATOR SEEMS TO BE EFFECTING THESE SHUTDOWNS WHEN WE START THE ENGINE. THE PORT AND STBD MAIN ENGINE ECMS HAVE ACTIVE DIAGNOSTICS CODES FOR 5VDC ABOVE NORMAL. THE STBOARD GENERATOR ECM IS DISPLAYING ACTIVE 5 VDC ABOVE NORMAL AND MULTIPAL FAUTY SENSORS. NEED TO THOROUGHLY COMB THROUGH THE CONTROL WIRING ON SGE AND PME. LOOK FOR ANY GROUNDS AND AC NOISE INTERFERING WITH THE 24VDC POWER. ECMS WERE REPLACED ON PORT AND STBD MAIN ENGINES AND PORT AND STBD MAIN GENERATORS. A CULMINATION OF FAULTY SENSORS ON STBD GENERATOR ENGINE AND GROUNDS ON PORT MAIN ENGINE ALONG WITH BURNED UP DIODES WHERE FOUND IN THE PORT MAIN ENGINE MMS PANEL. AN OUTPUT TO A DISCONTINUED SOLENOID ON PORT MAIN ENGINE WAS CHECKED AND FOUND COMPROMISED. THIS UNIT AND CABLE WERE REMOVED, AND THE BURNED OUT DIODES IN PORT MAIN ENGINE MMS PANEL WERE REPLACED. FURTHER CHECKS OF THE SHUTDOWN SYSTEM ON PORT MAIN ENGINE WERE DONE, AND NO MORE FAULTS WERE FOUND. WE TURNED THE ENGINE OVER TO BRIDGE TO COMENCE DREDGING. WE SUCCESSFULLY COMPLETED A LOAD AND PUMP OUT CYLCE WITH NO SHUT DOWNS. THE 5VDC ON PORT AND STBD MAIN ENGINE ECMS HAVE COME BACK ACTIVE; DREDGING CONTINUES WITH NO ENGINE SHUT DOWNS. IN THE DAYS OF TROUBLESHOOTING THIS ISSUE, IT WAS DISCOVERED THERE HAS BEEN DETERIORATION IN THE WIRING HARNESSES ON THE STBD GEN ENGINE. CHRIS SLIMMER IS WORKING WITH MAINTENANCE MANAGER MIKE K AND CARTER CAT TO ARRANGE REPLACEMENT OF THE CONTROL SYSTEMS ON ALL THE PORT AND STBD MAIN ENGINES AND PORT AND STBD MAIN GENERATORS. THESE ENGINES ARE NOW 20 YEARS OLD, SOME OF THE CONTROL PARTS ARE NOW MATURE OR OBSOLETE, REPLACEMENT WILL ENSURE ENGINE RELIABILITY. 10-23-20 AS OF YESTERDAY THE DREDGE IS OPERATING. THERE HAVE BEEN NO MORE SHUTDOWNS OF THE PME.THERE IS AN ONGOING ISSUE WITH THE SGE. THIS IS AN ISSUE OF THE ENGINE WIRING HARNESSES. CARTER CAT, CHRIS SLIMMER AND MIKE K. ARE WORKING TOGETHER TO FAST TRACK NEW REPLACEMENT HARNESSES. ONCE ONBOARD, WE WILL SCHEDULE INSTALLATION AT THE FIRST BREAK PERIOD.
209 | 2020 | 2020-10-15 | Carolina | Hydraulic | None | 61.4994 | Main Pump | Bearings / Shafts | 4803118 | None | Port pump bearing replacement | Port pump thrust bearing failed. Broke shaft. Replaced thrust bearing. Aligned shaft to stuffing box and coupling. Add packing and water ring Adjusted thrust clearance for impeller. Cleaned all oil lines and filled thrust bearing with oil. Test ran thrust bearing for 1 hour starting RPM at idle and running up to 281 RPM. Start - FWD bearing AFT bearing oil temp RPM Temp - 70 70 70 150 Ending - FWD bearing AFT bearing oil temp RPM Temp - 91 97 96 281
210 | 2020 | 2020-10-18 | Ohio | Hydraulic | None | 62.895 | Electrical System | PLC / Automation | None | UWP is tripping out on the main board | No Work Order entered | No Work Order entered into Delay Log
211 | 2020 | 2020-10-21 | 54 | Mechanical | No | 94.3867 | Crane Swing | Drive (motor, gear box, etc.) | None | stbd swing gear bushing went bad | No Work Order entered | No Work Order entered into Delay Log
212 | 2020 | 2020-10-22 | Alaska | Hydraulic | None | 67.4458 | Main Pump | Bearings / Shafts | 1747550 | thrust bearing heated up and the machine unclutched on its own | Work Order not found | Work Order not found
213 | 2020 | 2020-11-05 | Ohio | Hydraulic | None | 72.4706 | Ladder Pump | Bearings / Shafts | 4803593 | None | Ladder Pump Thrust Bearing R&R | Coupling end bearing went out. Shaft has dropped and destroyed the seal. R&R is a must.
214 | 2020 | 2020-11-08 | Ohio | Hydraulic | None | 29.8925 | Generators | Main Generator | None | None | No Work Order entered | No Work Order entered into Delay Log
215 | 2020 | 2020-11-11 | Liberty Island | Hopper | No | 30.64 | Other | Other Mechanical | None | None | No Work Order entered | No Work Order entered into Delay Log
216 | 2020 | 2020-11-17 | Alaska | Hydraulic | None | 33.3906 | Ladder Pump | Gland Seal | 1728852 | None | Replace CAT Duo Cone Seal | The old seal was worn on the motor side and grooved. To remove the seal we had to remove the UWP shell due to the inner seal ring being a soling piece and not split. New seal was installed and clearances set per CAT sela manula and verified by Joe Gracia. Pressure test was conducted with 20PSI of air pressure on the motor. 1 leak was discovered at the 1 O'clock position. Shaft was rolled while the seal was lubricated. Second pressure test was conducted with no leaks noted.
217 | 2020 | 2020-11-22 | Liberty Island | Hopper | No | 34.72 | Dredge Pump | Clutch | 850650 | Port clutch won't disengage. Stbd engine showing two ECM alarms | Troubleshoot the port dredge clutch failure to clutch out after dredging operations | At 2100, the drag tender called down and said he couldn't get the port dredge pump clutched in because the RPMs were reading to high (505 rpms) on the automation screen. Soon to realize that there was 0 psi on the clutch air manifold down in the lower engine room. The rotary air seal was spinning but the pump shaft was not. The magnetic pickup was reading 505 rpm as well. Even though the clutch air was reading 0 psi we closed the two valves on either side of the clutch air solenoid and dumped any air that might have been entrapped in the clutch by opening the dump valve. No air came out. We then removed the rotary air seal hose in the lower dredge pump room & exercised the clutch by manually clutching it in & dumping the air several times. This didn't resolve the problem. Next, we LOTO the PME, opened all the petcocks, pre-lubed the engine & turned the engine over by the jacking gear while having a com-a-long with a strap around the clutch to try to free up the clutch. This didn't resolve the problem either. We then placed a chain fall right above the clutch and slightly lifted the clutch vertically to see if this would free it up while turning the engine over by the jacking gear. This didn't resolve the problem either. Engine crew was told to remove the wedges from the clutch plate to facilitate the removal of the clutch once management had been notified of the issue. Email sent out just after midnight to maintenance manager Mike K and Jake. Decision was made to remove the clutch for inspection. JRM Catastrophic bearing failure of dredge pump clutch. New bearing assembly being shipped from Lyons ship repair. Bearing assembly arrive early Tuesday morning and engine crew began assembly all components torqued to spec, bearings checked for grease, foundation bolts checked. Clutch was finally complete today around 1600 hrs. All satisfactory. Rotary air seal however did blow out after a few minutes of run testing. Need rotary to be ordered. 11/24/20 JRM Replaced vulkan coupling elements
218 | 2020 | 2020-11-22 | Liberty Island | Hopper | None | 51.76 | Main Engine / Propulsion | Clutch | None | None | No Work Order entered | No Work Order entered into Delay Log
219 | 2020 | 2020-11-24 | Ohio | Hydraulic | None | 87.835 | Ladder Pump | Gearbox | None | broken bolts on shaft meets coupling,metal sceen stuck in numer 2 pummp,bad seals on gearbox. assistant chief and engineer with have futher info on the gearbox issues | No Work Order entered | No Work Order entered into Delay Log
220 | 2020 | 2020-11-28 | Liberty Island | Hopper | No | 25.13 | Drag Head | Other | None | breakaway flange repair | No Work Order entered | No Work Order entered into Delay Log
221 | 2020 | 2020-12-01 | Terrapin Island | Hopper | No | 43.6925 | Drag Head | Other | Need specific category, other no idea. | change out port & stbd | No Work Order entered | No Work Order entered into Delay Log
222 | 2020 | 2020-12-08 | New York | Mechanical | No | 26.1653 | Main Hoist/Main Hydraulics | Excavator Hydraulics | None | block on stick cylinder leaking | No Work Order entered | No Work Order entered into Delay Log
223 | 2020 | 2020-12-17 | Ohio | Hydraulic | None | 25.9833 | Main Pump | Pump Rebuild | None | None | No Work Order entered | No Work Order entered into Delay Log
224 | 2020 | 2020-12-27 | New York | Mechanical | 383 | 43.7275 | Crane Boom | Boom Structure | None | CYLINDER ISSUE | No Work Order entered | No Work Order entered into Delay Log
225 | 2021 | 2021-01-03 | 53 | Mechanical | No | 24.0642 | Main / Aux. Generators | Main Generator | 1750884 | # 2 generator shutdown. Reverse power/electrical trip. Inspected resistor bank on top of crane. One bank is cooler than the other 2. also found one wire chaffed and tapped up/secured wires | Work Order not found | Work Order not found
226 | 2021 | 2021-01-17 | 54 | Mechanical | 385 | 33.9333 | Main Hoist | Holder | None | None | No Work Order entered | No Work Order entered into Delay Log
227 | 2021 | 2021-01-30 | Texas | Hydraulic | None | 27.2611 | Cutter | Motor | None | cooler leaking on cutter motor | No Work Order entered | No Work Order entered into Delay Log
228 | 2021 | 2021-02-05 | Ellis Island | Hopper |  | 50.22 | Other | Other Mechanical | None | to dock for plate cooler repair and other maintenance | No Work Order entered | No Work Order entered into Delay Log
229 | 2021 | 2021-02-06 | 58 | Mechanical |  | 32.375 | Main Hoist | Holder | 4420100 | HOLDER WIRE BROKE | Broken Holder wire | While placing bucket in the scow, the holding wire broke at the drum. Removed old holding wire, ran tracer, put new wire on drum.
230 | 2021 | 2021-02-08 | 53 | Mechanical |  | 26.0025 | Auxiliary Systems | Heating, Ventilation, A/C | None | None | No Work Order entered | No Work Order entered into Delay Log
231 | 2021 | 2021-02-08 | Texas | Hydraulic |  | 40.7892 | Spuds / Xmass Tree | Wires | None | stb breast wire broke an lost stb bottom sheve on x-mas tree take dredge in to repair | No Work Order entered | No Work Order entered into Delay Log
232 | 2021 | 2021-02-24 | Illinois | Hydraulic | 391 | 149.6619 | Cutter | Gear Box | 4806414 | None | Replacement of Cutter gearbox HS input shaft bearings & HS Intermediate shaft bearings. | No Findings entered
233 | 2021 | 2021-02-25 | Dodge Island | Hopper |  | 25.2733 | Generator Engine | Other | 4071215 | port generator change head | Port Generator - Troubleshoot high exhaust temps | The Rocker arm hold down bolt on #2 cylinder failed. The push rods were found to be bent also. The push rods for #2 & #4 were replaced along with both sets of rocker arm hold down bolts. The top of the pistons were inspected by Bore-Scope through the fuel injection port. The heads showed no signs of damage. The valves were in good condition. The engine was inspected by Lousiana Cat Tech Jamie and determined to good to go if the suggested parts were replaced. We were missing two bolts need to complete the task this made completing task longer. The bolts were brought in from Atlanta by courier. The engine was reassembled and the valve lash was checked and set as needed. The engine was test ran. The engine operated within standard operating parameters. The engine was up on line and test loaded with a dredging load and operated properly.
234 | 2021 | 2021-02-28 | Terrapin Island | Hopper |  | 29.5911 | Dredge Pump | Gland Seal | 4182524 | fuel | Rebuild Pump | Rebuilt bearing housing. Replaced upper/lower bearings and seals, shaft sleeve, cleaned and painted housing Used 1 inboard grease seal part #13535. (shows none in inventory)
235 | 2021 | 2021-03-07 | Liberty Island | Hopper |  | 47.34 | Jet Pump | Pump Bearing | 850890 | Line Shaft Bearing | Replace stbd jet pump line shaft bearing and install the spare | Forward and aft bearing failure on line shaft, some indication that impeller was pinned up against the door after failure. Stuffing box found to be wasted away on the back side due to excessive leakage.
236 | 2021 | 2021-03-14 | 53 | Mechanical |  | 120 | Crane Swing | Swing Circle (rollers, etc.) | None | the cracks on the bow at the tub base are flexing and opening up. also excessive movement in the rail and popping sounds. Welding | No Work Order entered | No Work Order entered into Delay Log
237 | 2021 | 2021-03-15 | New York | Mechanical |  | 33.8339 | Tagline/Boom Assist | A-Frame (Wires, Winch, etc) | 4806683 | Structural damage/cracks on hog wire anchors | Quotes to remove and install new back stay dead end deck | No Findings entered
238 | 2021 | 2021-03-18 | 54 | Mechanical |  | 27.3458 | Main Hoist | Holder | 4806741 | brake pins damaged | change inboard brake band ( working brake band) | band had broke on the dead end portion of band about 2 inches from clevis pin hole brake was straight across band, meaning there no side trust on band. also found a keeper missing for clevis pin
239 | 2021 | 2021-03-29 | 54 | Mechanical |  | 27.75 | Crane Boom | Boom Winch | 4807069 | None | Trouble-shoot boom motor getting hot / smoking | BOOM NOT REACTING PROPERLY WHEN OPERATOR BOOM UP THE BOOM WOULD SLOWLY GO DOWN WHILE TROUBLE SHOOTING IT WAS NOTICED THE THE BOOM MOTOR WAS SMOKING AND VERY HOT
240 | 2021 | 2021-04-05 | Illinois | Hydraulic |  | 42.0783 | Cutter | Gear Box | 4806414 | None | Replacement of Cutter gearbox HS input shaft bearings & HS Intermediate shaft bearings. | No Findings entered
241 | 2021 | 2021-04-06 | 53 | Mechanical |  | 40.0828 | Electrical/Electronics | MCC / Switch Gear | None | bucket fell in scow (full load) drives tripped. troubleshooting. changed 2 blown fuses on closer, test. issue with holder drum not turning/inspected and found broken shaft on holder gearbox | No Work Order entered | No Work Order entered into Delay Log
242 | 2021 | 2021-04-21 | 54 | Mechanical |  | 67.9831 | Spud System | Spud Wires | 4807689 | Stern spud wire broke | Spud (Stern) Bottom Wire Change | stbd bottom spud wire failed, prematurely decided to replace stern spud bottom wire, due to its difficult to lift spud using our crane if need be
243 | 2021 | 2021-04-23 | Ohio | Hydraulic |  | 27.9039 | Main Pump | Pump Rebuild | 4807705 | pump liner wore out | Install new liner in #2 pump / Oak Island N.C. | Weeks liner installed having problems with adjustment / adjustment froze up new liners die first week in May 2021
244 | 2021 | 2021-04-26 | Carolina | Hydraulic |  | 50.7189 | Ladder Pump | Gearbox | 4038883 | None | Remove and reinstall UWP gear case top cover | Discover that the port speed pinon shaft bearings are lock and they are wearing out
245 | 2021 | 2021-05-05 | Carolina | Hydraulic |  | 117.1581 | Idler / Spud Barge | GL10 | None | winch issues | No Work Order entered | No Work Order entered into Delay Log
246 | 2021 | 2021-05-19 | Carolina | Hydraulic |  | 156.3961 | Ladder Pump | Gearbox | None | Gearbox repair. | No Work Order entered | No Work Order entered into Delay Log
247 | 2021 | 2021-05-28 | Carolina | Hydraulic |  | 88.8417 | Main Pump | Bearings / Shafts | None | None | No Work Order entered | No Work Order entered into Delay Log
248 | 2021 | 2021-06-04 | Liberty Island | Hopper |  | 42.96 | Other | Other Mechanical (repairs) | None | None | No Work Order entered | No Work Order entered into Delay Log
249 | 2021 | 2021-06-06 | 54 | Mechanical |  | 40.0117 | Spud System | Spud Wires | 4251870 | None | Change top spud wire | Annual wire change due, and also replaced adjustment bolts with new and new pin While installing the wedge in the wedge socket night crew dropped wedge overboard. no spear onboard, had to fly a wedge in from the Dredge 53
250 | 2021 | 2021-06-07 | Illinois | Hydraulic |  | 34.7061 | Main Pump | Engine / Motor | 4808652 | spring bearing | Install new spring bearing insert | bearing failed due to oil cooler raw water feed being plugged with mud.
251 | 2021 | 2021-06-08 | Liberty Island | Hopper |  | 67.89 | Main Engine / Propulsion | Other (repairs) | 851132 | engine overheated and shut down again. Replace Stbd Turbo | REPLACE SME INBOARD TURBO CHARGER | NEW TURBO: PART NUMBER: 189-4427 SER NUMBER T25405 514369 ENGINE HOURS WHEN REPLACED: 114,880 HRS FOUND METAL IN EXHAUST UPTAKE FOUND EXCESSIVE OIL AND METAL ON AFTER COOLERS, REPLACED FORE AND AFT AFTER COOLERS FAILED TURBO SENT BACK TO ABB AFTER COOLERS SENT TO GLDD YARD, WAITING FOR QUOTES TO HAVE CLEANED AND PRESSURE TESTED.
252 | 2021 | 2021-06-15 | Carolina | Hydraulic |  | 24.8903 | Main Pump | Pump Rebuild | 4808746 | None | Dredge Pump (Stbd) remove and replace crack shell | The pump shell cracked while pumping. Cleaned the line using the port pump and shut down to replace the shell. Pump shell changed out, gaskets and O-ring replaced. ordered new shell to have spare
253 | 2021 | 2021-06-19 | Carolina | Hydraulic |  | 116.1406 | Main Pump | Pump Leak | 4808866 | None | Dredge Pump (Stbd) Replace shell | Pump shell cracked at the trunk while digging as a result of a miss alignment of the elbow to the pump shell installed a shell the Buster had on hand and ordered another for them against the carolina After install the miss alignment was clean and elbow was cut in order to realign the pump.
254 | 2021 | 2021-06-23 | Illinois | Hydraulic |  | 67.9808 | Main Pump | Pump Rebuild | None | None | No Work Order entered | No Work Order entered into Delay Log
255 | 2021 | 2021-06-26 | Illinois | Hydraulic |  | 42.6 | Main Pump | Bearings / Shafts | 309837 | Thrust Bearing | Inspect and clean thrust bearing & add 2nd heat exchanger | No Findings Entered
256 | 2021 | 2021-06-29 | 54 | Mechanical |  | 87.1125 | Electrical/Electronics | MCC / Switch Gear | 4251884 | None | Trouble Shoot Hoist Generator | Hoist generator not putting out 500 volts. after cleaning brush rigging and commutator generator working properly
257 | 2021 | 2021-07-03 | 54 | Mechanical |  | 29.9428 | Electrical/Electronics | PLC | 4251884 | None | Trouble Shoot Hoist Generator | Hoist generator not putting out 500 volts. after cleaning brush rigging and commutator generator working properly
258 | 2021 | 2021-07-09 | 55 | Mechanical |  | 26.2706 | Main / Aux. Generators | Main Generator Engine | 4809140 | governor repair | Troubleshoot Governor Issues | Converted to SO# 1760239: No Findings Entered
259 | 2021 | 2021-07-09 | Liberty Island | Hopper |  | 52.7453 | Other | Other Mechanical | 0851204/0851205 | @ DOCK FOR MAINT. & REPAIRS | Manually open D8 dredge valve. / Troubleshoot why dredge valve D8 isn't opening. | The drag tender reported down that he couldn't open D8. After verifying that the fuse & sensors were fine, we opened the inspection cover off the valve to do an internal inspection. We identified that the gate was not level, meaning when the valve closed it sat unevenly, causing it to be pinched which restricts it from opening. After draining the water out of the pipe, we removed the plug on the bottom of the valve & used an enerpac to jack the valve open. Once the valve was open, we finished pumping a load. Total downtime: 0854-1258 (4 hours). Again, D8 wouldn't open back up. This time, we LOTO the valve stack for D8 (closed 3 valves). We then bled the pressure off the valve stack. We removed the bottom hydraulic hose to the valve cylinder & plugged it. We installed an enerpac adapter fitting to the bottom cylinder port, in order to manually open the valve with the enerpac. Once the enerpac was hooked up, we opened the valve stack valves. We then manually opened D8. Once opened, we removed the dim plugs off the valve stack so the valve couldn't close. Total downtime: 2224-0130 (3 hours)
260 | 2021 | 2021-07-11 | Carolina | Hydraulic |  | 26.2233 | Main Pump | Pump Rebuild | 4809309 | None | Dredge Pump (Port) Rebuild | The pump shell cracked while pumping. Cleaned the line using the strb pump and shut down to replace the shell. Pump shell changed out, gaskets and O-ring replaced. ordered new shell to have spare
261 | 2021 | 2021-07-15 | 58 | Mechanical |  | 51.5431 | Electrical/Electronics | MCC / Switch Gear | 4420132 | None | Install upgraded Avid Extreme 550 Inverters | All inverters replaced in holder drive.
262 | 2021 | 2021-07-21 | Texas | Hydraulic |  | 33.4239 | Ladder Pump | Motor / Engine | 4809535 | Replace UWP motor | Replace ladder pump motor | Found the windings in the installed motor burnt Had new motor transferred from Norfolk Yard. Final alignment numbers are in the attachments.
263 | 2021 | 2021-07-28 | 54 | Mechanical |  | 221.0078 | Hull | Hull / House Repair | 1761278 | coast guard inspecting the hull | Work Order not found | Work Order not found
264 | 2021 | 2021-08-01 | 58 | Mechanical |  | 573.0697 | Crane Boom | Boom Winch | 4420181 | After lightning storm , boom up to swing off deck. Come around to start digging. Had to make a move, after making move went to boom down and boom would not stop. | Repair Boom Cords | Converted to SO# 1761962: Please add into the messages or comments or RFQ; United States Crane (Orlando) visited the dredge and declined the repairs. WHECO from Charleston wanted the boom to be sent to their shop for repair. Certified Boom Repair (Tampa) was interested but could not commit for several weeks. Southern Crane (Houma) looked at the job and can start immediately (please award the PO to them, no need to RFQ) Once they source and quote the steel required for repairs I will amend this PO.
265 | 2021 | 2021-08-03 | Ellis Island | Hopper |  | 44.5497 | Other | Other Mechanical | None | at dock | No Work Order entered | No Work Order entered into Delay Log
266 | 2021 | 2021-08-05 | Iowa | R&L |  | 23.9997 | Swing System | Winch System | None | Major Mech. Repair to swing wire hydraulics | No Work Order entered | No Work Order entered into Delay Log
267 | 2021 | 2021-08-15 | Texas | Hydraulic |  | 33.8492 | Swing System | Swing Sheaves | None | None | No Work Order entered | No Work Order entered into Delay Log
268 | 2021 | 2021-08-17 | 54 | Mechanical |  | 100.7683 | Main / Aux. Generators | Main Generator Engine | 4810115 | None | Replace Thrush Washers / Inspect engine components | Converted to SO# 1762496: performed lead test for each cylinder and found unacceptable clearances no ELECTRICAL controls or PLC were checked
269 | 2021 | 2021-08-19 | Texas | Hydraulic |  | 24.1561 | Spuds / Xmass Tree | Tree Structure | None | None | No Work Order entered | No Work Order entered into Delay Log
270 | 2021 | 2021-08-25 | Dodge Island | Hopper |  | 173.5103 | Steering | Rudder | None | None | No Work Order entered | No Work Order entered into Delay Log
271 | 2021 | 2021-09-01 | Liberty Island | Hopper |  | 23.9997 | Hydraulics | Other | None | Dredge at Dock for STB Main HYD Repairs | No Work Order entered | No Work Order entered into Delay Log
272 | 2021 | 2021-09-02 | New York | Mechanical |  | 32.5981 | Tagline/Boom Assist | A-Frame (Wires, Winch, etc) | 4810395 | moving to office location for repairs | Change Stay Wires | Wires showed up on project at 15:45 03Sept2021 Day crew removed both port and stbd wires and placed on BTT crane Night crew set up wire and installed both wires throughout the night installing the last pin at 5:30 Day crew finished up with installing keeper on all pins and and sprayed paint at wire thimble connection
273 | 2021 | 2021-09-03 | Carolina | Hydraulic |  | 59.0297 | Main Pump | Gearbox | 4038962 | coupler to thrust bearing broke | Repair stbd pump coupling & Thrust bear replacement | We found that the coupling seal ring was broken and the coupling engaging teeth were worn off. While the runner was trying to be removed the thrust bearing top cover was lifted by the force of trying to remove the runner.
274 | 2021 | 2021-09-05 | Ohio | Hydraulic |  | 30.7736 | Ladder | Wire | None | Ladder wire strarting to part. Changing wire. All stop oder due to lighting | No Work Order entered | No Work Order entered into Delay Log
275 | 2021 | 2021-09-07 | Dodge Island | Hopper |  | 35.4375 | Hydraulics | Other | 4071556 | None | Port Hyd. Service System: Repair Leak in Piping | We were losing oil in the port service system excessively, a leak was foundn the port #1 wing tank void. The space was properly ventilated, oil was sucked out as best as we could. The sectin of pipe was cut out and a new segment was installed in its place. The system was tested for leaks, once qualified the system was returned to service. It is suggested that the PypLOK swage tool is purchased to cut down on down time required to complete this recurring issue.
276 | 2021 | 2021-09-18 | Ohio | Hydraulic |  | 95.7069 | Ladder Pump | SCR Drive | None | underwater pump wont start back up. Waiting on parts. | No Work Order entered | No Work Order entered into Delay Log
277 | 2021 | 2021-09-25 | 54 | Mechanical |  | 26.3153 | Spud System | Spud Structure | None | None | No Work Order entered | No Work Order entered into Delay Log
278 | 2021 | 2021-09-29 | New York | Mechanical |  | 51.2067 | Crane Swing | Drive (Motor, Gear Box, etc) | 4811009 | CHECKING ON NOISE FFROM ONE OF THE SWINGS ON 996 TAKE SWING MOTOR OFF SWING PLANATERY #111 TO CKECK SUN GEAR | Troubleshoot Swing Gear - Install new Swing gear | Completed Failed bearing had to be changed Serialized swing box #4 failed @9,237 hours on unite Installed serialized swing box #5
279 | 2021 | 2021-10-02 | New York | Mechanical |  | 24.8617 | Crane Swing | Drive (Motor, Gear Box, etc) | 4811214 | problem with new swing hydralic going into gear oil | Replace Hydraulic Motor | Completed by Todd Reisinger / Dalton Padgett / Archie Gray / Jason Sprague / David D'Zurilla / James Deyton / Jack Kelley New motor has been installed and tested
280 | 2021 | 2021-10-04 | Alaska | Hydraulic |  | 58.5 | Spuds / Xmass Tree | SCR Drive | 4811264 | None | Troubeshoot and repair spud drive | Phase A melted on the 480 vac power. Removed the block assembly and connect the wiring Reprogrammed the micrologix computer tested drive
281 | 2021 | 2021-10-05 | New York | Mechanical |  | 68.4847 | Main/Aux Generators | PP1 | 4811241 | spudded down in inner harbor for work to PP1 and Gen 1/inspections | Weld up cracking on bucket | Completed by Paul Murdock
282 | 2021 | 2021-10-06 | Sandpiper | R&L |  | 24.4239 | Swing System | Winch System | None | SWING WINCH HYDRAULIC PUMP ISSUES | No Work Order entered | No Work Order entered into Delay Log
283 | 2021 | 2021-10-10 | 54 | Mechanical |  | 35.8581 | Spud System | Spud Wires | 4811448 | Stern spud wire about to break | Change bottom spud wire | wire failed, large bad areas found, requiring wire to be changed
284 | 2021 | 2021-10-15 | Liberty Island | Hopper |  | 23.9997 | Main Engine/Propulsion | Other | 851480 | None | Port Main Engine inboard and outboard turbo failure | Bearing failure on the left bank turbo (outboard) Blade damage on the right bank turbo (Inboard)
285 | 2021 | 2021-10-21 | Ellis Island | Hopper |  | 68.9667 | Gimbal Hoist | Wires | 4272235 | None | Stbd gimbal wire retrieval | Retrieve stbd drgarm after stbd gimbal wire breaks. Change stbd gimbal wire once dragarm is secure on deck. Change all other dragarm wires.
286 | 2021 | 2021-10-29 | Ellis Island | Hopper |  | 69.6831 | Other | Electrical | None | Ellis Drag Head Computer Fried - Needs to be remoted into | No Work Order entered | No Work Order entered into Delay Log
287 | 2021 | 2021-10-29 | Carolina | Hydraulic |  | 35.5508 | Swing System | Winch System | None | None | No Work Order entered | No Work Order entered into Delay Log
288 | 2021 | 2021-10-30 | Liberty Island | Hopper |  | 232.4 | Steering | Rudder | 851525 | STB rudder non-responsive | Troubleshooting P/S Steering Gear Systems rudder control | Three of four cylinders has oil leaking pass the piston seals.
289 | 2021 | 2021-11-13 | Alaska | Hydraulic |  | 145.4464 | Ladder Pump | Motor / Engine | 1729030 | TRIPPING | Remove the UWP Motor | No Findings entered
290 | 2021 | 2021-11-15 | Terrapin Island | Hopper |  | 61.1567 | Dredge Pump | Gland Seal | 4184180 | port pump gland seal, went to dock for repairs | Impeller - Port dredge pump - Remove & install for gland seal replacement | found gland seal leaking water into the bilge
291 | 2021 | 2021-11-15 | Carolina | Hydraulic |  | 55.0117 | Swing System | Swing Sheaves | 4038991 | stardboard side | Make repairs to swing winch frame | Weld cracks in winch foundation
292 | 2021 | 2021-11-19 | Sandpiper | R&L |  | 28.2 | Main Pump | Engine / Motor | None | was cleaning out line when steel engine coolant fitting cracked causing antifreeze to leak in engine room. reweld fitting and get back to running | No Work Order entered | No Work Order entered into Delay Log
293 | 2021 | 2021-11-20 | Iowa | R&L |  | 23.9994 | Ladder Pump | Bearings / Shafts | None | None | No Work Order entered | No Work Order entered into Delay Log
294 | 2021 | 2021-11-24 | New York | Mechanical |  | 83.2533 | Spud System | Spud Wires | 4812674 | Port spud repair | Change Wire | 25Nov2021 - Removed bottom wire from drum, cut into sections as it was lifted from winch room Pulled all slack from top wire from winch and placed on deck behind spud Cleaned winch room in preparation of changing wire 26Nov2021 - Installing emergency lift cylinders Install a new half moon above existing Connect hydraulic hoses and test 27Nov2021 - Divers in the water to retrieve wire Truck with wire delayed Installing bottom stern wire onto port bottom wire Ordered new wire to replace Task completed around 22:00 and dredge returned to work
295 | 2021 | 2021-11-24 | Ohio | Hydraulic |  | 27.6658 | Spuds / Xmass Tree | Wires | None | Starboard breast wire broke while moving anchors. | No Work Order entered | No Work Order entered into Delay Log
296 | 2021 | 2021-11-27 | Sandpiper | R&L |  | 47.9997 | Main Pump | Engine / Motor | None | replace 3 heads on main engine 3516 | No Work Order entered | No Work Order entered into Delay Log
297 | 2021 | 2021-12-05 | Ohio | Hydraulic |  | 51.4 | Ladder Pump | Pump Rebuild | 4812866 | fracture in underwater pump | Replace impeller UWP. | Remove broken impeller Install new impeller Remove new front door liner and install old wear liner for extend clearance Thrust bearing issues new impeller trap down about 1/4'' new impeller touch front pump shell . I mpeller clearance 1/4'' move thrust bearing about 1/4'' back Reported have Thrust bearing issues. plan to fix next time shutdown for repairs after we finish cammeron meadows project. Sean McGowan Inspected impeller and pump. The old front door was installed and rotated 180 from how it was removed. The problem seems to be the thrust bearing that was installed is 'shorter' then the original thrust bearing which is causing the entire pump shaft and impeller to sit inside the pump housing crooked. We plan on measuring the axial, radial play a our earliest convenience. Mark Manfredi is looking for our thrust bearing sent out for repair AND the notes of what was actually done to it.
298 | 2021 | 2021-12-08 | New York | Mechanical |  | 131.1494 | Main/Aux Generators | Generator #1 | 4812901 | LOST GENERATOR DUE TO ELECTRICAL TRIP @00:20,SWITCH GENERATOR. BLOWER FOR BOOM ASSIST KEEPS TRIPPING OUT | replace boom assist blower motor | Found blower motor to be faulted. Blower removed. Blower motor replaced. Blower installed. Work completed by Aaron Taylor, Dalton Padgett and Archie Gray.
299 | 2021 | 2021-12-08 | Sandpiper | R&L |  | 32.215 | Swing System | Winch System | 4812886 | GEARBOX WENT DOWN | HPU Gear Hydraulic Failure | Uppon HPU Hydraulic Single pump failure we noticed that the spline adaptor was cracked and the shaft on the pump was missed shaped , so i instructed the crew to change single pump due to the flaws on the pump , after single pump was installed and crew test ran engine and noticed knocking coming from the main drive gear internally , i instructed them to pull the K27 Pump to inspect the internal gears uppon inspection we noticed that gears on the inside of the gear box where bad so we proceeded to dissemble the gear box and found further damage 1. Needed new bearings 2. Bearing Pockets on gear housing had wear 3. Gears where bad on the main input shaft, K27 Bearing, Double pump, Single pump 4. Rear seal was bad Uppon repair , We changed bearings and gears proceeded to assemble and then filled back up the fluids and test ran the system to get the air out of the system
300 | 2021 | 2021-12-14 | Sandpiper | R&L |  | 53.8594 | Main Pump | Engine / Motor | 4813019 | replace head on main engine | Dredge Main engine mechanical failure | Converted to SO# 1768533: Inspection Details: Inspected Engine found that the engine Cylinder #9 Drop a valve which caused the engine to over heat and fail , upon inspection we found that the head was badly scared and had to be replaced, also inspected the turbo found damage on the turbo fins so we replaced , also bore scoped the exhaust manifolds to inspect for loose trash that could potentially cause more damage upon start up are inspection we reassembled engine and filled with fluids and test ran (GOOD)
301 | 2021 | 2021-12-14 | New York | Mechanical |  | 32.9833 | Tagline/Boom Assist | Boom Assist Wire | 4813001 | Boom assist wire broke | change boom assist wire | wire broke. day shift and night shift worked around clock to remove wire from point sheave. it was a mess up there.
302 | 2021 | 2021-12-17 | New York | Mechanical |  | 39.1667 | Spud System | Spud Wires | 4813043 | Replace stern spud wire | change stern spud wire | both crews worked on installing wire for several days. wire was installed backwards and had to be removed . during removal we broke chaser. wire was installed byjack kelley
303 | 2021 | 2021-12-18 | Texas | Hydraulic |  | 47.5331 | Cutter | Motor | 792854 | None | No Work Order entered | No Work Order entered into Delay Log
304 | 2021 | 2021-12-20 | Sandpiper | R&L |  | 55.2 | Main Pump | Engine / Motor | 4813490 | None | No Work Order entered | No Work Order entered into Delay Log
305 | 2021 | 2021-12-22 | 53 | Mechanical |  | 216 | Tagline | Tagline Winch (motor, gearbox, etc.) | 4813071 | Tagline gearbox repair | Tagline gearbox repairs | Coverted to SO# 1768428: No Findings Entered yet
306 | 2021 | 2021-12-27 | New York | Mechanical |  | 79.5 | Crane Boom | Boom Structure | 4813504 | Working on Welding repairs in Boom. Spudded down in Inner Harbor near office. | No Work Order entered | No Work Order entered into Delay Log
307 | 2022 | 2022-01-11 | 55 | Mechanical |  | 25.6711 | Auxiliary Systems | Compressed Air | N/A | Water froze in air lines | No Work Order entered | No Work Order entered into Delay Log
308 | 2022 | 2022-01-15 | Carolina | Hydraulic |  | 110.8522 | Ladder Pump | Bearings / Shafts | 4813489 | None | Thrust bearing replacement | Pump end seal failed Stuffing box shot Thrust Bearing is 14,400LBS dry. Front door with clean-out 24,000lbs Bearing: Lift= Thrust=
309 | 2022 | 2022-01-17 | Terrapin Island | Hopper |  | 58.625 | Dredge Pump | Gland Seal | 4184362 | None | Replace the gland seal - Stbd Pump - Leaking too much water | Gland seal water leaks approx. 2 gallons per minute. Gland seals tore up. Realigned lineshaft brg. to pump seal housing.
310 | 2022 | 2022-01-21 | New York | Mechanical |  | 26.1942 | Main/Aux Generators | PP1 | 1769537 | Work on PP1; Moved to Spud down location outside of office to finish repairs | Work Order not found | Work Order not found
311 | 2022 | 2022-01-26 | Carolina | Hydraulic |  | 48.7569 | Idler / Spud Barge | GL10 | 4813835 | None | Replace Sprockets and Drive Chain on GL10 Spud Winch | 26 Jan 2022 - 2230hrs - Chain is skipping on Spud Winch hoist traction motor sprocket. Excessive wear found on both sprockets. New sprockets have been received and have been sent to be bored to shaft specs. 27 Jan 2022 - Hooked up drve chain to jacking motor to attempt sud movement. Chain skipped on gearbox input shaft sprocket. Jackng motor is in fixed positon on Gearbox and proper chain tensioning is not possible. Drive sprocket worn excessively. Removed Traction motor and sent to shop to have tapered sprocket mounted. Worn gearbox input shaft sprocket removed. Shaft dressed and prepped for new sprocket. 28 Jan 2022 - New Gearbox sprocket received and installed. Traction motor with drive sprocket received, mounted and aligned. Chain installed, wires connected, and function tested. Dredging resumed approx 2330hrs.
312 | 2022 | 2022-02-09 | New York | Mechanical |  | 25.2 | Main/Aux Generators | PP1 | 4814066 | CHANGE OIL AND FILTERS | Troubleshoot boom drift and stick float issues | Found the pressure for booming up was at 80 bar, adjusted to 200 bar. Replaced all 4 relief valves on the boom cylinder load hold blocks wich rectified the boom drifting issue. On the stick float we found that the 1st and 2nd stage were not set correctly. Set to recommended specs from Keith. Aaron Taylor
313 | 2022 | 2022-02-10 | 53 | Mechanical |  | 69 | Tagline | Tagline Winch (motor, gearbox, etc.) | 1770611 | None | Work Order not found | Work Order not found
314 | 2022 | 2022-02-13 | Sandpiper | R&L |  | 81.9167 | Cutter | Motor | 4814293 | replaced k27 pump, pilot pump, and 2 saffer pumps on ladderffer | K27 pump failure & Removal | We where having issues with the hydraulics , issues- hydraulics causing issues do to pilot pump on the 3406 blowing the seal and filling the engine up with hydraulic fluid which came out of the valve cover breather and sprayed all over the wall , so we installed a gauge to determine pump pressure which was not stable and was causing other peaces of equipment to fail ( traveling spuds, holding spud , and cutter head issues ) The engine driven pump supplies pilot pressure to all these peaces of equipment ( Symptoms where traveling spuds and holding spuds where coming up together and not function correctly , Free fall was not operational function was going straight up Cutter head had no function just free spinning in one direction 1. Changed pilot pump on the 3406 2. Changed K27 pump on the 3406 3. Changed Cutter Head 4. Changed Cutter Head motor
315 | 2022 | 2022-02-15 | Terrapin Island | Hopper |  | 121 | Other | Other Mechanical | 4814218 | Vessel at anchor surveying the vessel to find the sounce of water and and follw up repairs to the hull. | Services for Repairs | Converted to SO# 1770758: No Findings
316 | 2022 | 2022-02-17 | Sandpiper | R&L |  | 26.6167 | Cutter | Motor | None | hydraulic pump | No Work Order entered | No Work Order entered into Delay Log
317 | 2022 | 2022-02-18 | Ellis Island | Hopper |  | 163.1831 | Piping/Hoses | Pump Room Discharge Pipe | None | Repair Bow Connection Elbow Pipe | No Work Order entered | No Work Order entered into Delay Log
318 | 2022 | 2022-02-21 | Sandpiper | R&L |  | 35.5331 | Main Pump | Pump Rebuild | 4814402 | replace booster pump impeller | Repairs to Booster Pump | Repairs to booster pump after impeller structural failure. Disassemble piping and pump assembly. Clean and maintenance thrust bearing shaft. Replace cracked suction liner. Reassemble pump with new impeller. Reassemble piping.
319 | 2022 | 2022-02-24 | Carolina | Hydraulic |  | 139.6969 | Main Pump | Pump Rebuild | 4814445, 4814426 | Scheduled Maintenance. Opportunity tasks - replace sleeve | Stuffing box R&R / Sleave replacement | Stuffing box was eaten away on the inside.
320 | 2022 | 2022-02-27 | 55 | Mechanical |  | 36.2261 | Main Hoist | Holder | 4814843 | None | Aft Hoist Motor Replaced | Removed the aft hoist motor #2 in crane. Replaced with a spare motor we had sitting in Norfolk VA. This was a reconditioned motor that had been installed in the crane previously and serviced by Keystone Electric in Baltimore. Operator noticed a burned electrical smell in the crane. Further inspection of the hoist motor revealed possible failure of motor. See picture attached. Commutator bars had solder bubbling our of ends.
321 | 2022 | 2022-03-10 | 55 | Mechanical |  | 53.6492 | Main Hoist | Holder | 4814744 | aft hoist motor failed | # 2 Hoist DC Motor Removal and Replacement Style Old Style # 27N8958 New Style # 27N8959 | Findings will be entered when report is completed by service provider ( Key Stone Electric )
322 | 2022 | 2022-03-15 | Texas | Hydraulic |  | 76.3906 | Spuds / Xmass Tree | Tree Structure | 4814743 | None | Xtree Inspection (ILM) | Found pin on center sheave with wedges missing on both sides and pin had moved toward one side ready to come out sheave box. Welder hammered pin in place and welder welded wedges in place welder reported that original wedges had very little weld on them and bearly any penetration . Found one missing bottom 4 inch pin that secures tree on bottom of frame .
323 | 2022 | 2022-04-02 | Dodge Island | Hopper |  | 37.0994 | Dredge Pump Engine | Other | 4071941 | None | Stbd Dredge Engine - Troubleshoot Shutdowns | The differential lube oil pressure sensors were showing code of irregular or erratic readings. The sensors were replaced and the codes did not clear. Cylinder cut out test were performed and sent to the Carter Cat tech for review. The ECM was swapped out with the one from the port dredge engine to check for possible ECM failure. The port dredge ran all night with the stbd ECM installed. The stbd dredge engine ran with the Port ECM all night and shut down in the AM. A Cat Tech from Carter CAt arrived on 3 April around noon to assist with trouble shooting the engine. The ECM's were returned to their proper engines and troubleshooting was begun. It was determined that there was a short in the signal wire from the unfiltered lube oil sensor. A by-pass wire was ran externally along the wire harness from the sensor to the connection block in the main ECM. The engine was tested to check for codes and there were no more active codes. The wire was secured to the existing wire harness with wire ties and the engine was test ran by topping off the existing load, The engine pumped off a complete load with out any issues. The ship returned to work at 1800 on April 3rd.
324 | 2022 | 2022-04-07 | 55 | Mechanical |  | 36.1831 | Main Hoist | Holder | 4815483 | CRANE TRIPPED, TROUBLE SHOOTING | C/O Hoist Motor FWD #1 Drive Transformer | Initial troubleshooting involved: 1. the change out of snap in terminal strip connector blocks that showed damage. 2. The cutting back and adding of wire extensions where damage was showing. 3. Checking tightness of connections 4. Changing out blown fuses. 5. Inspecting the wiring in the transformer and re-wiring suspected connections. 6. Checking resistance with multi meter and Megger through various sections of the circuits. See all attachments included in this WO This transformer has been requested to be added to NS Remove failed 480/240V 7.5 KVA Transformer for the Hoist Motor FWD #1 Drive- Square D P/N 7S40F Grainger # 2CN73 Cost $ 1350.00
325 | 2022 | 2022-04-13 | Texas | Hydraulic |  | 89.8072 | Ladder Pump | Motor / Engine | 792995 | wire shorted out | Replace Ladder Pump Motor | Motor had a bad leg it burned up all three conductors wires Also burned up the windings inside. Dredge continue repairing UWP motor. Est. ROW is evening of 4/16.
326 | 2022 | 2022-04-20 | 53 | Mechanical |  | 28.7194 | Main / Aux. Generators | Main Generator Engine | 4815650 | None | Change out idler pulley pillar block #2 engine | Main generator. Pillow block shaft replacement. The pillow block shaft for the idler pulley was found to be bent following the repairs to the bearing on the pillow block this morning. The dredge is down and will remain down until the replacement shaft is received and can be installed. bearing went out in pillar block, changed out pillar block and installed shaft. ordered the parts
327 | 2022 | 2022-04-25 | Padre Island | Hopper |  | 135.9994 | Dredge Pump | Shafting | 4815725 | While adjusting the impellor pump, the shaft and bearings in the gear box assembly broke. | Dredge Pump Line Shaft and bearing repair | Converted to SO# 1773985: PI @ dock due to brkn shaft gear bx in pmp impllr. RTW 5/1 aftr repair complt. The Padre Island remained at dock due to the shaft and bearings in the gear box assembly breaking while the dredge pump impeller was adjusted on 4/23 (SJ081). Estimated RTW 5/1 once repair is completed.
328 | 2022 | 2022-04-26 | Texas | Hydraulic |  | 24.4667 | Spuds / Xmass Tree | Wires | 4815889 | broke stern wire | replace D03 ) bone crusher hose (ILM) | captain found 2 bubbles on out side of hose and damage ribs on the inside
329 | 2022 | 2022-04-27 | 54 | Mechanical |  | 332.8331 | Spud System | Spud Structure | 4815856 | Leak in spud well | DryDocking for Repairs to Side Shell of Starboard Spudwell | Converted to SO#1774391: No Findings
330 | 2022 | 2022-04-30 | New York | Mechanical |  | 64.3133 | Spud System | Spud Wires | 4815925 | lifting stern spud to take a step back.....spud started freefalling down... Bottom wire broke | Pick and secure | Wire failed on 30April2022 @ 23:30. 01May2022 - Brainstormed a plan to pick and secure spud to continue shoaling 02May2022 - Divers onboard inspecting sheaves and location of wire - wire jumped sheave on stbd side and sheave on port side was completely missing Divers help crew remove and place wire through bottom sheave od spud Crew pulled wire onto deck and secured. Rolled eye in cable and secured with cable clamps Capt Tom onboard dredge discussing a plan to lift spud with Dredge 55 03May2022 - Dredge 55 arrived at dredge @ 08:00 Picked up spud and secured on dogs @ 18' Welder installing wedges around spud and welding in place Reinstall cat walk on front of carriage Pull carriage back to stern and secure to continue dredging operations
331 | 2022 | 2022-05-26 | 58 | Mechanical |  | 62.25 | Tagline | Tagline Winch (motor, gearbox, etc.) | 4816345 | drum shifted on shaft | Repair Drum | Converted to SO#1775812: No Findings / Not Completed yet - still IP
332 | 2022 | 2022-05-31 | Ohio | Hydraulic |  | 151.4167 | Ladder Pump | Gearbox | 4816439 | None | UWP gearbox oil leak | 1JUL22 We opened the gearbox and replaced all the bearings and the output seal and the oil cooler. Then we smoked the aft bearing on the port intermediate shaft. Had ato remove the shaft and install a sleeve and new bearing on the shaft then reinstall the shaft and monitored the temps upon restart. The cause of the bearing failure was the gear oil circulation pump wasn't pumping enough oil and the flow meter was adjusted down. Installed a new pump and ordered a new spare, see REQ#: 4579432 and a spare spider coupling REQ#: 4579455 for spares. Adjusting the flow meter to alarm properly and training the crew on operations so this doesn't happen again. Also replaced 5 of the oil flow regulators. Up and running bearing temps are all around 130 degrees F and the oil flow is 36 gpm.
333 | 2022 | 2022-05-31 | 54 | Mechanical |  | 108.4833 | Crane Boom | Boom Wires | 4816411 | remove broken wire rubber rest on boom | Crop and renew Lacing on Boom | Converted to SO#1775779: Requirements: Crop and Renew two sections of damaged lacing on the Main Boom- The repair areas are in such positions that two crews could work simultaneously. This is the preference of GLDD Damaged Area #1 - Angle Iron A-36 - 3-1/2 in x 2-1/2 in x 3/8 in Damaged Area #2- Angle Iron A-36- 4 in x 3in x 3/8 in Request 2 each 20 ft pieces of each size angle iron blasted and primed for cost purposes.
334 | 2022 | 2022-06-05 | 53 | Mechanical |  | 31.5664 | Crane Swing | Swing Circle (rollers, etc.) | 1776468 | Crane rail tabs breaking off | Work Order not found | Work Order not found
335 | 2022 | 2022-06-07 | 53 | Mechanical |  | 72.15 | Main / Aux. Generators | Main Generator Engine | 1776476 | Planned CAT engine work | Work Order not found | Work Order not found
336 | 2022 | 2022-06-12 | 54 | Mechanical |  | 82.7167 | Crane Boom | Boom / Gantry Sheaves | 4251945 | Bearing on holding wire tip sheave failed | Boom Point Sheave asem removal | Boom Point Sheave Retainer ring weld failed and alowed boom point sheaves to move around from side to side.
337 | 2022 | 2022-06-12 | 53 | Mechanical |  | 45.9 | Electrical/Electronics | PLC | 4816621 | None | Troubleshoot closing drive tripping | drive tripped off 15 times, changed bridge board, 0600 drive tripped off at 1600, found burnt up bridge board and 75 ohm resistors burnt up
339 | 2022 | 2022-06-20 | 54 | Mechanical |  | 25.5833 | Crane Swing | Drive (motor, gear box, etc.) | 4251951 | AC Drive Motor, check end time. | Benshaw 2400 repair | Bad Control Board
340 | 2022 | 2022-06-25 | Ohio | Hydraulic |  | 124.2667 | Ladder Pump | Gearbox | 4816439 | None | UWP gearbox oil leak | .1JUL22 We opened the gearbox and replaced all the bearings and the output seal and the oil cooler. Then we smoked the aft bearing on the port intermediate shaft. Had ato remove the shaft and install a sleeve and new bearing on the shaft then reinstall the shaft and monitored the temps upon restart. The cause of the bearing failure was the gear oil circulation pump wasn't pumping enough oil and the flow meter was adjusted down. Installed a new pump and ordered a new spare, see REQ#: 4579432 and a spare spider coupling REQ#: 4579455 for spares. Adjusting the flow meter to alarm properly and training the crew on operations so this doesn't happen again. Also replaced 5 of the oil flow regulators. Up and running bearing temps are all around 130 degrees F and the oil flow is 36 gpm.
341 | 2022 | 2022-06-25 | 53 | Mechanical |  | 62.7333 | Electrical/Electronics | MCC / Switch Gear | 4816907 | Choke coil burnt up | Change out burnt up coil on Closer phase | Changed out coil that was burnt up, and found 1 broken wire on capacitor on SCR
342 | 2022 | 2022-07-09 | Ohio | Hydraulic |  | 195 | Ladder Pump | Motor / Engine | 4532599 | None | Ladder Pump Gearbox Quarterly PM/Inspection | Replaced STBD high speed shaft and bearings. Replaced Port intermediate aft bearing. Hone port intermediate bearing bore. Replaced 2 antiroll pins for Port high speed aft bearing and Port intermediate aft bearing. Cleaned out all oil squirters screens and adjust for proper bearing oil flow. Checked backlash on all gears. average lash was .018 to .020 thousands. Resealed box and torqued all superbolts to 55ft lbs. After torque there was a .008 clearance between split line near aft intermediate bearing. Realigned Stbd motor and changed coupling, hardware and gaskets. Test gearbox bearing temperatures. highest temp was 135 degrees.
343 | 2022 | 2022-07-20 | Dodge Island | Hopper |  | 28.5 | Generator Engine | Other | 4072127 | None | Port Generator - Replace air starter | No Findings entered
344 | 2022 | 2022-07-26 | 54 | Mechanical |  | 116.2 | Crane Boom | Boom Winch | 4817452 | Boom motor failure | Complete Inspection of all DC Motors / Generators brushes/holders and commutators associated with Crane Boom Operation | Amerimex came out to Dredge-54 and ispected and repaired all motors as needed.
345 | 2022 | 2022-08-05 | Ohio | Hydraulic |  | 46.8167 | Main Pump | Engine / Motor | 4817827 | None | Inspect and repair vibration in STBD pump Driveline | STBD pump Driveline is shaking badly. Troubleshooting and inspecting. Went through the Driveline to find the source of vibration. Determined to rebuild the HRC coupling on the fly wheel.
346 | 2022 | 2022-08-08 | Alaska | Hydraulic |  | 169.8833 | Spuds / Xmass Tree | Tree Structure | 1779011 | Installing xmas tree before starting up | Work Order not found | Work Order not found
347 | 2022 | 2022-08-11 | Ohio | Hydraulic |  | 78.1333 | Generators | Main Generator | 4817430 | None | Condut the UT Survey as Required for ABS LL Renewal | Converted to SO# 1778416: Incorrect vessel (Derrick 64)
348 | 2022 | 2022-08-13 | Liberty Island | Hopper |  | 44.15 | Main Engine/Propulsion | Other | 851900 | Starboard Turbo Overheated/Failure - Repair | Stbd Propulsion engine inboard turbo failure and Exhaust bellows | Exhaust bellows found damaged and torn away from the inlet exhaust to turbo. This is what caused the high temp on the engine. The loss of exhaust to the turbo. Inspection of engine and turbo's we then found damaged to the compressor blades. `
349 | 2022 | 2022-08-17 | Liberty Island | Hopper |  | 34.2667 | Gimbal Hoist | Other | 851907 | Gimbal bolts sheared | Remove and replace stbd gimble from damage | No Findings Entered
350 | 2022 | 2022-08-27 | Ohio | Hydraulic |  | 35.5667 | Ladder | Ladder Structure | 4818043 | None | Damaged ladder service water lines and air lines | Swing wire got slack and ripped off ladder service water line, cooling water line for ladder gear box cooler, and ladder air supply line for winches. Repaired and replaced all damaged lines, put new flanges, gaskets and bolts. Tested for leaks. Flushed out any debris from ladder service water line.
351 | 2022 | 2022-08-28 | Alaska | Hydraulic |  | 25.05 | Generators | Main Generator | 1729214 | changing the power pack | Change Out EMD Injector #1 cylinder on main gen. | Main generator injector #1 & 2 were changed out at 11916 hours 08/28/22
352 | 2022 | 2022-09-05 | Ohio | Hydraulic |  | 24.3167 | Main Pump | Pump Rebuild | 4174225 | Main Pump #1
353 | 2022 | 2022-09-07 | Iowa | R&L |  | 70.85 | Ladder | Wire | None | Ladder wire broke
354 | 2022 | 2022-09-13 | 54 | Mechanical |  | 26.7167 | Main Hoist | Holder | 4251964 | brake on holding drum not holding load, troubleshooting
355 | 2022 | 2022-09-16 | Illinois | Hydraulic |  | 120.9667 | Pipeline | Pipe Leak | None | None
356 | 2022 | 2022-09-29 | Ohio | Hydraulic |  | 35.0333 | Ladder Pump | Shaft | 4818797 | None

## Summary
|  |  | Hopper | Hydraulic | Mechanical | R&L
Enter in blue shaded block only |  | Avg Daily costs: | 30000 | 25000 | 23333 | 17000 | <-- (Arbitrary numbers for analysis purposes only)
|  | Avg Hr costs: | 1250 | 1041.6667 | 972.2083 | 708.3333
|  | Totals: | Hopper | Hydraulic | Mechanical | R&L
| Count: | 355 | 105 | 143 | 95 | 12
| Hours: | 30231.7678 | 9260.4192 | 12631.6181 | 7834.9169 | 504.8136
| Days: | 1259.657 | 385.8508 | 526.3174 | 326.4549 | 21.0339
| Delay Costs: | 32708207.2851 | 11575523.9583 | 13157935.4745 | 7617171.5444 | 357576.3079
2017 | # of Major Mechanical: | 44 | 15 | 19 | 10 | 0
| Hours: | 3678.14 | 896.97 | 2253.57 | 527.6 | 0
| Delay Costs: | 3981618.3667 | 1121212.5 | 2347468.75 | 512937.1167 | 0
2018 | # of Major Mechanical: | 67 | 31 | 30 | 6 | 0
| Hours: | 7171.73 | 3448.18 | 3031.02 | 692.53 | 0
| Delay Costs: | 8140820.9371 | 4310225 | 3157312.5 | 673283.4371 | 0
2019 | # of Major Mechanical: | 65 | 23 | 23 | 19 | 0
| Hours: | 6985.9 | 2377 | 2174.21 | 2434.69 | 0
| Delay Costs | 7603077.9904 | 2971250 | 2264802.0833 | 2367025.9071 | 0
2020 | # of Major Mechanical: | 48 | 12 | 26 | 10 | 0
| Hours: | 3294.0561 | 865.7225 | 1965 | 463.3336 | 0
| Delay Costs: | 3579484.9228 | 1082153.125 | 2046875 | 450456.7978 | 0
2021 | # of Major Mechanical: | 82 | 16 | 28 | 30 | 8
| Hours: | 5435.4919 | 1049.7231 | 1711.3975 | 2384.4742 | 289.8972
| Delay Costs: | 5618409.0698 | 1312153.8194 | 1782705.7292 | 2318205.6555 | 205343.8657
2022 | # of Major Mechanical: | 49 | 8 | 17 | 20 | 4
| Hours: | 3666.4497 | 622.8236 | 1496.4206 | 1332.2892 | 214.9164
| Delay Costs: | 3784795.9983 | 778529.5139 | 1558771.412 | 1295262.6302 | 152232.4421
2023 | # of Major Mechanical: | 0 | 0 | 0 | 0 | 0
| Hours: | 0 | 0 | 0 | 0 | 0
| Delay Costs | 0 | 0 | 0 | 0 | 0 |  | DO NOT MOVE OR CHANGE
2024 | # of Major Mechanical: | 0 | 0 | 0 | 0 | 0 |  | Plant | Vessel | Division
| Hours: | 0 | 0 | 0 | 0 | 0 |  | 0101 | Alaska | Hydraulic
| Delay Costs: | 0 | 0 | 0 | 0 | 0 |  | 0103 | Ohio | Hydraulic
[8 empty] | 0105 | Illinois | Hydraulic
[8 empty] | 0110 | Carolina | Hydraulic
[8 empty] | 0118 | Texas | Hydraulic
[8 empty] | 0120 | New York | Mechanical
[8 empty] | 0132 | Dredge-55 | Mechanical
[8 empty] | 0132 | 55 | Mechanical
[8 empty] | 0133 | Dredge-53 | Mechanical
[8 empty] | 0133 | 53 | Mechanical
[8 empty] | 0134 | Dredge-54 | Mechanical
[8 empty] | 0134 | 54 | Mechanical
[8 empty] | 0138 | Dredge-58 | Mechanical
[8 empty] | 0138 | 58 | Mechanical
[8 empty] | 0141 | Sugar Island | Hopper
[8 empty] | 0142 | Dodge Island | Hopper
[8 empty] | 0143 | Padre Island | Hopper
[8 empty] | 0147 | Liberty Island | Hopper
[8 empty] | 0148 | Terrapin Island | Hopper
[8 empty] | 0151 | Ellis Island | Hopper
[8 empty] | 0152 | Newbuild Hopper | Hopper
[8 empty] | 0170 | Rock Install Vessel
[8 empty] | 0202 | Unloader #2
[8 empty] | 0211 | Jack | Booster
[8 empty] | 0212 | Jessie | Booster
[8 empty] | 0214 | Reggie | Booster
[8 empty] | 0215 | Erin | Booster
[8 empty] | 0216 | Buster | Booster
[8 empty] | 0217 | Texas JR | Booster
[8 empty] | 0218 | Captain Barney | Booster
[8 empty] | 0219 | Booster 9 | Booster
[8 empty] | 0229 | Apache
[8 empty] | 0243 | Fuel Barge 1001
[8 empty] | 0244 | Fuel Barge 1002
[8 empty] | 0245 | Fuel Barge 1003
[8 empty] | 0300 | Lake Michigan
[8 empty] | 0302 | D.B. Mackie
[8 empty] | 0303 | PR Dickinson
[8 empty] | 0307 | Brangus
[8 empty] | 0311 | Richard M Lowry
[8 empty] | 0316 | McCormack Boys
[8 empty] | 0322 | Plametto State
[8 empty] | 0334 | Evergreen State
[8 empty] | 0340 | Cavalier State
[8 empty] | 0341 | Volunteer State
[8 empty] | 0342 | Tarheel State
[8 empty] | 0343 | Hoosier State
[8 empty] | 0354 | Lake Tahoe
[8 empty] | 0355 | Lone Star State
[8 empty] | 0356 | Multi-Cat 01
[8 empty] | 0357 | Multi-Cat 02
[8 empty] | 0360 | West Bay
[8 empty] | 0362 | Cooper River
[8 empty] | 0363 | St Johns River
[8 empty] | 0365 | Muskegon River
[8 empty] | 0366 | Saginaw River
[8 empty] | 0367 | St. Louis River
[8 empty] | 0368 | Wolf River
[8 empty] | 0369 | York River
[8 empty] | 0371 | East River
[8 empty] | 0372 | Miami River
[8 empty] | 0373 | Colorado River
[8 empty] | 0375 | Potomac River
[8 empty] | 0377 | Pearl River
[8 empty] | 0378 | Columbia River
[8 empty] | 0380 | Calcasieu River
[8 empty] | 0382 | South Bay
[8 empty] | 0384 | Ohio River
[8 empty] | 0390 | Sandusky Bay
[8 empty] | 0391 | Winyah Bay
[8 empty] | 0392 | Hamby Pond
[8 empty] | 0394 | Raritan Bay
[8 empty] | 0395 | Galveston Bay
[8 empty] | 0396 | Chesapeake Bay
[8 empty] | 0397 | Sturgeon Bay
[8 empty] | 0411 | GL-601 Scow
[8 empty] | 0412 | GL-602 Scow
[8 empty] | 0413 | GL-603 Scow
[8 empty] | 0414 | GL-604 Scow
[8 empty] | 0431 | GL-31 Scow
[8 empty] | 0451 | GL-501 Scow
[8 empty] | 0452 | GL-502 Scow
[8 empty] | 0461 | GL-61 Scow
[8 empty] | 0463 | GL-63 Scow
[8 empty] | 0464 | GL-64 Scow
[8 empty] | 0465 | GL-65 Scow
[8 empty] | 0466 | GL-66 Scow
[8 empty] | 0467 | GL-67 Scow
[8 empty] | 0468 | GL-68 Scow
[8 empty] | 0469 | GL-69 Scow
[8 empty] | 0471 | GL-701 Scow
[8 empty] | 0472 | GL-702 Scow
[8 empty] | 0506 | GL-117 Deck Barge
[8 empty] | 0512 | GL-123 Deck Barge
[8 empty] | 0515 | GL-126 Deck Barge
[8 empty] | 0516 | GL-127 Deck Barge
[8 empty] | 0517 | GL-128 Deck Barge
[8 empty] | 0519 | GL-129 Deck Barge
[8 empty] | 0520 | GL-146 Deck Barge
[8 empty] | 0522 | GL-148 Deck Barge
[8 empty] | 0524 | GL-150 Deck Barge
[8 empty] | 0531 | GL-173 Deck Barge
[8 empty] | 0533 | GL-175 Spider Barge
[8 empty] | 0535 | GL-177 Spud Barge
[8 empty] | 0537 | GLDD-537-BH
[8 empty] | 0540 | GL-182 Deck Barge
[8 empty] | 0541 | GL-183 Deck Barge
[8 empty] | 0542 | DB-184
[8 empty] | 0543 | DB-185
[8 empty] | 0544 | DB-186
[8 empty] | 0545 | DB-187
[8 empty] | 0546 | GL-160 Skidder Barge
[8 empty] | 0547 | GL-161 Skidder Barge
[8 empty] | 0548 | GL-162 Skidder Barge
[8 empty] | 0560 | GL-101 Anchor Barge
[8 empty] | 0562 | GL-102 Anchor Barge
[8 empty] | 0563 | GL-103 Anchor Barge
[8 empty] | 0564 | GL-107 Anchor Barge
[8 empty] | 0565 | GL-111 Anchor Barge
[8 empty] | 0566 | GL-104 Anchor Barge
[8 empty] | 0569 | AB-113
[8 empty] | 0570 | AB-114
[8 empty] | 0571 | AB-115
[8 empty] | 0572 | GL-109 Anchor Barge
[8 empty] | 0573 | GL-110 Anchor Barge
[8 empty] | 0574 | AB-116
[8 empty] | 0575 | GL-112 Anchor Barge
[8 empty] | 0576 | AB-119
[8 empty] | 0577 | AB-120
[8 empty] | 0578 | AB0117
[8 empty] | 0579 | AB-118
[8 empty] | 0584 | K5 4002 Spud Barge
[8 empty] | 0585 | GLDD-585-BH
[8 empty] | 0591 | GL-142 Idler Barge
[8 empty] | 0592 | GL-143 Spud Barge
[8 empty] | 0594 | GL-141 Idler Barge
[8 empty] | 0595 | G.L.10
[8 empty] | 0600 | Derrick 60
[8 empty] | 0601 | Derrick 71
[8 empty] | 0602 | Derrick 62
[8 empty] | 0603 | Derrick 72
[8 empty] | 0604 | Derrick 64
[8 empty] | 0605 | Derrick 65
[8 empty] | 0606 | Derrick 66
[8 empty] | 0607 | Drrick 73
[8 empty] | 0608 | Derrick 68
[8 empty] | 0609 | Derrick 69
[8 empty] | 0610 | Derrick 70
[8 empty] | 0611 | MB 1700
[8 empty] | 0615 | Crane 1
[8 empty] | 0620 | Crane 6
[8 empty] | 0622 | Crane 22
[8 empty] | 0623 | Crane 8
[8 empty] | 0624 | Derrick 74
[8 empty] | 0625 | Derrick 75
[8 empty] | 0626 | Derrick 76
[8 empty] | 0627 | Derrick 77
[8 empty] | 0631 | Grove RT880 Crane
[8 empty] | 0633 | Crane 7
[8 empty] | 0639 | Crane 17
[8 empty] | 0690 | Cat 390 Excavator
[8 empty] | 0691 | Cat 336EL Excavator
[8 empty] | 0692 | Excavator GL-692
[8 empty] | 0701 | Air Compressors
[8 empty] | 0703 | Pump
[8 empty] | 0704 | Welders
[8 empty] | 0706 | Misc Equip
[8 empty] | 0708 | Utility Vehicles
[8 empty] | 0709 | OFC Dump Shack
[8 empty] | 0710 | G.L. 710 PO Cube
[8 empty] | 0711 | G.L. 711 PO Cube
[8 empty] | 0712 | G.L. 712 PO Cube
[8 empty] | 0713 | Survey Equip
[8 empty] | 0714 | G.L. 714 PO Cube
[8 empty] | 0715 | G.L. 715 PO Cube
[8 empty] | 0716 | G.L. 716 PO Cube
[8 empty] | 0717 | G.L. 717 PO Cube
[8 empty] | 0718 | G.L. 718 PO Cube
[8 empty] | 0719 | G.L. 719 PO Cube
[8 empty] | 0735 | G.L. 735 PO Cube
[8 empty] | 0736 | G.L. 736 PO Cube
[8 empty] | 0761 | Drill Rig
[8 empty] | 0771 | Survey Crab 2
[8 empty] | 0772 | Survey Crab 3
[8 empty] | R004 | Cape Girardeau Yard
[8 empty] | R010 | Iowa | R&L
[8 empty] | R011 | Sandpiper | R&L
[8 empty] | R012 | L.W. | R&L
[8 empty] | R013 | L.P. | R&L
[8 empty] | R015 | Little Rock
[8 empty] | R016 | Commodore
[8 empty] | R017 | Chris L
[8 empty] | R018 | Lake Lady
[8 empty] | R019 | Maggie
[8 empty] | R030 | Booster R030-22
[8 empty] | R031 | Booster R031-22
[8 empty] | R032 | Booster R032-20
[8 empty] | R033 | Booster R033-20
[8 empty] | R034 | Booster R034-20
[8 empty] | R035 | Booster R035-20
[8 empty] | R036 | Booster R036-20
[8 empty] | R037 | Booster R037
[8 empty] | R038 | Booster R038-18
[8 empty] | R039 | Booster R039
[8 empty] | R040 | Booster R040
[8 empty] | R041 | Booster R041
[8 empty] | R042 | Booster R042
[8 empty] | R043 | Booster R043
[8 empty] | R044 | Booster R044-20
[8 empty] | R045 | Booster R045-20
[8 empty] | R046 | Booster R046-18
[8 empty] | R047 | Booster R047-08
[8 empty] | R051 | Fort Smith
[8 empty] | R057 | White River
[8 empty] | R058 | Captain Zed
[8 empty] | R060 | Farm Boy
[8 empty] | R061 | Plow Boy
[8 empty] | R062 | Chore Boy
[8 empty] | R063 | Uniserve
[8 empty] | R064 | Arkansas
[8 empty] | R065 | Missouri
[8 empty] | R067 | Delaware Bay

## MCIA Cases
Case ID | Case Title | Scribe | Case Type | Operating Division | Project Number | Project Name | Delay Tracker ID # | OSHA Number | Incident Outcome | MCIA Date | Case Status | Prop Number | Alternate Scribe | Lead Contact | Executive Review Team | Date of Incident | Time of Incident | Location of Incident | Incident Type | JSA Review | Job Site | Operation Underway | Job Task Underway | Weather | Supervisor | Crew Configuration | Plant Number | Vessel Name | Vessel / Equipment | Tools / Materials | Barriers that Worked | Barriers that Failed | Recovery Factors Summary
30 | Equipment Damage Survey Boat Hallets Point | Ed ODowd | Mechanical | Int'l - Hydraulic Dredging | 022442 | SUEZ CANAL; EGYPT | NONE | 0 |  | 08/02/2016 | Complete | 924 |  | Ed ODowd | Steve O'Hara, Sam R Morrison, Ed Tiearney | 08/09/2015 | 1730 | Booster | Other | No | Crewboat/Survey Boat | Project - Attn.Plant | Idle | High Winds | Hector Gonzales | Unmanned |  |  | Vessel was moored Starboard to Starboard along side the Survey Boat Potomac River on the Starboard side of the Buster | N/A | Other | JSA - Job Safety Analysis, PTP - Pre-Task Planning | At 07:30pm the Dredge Carolina Deck Captain instructed the Coastal Guardian operator to support the Hallets Point with their crane to slow the ingress of the water instead of lifting it out. This would allow time for the Tug Boats Paul R. Dickinson and Richard M. Lowry operators to get the Crane 1 (GL143) in position. The tugboat Hoosier State operator was contacted by the Deck Captain and asked him to be on standby incase his assistance was required. When the Coastal Guardian arrived they positioned themselves at the Starboard side of the Buster and held the Hallets Point with their crane. The Crane 1 (GL 143) spudded down and made arrangements to basket lift the vessel. A slow lift took place allowing water to be drained from the Hallets Point. She was then placed in a boat cradle on the deck of the Crane 1 (GL143) The Lever-man notified the Project Management of the incident once the Hallets Point was secured.
31 | GL67 Boom Damage | Matt Ferrell | Mechanical | Rivers & Lakes Dredging | RR1229 | MISS RVR & HARBOR; KY; MO; AR; TN | NONE | 0 |  | 08/05/2016 | Complete | 3438 | Christopher Charron | Matt Ferrell | Chris Faught, Steven Lane, David J Johanson, Andrew M Funke | 08/03/2016 | 1030 | Derrick | Vessel Accident -allision / collision, grounding | No | Derrick | Mob/Demob | In Process | Cloudy | William Waltman | Tug crew were on tugs and GLDD Mate and Engineer were at stern of tow. |  |  | GL-67 and Marquette Tugs | None | JSA - Job Safety Analysis, PPE - Personal Protection Equipment, PFD - Personal Flotation Device | Company Policy | No crew members were in the area at the time of impact. Damage was isolated to the boom of the GL-67. Tow was going at a slowing rate through bridge and no damage was caused to bridge.
33 | MCIA 053 Dozer Sinking | Manny Vianzon | Mechanical | Hopper Dredging | 015526 | ROBERT MOSES STATE PARK; FIRE ISLAND; NY | NONE | 0 |  | 11/17/2015 | Complete | 1374 |  | Manny Vianzon | Christopher M Wire, Steve O'Hara | 11/17/2015 | 0230 | Fill Site | Motor Vehicle Incident | Yes | Fill Site | Project - Land/Disposal Area | In Transition |  | Barry Jones | 3rd Shift Bulldozer Operator (Local 138) working at dredge discharge adding shore pipe to the lower discharge line, 17 yrs as an Operator / First Beach Job (2 weeks into project). Shift Foreman on the Loader and another Dozer were in the area. | 0646 | GL 646 | GL 646 Caterpillar D7E Bulldozer with RTK Setup. Dozer was backing into the surf zone after adding pipe to the lower discharge line. |  | JSA - Job Safety Analysis, PTP - Pre-Task Planning |  | Operator grabbed RTK Equipment prior to evacuating the bulldozer. Site team mobilized an excavator to recover the machine at the next low tide. Operator was able safely exit the cab once dozer lost power.
46 | MCIA 039 - Spider Barge Arm Break | Armand F Riehl | Mechanical | Hydraulic Dredging | 072445 | SAVANNAH HARBOR EXPANSION PROJECT (SHEP) | NONE | 0 |  | 08/20/2016 | In Progress | 1821 |  | Armand F Riehl | David Rappe, Bill Baumann, David J Johanson | 08/16/2016 | 0400 | Attendant Plant - Other | Mechanical Breakdown | Yes | Attendant Plant - Other | Project - Dredge | In Process |  |  | Operator, mate and two deck hands. The operator was up stairs in the control tower. The mate and one deck hand were on deck. | 0533 | G.L. 175 | The spider barge was 600' behind the Dredge Illinois with the GL 66 scow on the port side. The tug Miss Emily was tided to the outside of the tug and the tug Allie B was connected by their tow bridal and tided off to the outside of the scow. | The discharge arm was connected to spider arm winch with an eight parted 3/4" wire. The 1 1/4" stay wires are connected to the arm with 1 1/2" shackles. | Mechanical - SOP | Mechanical - Material Specs
64 | MCIA 005_2016 | James P Arias | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | NONE | 0 |  | 05/05/2016 | Complete | 1383 |  | Mike Hungerford | Steve O'Hara, Sam R Morrison | 09/01/2016 | 2100 | Booster | Other | No | Booster | Project - Attn.Plant | Clean Up |  | Hector Gonzales | Rey Canda - Leverman Utah/Alabama/Maine for 6 Years, Mate of Carolina for 2 Years, Alex Zaragoza - Deckhand of Carolina for 3 years | 0219 | Booster #9 | See attached | As per attached Vessel/Equipment configuration | Step Back for Safety, Stop Work | JSA - Job Safety Analysis, Mechanical - SOP | The task was completely stopped after a crack was seen on the top portion of pump casing flange. It was reported immediately to the CSD Carolina Captain & Deck Captain.
71 | MCIA 001 - Crane Collision 72464 | Dave Johanson | Mechanical | Hydraulic Dredging | 072464 | WILMINGTON INNER HARBOR; SMITH ISLAND | NONE | 0 |  | 09/09/2016 | Complete | 2441 |  | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 01/03/2015 | 0830 | Derrick | Vessel Accident -allision / collision, grounding | No | Derrick | Project - Attn.Plant | In Process | Fog, Rain | Brian Bohanan | derrick operator - craig cordice, deckhands - quantus brown and J. lewis - all on derrick in break room | 0606 | Derrick 66 | Derrick 66 being pushed by Tug Bayou Dawn. Derrick was boomed up | N/A | PFD - Personal Flotation Device | JSA - Job Safety Analysis | The Sandusky Bay (outboard motor survey boat) was dispatched to secure area and warn mariners of hazards and to stay clear of the area until USCG arrived and assumed duties and took control of situation.
79 | Dredge 54 Boom Hoist - Philadelphia | Steve W Lawrence | Mechanical | Mechanical Dredging | 015607 | PHILADELPHIA NAVAL RESERVE BASIN MAINT. | NONE | 0 |  | 09/23/2016 | In Progress | 1487 |  | Steve W Lawrence | Mark L. Reid, Christopher Gunsten, Jason Campbell | 09/21/2016 | 1130 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  | Captain, 1 operator (19 yrs), 1 Mate (18 yrs), 1 Deckhand (10+ yrs), 1 WE (22 yrs), 1 Painter (25+ yrs), 1 Welder (10+ yrs) | 0134 | GL 54 | Dredge 54 spudded down inside Philadelphia Navy Basin, facing south. Scow 601 tied to the stbd side of dredge, also facing south. Tug Gulf Dawn made up in push gear to Scow 601. | Bucket #484 - 12 yd. Removed teeth/bases. | Stop Work | Mechanical - PM Plan, Mechanical - SOP
81 | Padre Island dredge pump cleanout door failure | Paul C Lamourie | Mechanical | Hopper Dredging | 015516 | BARNEGAT INLET; LONG BEACH ISLAND; NJ | NONE | 0 |  | 10/06/2016 | Complete | 438 | James M Walker | Paul C Lamourie | James C Gillespie | 07/01/2016 | 2400 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  |  | 0143 | Padre Island | Padre Island Stbd pump room | Dredge engaged in the dredging process at time of incident | Company Policy, Regulations, Mechanical - SOP | Mechanical - Material Specs
83 | FL MP Thrust Bearing Failure | Eugene Corey | Mechanical | Hydraulic Dredging | 084379 | SHELL ISLAND WEST NRDA RESTORATION PROJ. | NONE | 0 |  | 10/21/2016 | Complete | 84379 | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen | 09/29/2016 | 1500 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | [5 empty] | Dredge Pump and thrust bearing in normal configuration. | Pump and thrust configured for normal dredging operations |  | Mechanical - QA/QC, Other
95 | MCIA_012_2016_CSD Ohio Broken STBD Pump Shell | Rey Mart Taneo | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 58233 | 0 |  | 11/19/2016 | Complete | 22582 | James P Arias | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 11/06/2016 | 2230 | Dredge | Other | No | Dredge | Project - Dredge | In Process | Dark | Barry Ashton | Leverman in dredge ohio for 4-5 years | 0103 | Ohio | Dredge Pump #2 (Vel - 16.0 ft/s, Density - 1.11, Pump RPM - 344, Discharge - 250psi) | Megatteaux pump shell | SALT - Save A Life Today Rule, Life Saving Absolutes | Mechanical - QA/QC, Mechanical - Material Specs | Leverman immediately put dredge in emergency idle.
99 | Derrick 65 - Bent Boom Chord and Lacing | Stuart Hilgendorf | Mechanical | Hydraulic Dredging | 084379 | SHELL ISLAND WEST NRDA RESTORATION PROJ. | NONE | 0 |  | 12/08/2016 | Complete | 6212 | David Rappe | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 10/07/2016 | 1130 | Derrick | Mechanical Breakdown | No | Derrick | Mob/Demob | In Process | Sunny | LV Breithaupt | Derrick operator in crane, Mate & boat operator as riggers | 0605 | Derrick 65 | The Derrick was tied up alongside the Megga Yard Dock. | N/A | SALT - Save A Life Today Rule, Life Saving Absolutes | JSA - Job Safety Analysis | Barriers that worked was to keep clear of suspended loads. Barriers that failed 1) JSA did not identify potential risk in using the pin holes to make lift 2) Ensure load is secure prior to lift 3) access weight, size & lifting characteristics
100 | MB1706 Derrick - Lifting Cube | Rodney Fromenthal Jr. | Mechanical | Hopper Dredging | 072527 | DUVAL COUNTY SHORE PROTECTTION 2016 | NONE | 0 |  | 12/11/2016 | Ready for Edits | 1623 |  | Rodney Fromenthal Jr. | Mark L. Reid | 12/10/2016 | 1430 | Derrick | Trip, Slip, Fall | Yes | Derrick | Mob/Demob | In Process | Cloudy | Lupe Benavides | Crane Operator (certified) - operating the crane Deck Captain - Port Side Forward Mate - Along side the Deck Captain Riggers (certified) - Port Bow | 0706 | Misc. Equip | Derrick Barge - MB 1706 Deck Mounted Crawler Crane - American 165 Ton - Mobro 9299 Tug Boat - Free State Cube with attached hoses | Rigging: 4 way chains 3/4" X 40' (good for 91,400 lbs.) 1 1/4" safety shackles (12 Tons each X 4) | PPE - Personal Protection Equipment, Life Saving Absolutes, Safety Rules | JSA - Job Safety Analysis, PTP - Pre-Task Planning
105 | MCIA_003_2016_Lake Michigan Grounding | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | NONE | 0 |  | 01/04/2017 | Complete | 1383 |  | Sheldon Brooks | Sam R Morrison, Ed Tiearney | 05/14/2016 | 1330 | Tug | Vessel Accident -allision / collision, grounding | No | Tug | Project - Dredge | In Process | Sunny | Ivan Urrutia | Captain was in wheel house (14 Year experience ); One Deckhand on the forward bow (8-year experience) and another Deckhand on Stern deck (3 years experience); Chief Engineer in the engine room (14 Years of experience). | 0300 | Lake Michigan | See attached | See attached | PTP - Pre-Task Planning, Step Back for Safety, Stop Work | JSA - Job Safety Analysis | 1- Upon the initial grounding, the Captain quickly manoeuvred the vessel away from the shallow area to avoid incurring further damage to the hull. 2- Quick repose in identifying the damage, take immediate action to transfer the fuel from tank # 8 to tank 1 and 3.
108 | DR 55 - Load Drop | Andrew Larkin | Mechanical | Mechanical Dredging | 000000 | Off Project | NONE | 0 |  | 01/14/2017 | Complete | 12345 |  | Andrew Larkin | Bill Baumann, Christopher Gunsten | 01/13/2017 | 1130 | Dredge | Mechanical Breakdown | No | Dredge | Layup/Shipyard | In Process | Cloudy |  | Operator #1 - Entering Cab of crane - 20 yrs expereince Operator #2 - Port Spud Room, 10 yrs experience Chief Engineer - Barge in front of crane, 3 yrs on DR 55 Watch Engineer - Engine Room - 18 yrs experience Mate - Port Spud room - 4 yrs expereince Deckhand - Port Spud Room - 12 yrs experience | 0132 | GL 55 | DR 55, Collana's Crane Barge, Deck barge arranged in attached documetn | Weight test bags (water filled) | SALT Recommended Practice, Company Policy | JSA - Job Safety Analysis, PTP - Pre-Task Planning, Stop Work
110 | Dredge 54 Boom Dropped | Rene V Fernandez | Mechanical | Mechanical Dredging | 015591 | BALTIMORE HARBOR & CHANNELS - MAINT.DRG | NONE | 0 |  | 01/27/2017 | Complete | 1333 | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 06/07/2016 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | David Burlew | Operator in cab running machine. Watch engineer inside crane's "whirly" engine room completing daily morning watch round. | 0134 | GL 54 | Dredge 54 loading scow GL65 on the STBD side digging outbound in the green side of the channel. As recorded in the dredge's electronic data file (D060716.drg) the operator dug the last bucket of his 50 degree set on the port side of the cut. | GL 515 50cy cable arm bucket weighing 37,400lbs. Last material sample gather was 72lbs/cubic ft. The average payload per bucket from midnight until the time of the incident was 28.4 cubic yards. Material composition was 100% mud/silt. | SALT - Save A Life Today Rule, PTP - Pre-Task Planning, Company Policy, Life Saving Absolutes, Step Back for Safety | Mechanical - PM Plan, Mechanical - QA/QC | Engineer immediately shut off motor generator set. Equipment all stop and Post incident stand-down prior to further action. USCG & Pilots Advisory Position Warning. Post Incident Drug Test.
112 | MCIA_015_2016_UWP Knife Brook_CSD Carolina_161201 | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN |  | 0 |  | 02/04/2017 | Complete | 22582 |  | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 12/01/2016 | 1600 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Javier diaz | Leverman operating - 2 years and 7 Months of experience. Watch engineer in the Engine control room - 11 years of experience. Assistant Watch Engineer in the engine room - 8 years and 8 months of experience. | 0110 | Carolina | See attachment | See attachment | Step Back for Safety, Stop Work | PTP - Pre-Task Planning | When an engine room crew saw a severe vibration in pump number 2, they immediately called the leverman to shut the dredge down.
114 | Booster Jack stern spud failure / drop | Bill Baumann | Mechanical | Hydraulic Dredging | 015664 | CAPE MAY INLET; NJ |  | 0 |  | 02/13/2017 | Complete | 15664 |  | Mark V Outten | David J Johanson | 01/15/2017 | 1230 | Booster | Mechanical Breakdown | No | Booster | Mob/Demob | In Process | Cloudy | Hosiah Thompson |  | 0211 | Jack | Booster was on location in the ocean 37' water depth. stern connection was hooked up (1 float hose and two sink hoses. Port spud had 10 gearboxes, stbd and stern spud had 11 each. full compliment is 12. | None involved | Company Policy | JSA - Job Safety Analysis, Mechanical - SOP, Mechanical - QA/QC, Mechanical - Material Specs
116 | Dredge Illinois Stbd Main Engine Turbo Failure | Terry Wright | Mechanical | Hydraulic Dredging | 015664 | CAPE MAY INLET; NJ | 16292 | 0 |  | 02/13/2017 | Complete | 15664 |  | Terry Wright | David J Johanson | 02/04/2017 | 0230 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Dark |  | engine room accomplishing normal activities | 0105 | Illinois | NA | NA | Mechanical - SOP | Mechanical - PM Plan
117 | MCIA_001_2017_Stern Swivel Vertical Inlet Broke | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 59158 | 0 |  | 02/18/2017 | Complete | 1383 |  | Robert pierce | Bill Baumann, Sam R Morrison, Chris C Harris, Ed Tiearney | 01/22/2017 | 0400 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | Barry Ashton | 1. Jack Brew -Lever-man in Lever room, experience 2 year and 1 months with GLDD 2. Johnston Joy Verazon - Deck Mate-on dept.,Experience 8 year and 2 months with GLDD. | 0103 | Ohio | CSD Ohio was dredging at the cut # CC7-8 Ohio Cut 4 Central Channel. Also see the attached equipment damage report with Pictures | See the attached strip charts CSD Ohio was dredging at the cut # CC7-8 Ohio Cut 4 Central Channel. | PTP - Pre-Task Planning, Company Policy, Life Saving Absolutes, Stop Work | JSA - Job Safety Analysis, Safety Rules | There were instructions that no one should be around the stern area during the dredging operations, which avoided a serious injury and/or a fatality during the occurrence.
120 | Equipment Damage - Boat Operator | James P Arias | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | NONE | 0 |  | 02/12/2017 | Complete | 22582 | Joseph Sadiq | Sheldon Brooks | Sam R Morrison, Chris C Harris, Ed Tiearney | 02/12/2017 | 1100 | Crewboat/Survey Boat | Vessel Accident -allision / collision, grounding | No | Crewboat/Survey Boat | Project - Dredge | In Process | Cloudy |  | Dave Ryan Siguenza Experiences: Crew/Survey Boat Operator for Al Naseem Project at 2 months, 2 yrs. Boat Operator for other company & 7 yrs. GLDD Boat Operator in the past. |  |  | Attached Document | N/A | JSA - Job Safety Analysis, Company Policy, Regulations, Safety Rules, Step Back for Safety | PTP - Pre-Task Planning, Stop Work
122 | Crane 63 Boom Damage | Brian C Puckett | Mechanical | Hydraulic Dredging | 084379 | SHELL ISLAND WEST NRDA RESTORATION PROJ. | NONE | 0 |  | 02/21/2017 | Complete | 6212 | David J Johanson | Terry Wright | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 02/14/2017 | 1030 | Derrick | Mechanical Breakdown | Yes | Derrick | Mob/Demob | In Process | Sunny | Charles Kelly | Charles Kelly was on shore with Robert Pullins rigging the tank and David Snead was in the crane. | 0463 | G.L. 63 | Derrick was 10' off shore, eastern end of Shell East. Pontoon tank was 10' shore side. Approximately 30' from center pin. | See attached drawing. | PPE - Personal Protection Equipment | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, Company Policy, Life Saving Absolutes | No individuals were in the line of fire which had there been this equipment damage could have been an injury at minimum and fatality at worse.
123 | Subline tow - lost raft incident | Dave Allen | Mechanical | Hydraulic Dredging | 072446 | TAMPA HARBOR MAINTENANCE DREDGING | NONE | 0 |  | 02/21/2017 | Complete | 72445 | David J Johanson | Dave Allen | David Rappe, David J Johanson, James C Gillespie | 02/13/2017 | 0030 | Pipe Raft | Mechanical Breakdown | No | Pipe Raft | Mob/Demob | In Process | Dark |  |  | 9034 | Lady Theo | see attached pdf. | see attached pdf. | Company Policy, Mechanical - SOP | Mechanical - Material Specs
124 | Columbia River Multi Beam Head Damage | Eugene Corey | Mechanical | Hydraulic Dredging | 015681 | WILMINGTON; DE | NONE | 0 |  | 02/25/2017 | Complete | ABC123 |  | Eugene Corey | Washington Bryan, Chris Roberts, David Rappe, Mark L. Reid, Dave Allen | 02/06/2017 | 0230 | Crewboat/Survey Boat | Vessel Accident -allision / collision, grounding | No | Dredge | Project - Dredge | In Process | Dark |  | Captain Raeford Mills Jr - Columbia River Captain Mike Sanzon - Gulf Dawn | 0378 | Columbia River | The Gulf Dawn was nosed up to the strbd bow of the TX. He was being used to assist in swinging into the dock face. The Columbia river was tied up alongside the North Star Tug which was tied up around midship strbd side of the dredge TX | Tug Boat and Crew/Survey Boat | Other | PTP - Pre-Task Planning, Safety Rules
125 | Dredge New York Boom Assist Mid Platform | Jaclyn Abrams | Mechanical | Mechanical Dredging | 015578 | DELAWARE RIVER ROCK REACH B | NONE | 0 |  | 02/23/2017 | Complete | 3299 |  | Jaclyn Abrams | Andrew Larkin, Christopher Gunsten | 02/23/2017 | 0900 | Dredge | Struck by | Yes | Dredge | Project - Dredge | In Transition | Fog |  | Night shift is listed first, day shift is listed second on list below. Experience is time on dredge. During incident, day shift was on. The operator was in operators cab, the deckhand was on deck, the mate was in the observation house at the a-frame controls. | 0120 | New York | Dredge New York/ Boom Assist Wire/ Mid Platform: the damage occurred to the mid platform since the boom assist wire was under the mid platform due to the position of the flag sheave. When the operator engaged the boom assist system, the wire came tight onto the platform causing the damage. When the operator went to swing the excavator around the wire popped off of the corner of the platform. | N/A | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, SALT Recommended Practice, PTP - Pre-Task Planning, PPE - Personal Protection Equipment, Safety Rules, Stop Work | Mechanical - SOP
128 | GL702 Headlog Repairs | Christopher Gunsten | Mechanical | Mechanical Dredging | 000000 | Off Project |  | 0 |  | 03/01/2017 | Complete | Plant #0472 |  | Christopher Gunsten | Steven W Becker, Bill Baumann | 02/13/2017 | 0900 | Yard | Other | No | Yard | Layup/Shipyard | In Process |  |  |  | 0472 | G.L. 702 | GL702 Scow | No tools | Other | Mechanical - SOP
132 | Buried Bulldozer | William E Mitchell | Mechanical | Hydraulic Dredging | 072561 | MOREHEAD CITY HARBOR& CUTOFF ANGLE MAINT | 16414 | 0 |  | 03/28/2017 | Complete | W912PM-17-C-0002 | Chris Ameika | William E Mitchell | Chris Ameika, David J Johanson, James C Gillespie, Dave Allen | 03/28/2017 | 1430 | Fill Site | Other | Yes | Fill Site | Project - Land/Disposal Area | In Process | Cloudy | James Ganus | Dozer #1 Op: Pushing material in front of Berm Discharge ~30-40' away from discharge pipe. Dozer #2 Op: Grading operations ~300' from Discharge Loader Op: Lay Down Area ~500' from Discharge Shoreman #1 and #2: Supply Shack ~300' from discharge Fill Foreman: Stage Area ~5,000' from Discharge | 0706 | Misc. Equip | Dozer #1: Pushing material in front of Berm Discharge ~30-40' away from discharge pipe Dozer #2: Grading operations ~300' from Discharge Loader: Lay Down Area ~500' from Discharge | Wye-Valve located ~700' from discharge. | PPE - Personal Protection Equipment | JSA - Job Safety Analysis | Operator of sunken Dozer was able to free himself quickly. Dredge able to shutdown in sufficient time. Dozer #2 was able to construct a relief trench to release water buildup around sunken dozer. Axiom treatment initiated.
133 | DR 55 Tagline Motor | Andrew Larkin | Mechanical | Mechanical Dredging | 015654 | BALTIMORE HARBOR &CHANNELS - MAINT DRG. | 25529 | 0 |  | 03/30/2017 | Complete | 15654 | Brian Goetchius | Andrew Larkin | Bill Baumann, Christopher Gunsten | 03/29/2017 | 1200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Phil Sanzone |  | 0132 | GL 55 | DR 55 with GL 65 alongisde the stbd side. | N/A | Company Policy | Mechanical - SOP, Mechanical - QA/QC | Crew Limited damage by responding quickly to put out the fire due to training they have received in fire response.
136 | DR 55 - Gusset Crack | Andrew Larkin | Mechanical | Mechanical Dredging | 015654 | BALTIMORE HARBOR &CHANNELS - MAINT DRG. | 25532 | 0 |  | 04/07/2017 | Complete | 15654 | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 03/30/2017 | 1800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Prep | Rain | Phil Sanzone | Crew was standing by as an inspection of the previous complete tagline motor replacement took place. | 0132 | GL 55 | Dredge 55 with the GL 65 alongside the stbd side.. | Dredge 55 gantry support structure. | Step Back for Safety, Mechanical - QA/QC | Mechanical - SOP | Repairs were completed prior to operating the dredge.
137 | Unloader # 2 - CAT 398 Gasket | Andrew Larkin | Mechanical | Mechanical Dredging | 015654 | BALTIMORE HARBOR &CHANNELS - MAINT DRG. | NONE | 0 |  | 04/07/2017 | Complete | 15654 | Andrew Larkin | Kurt Hill | Bill Baumann, Christopher Gunsten | 04/06/2017 | 0030 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  | Engineer was in the engine room, operator was in the cab while the mate and deckhand were landing the GL702. | 0202 | Unloader No. 2 | Unloader #2 @ Poplar Island | N/A | Other | Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC | Response of the maintenance manager to line up CAT mechanics quickly.
138 | MCIA_003_2017_CSD Ohio_Cutter Motor # 2 Failure | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 59835 | 0 |  | 03/20/2017 | Complete | 22582 | James P Arias | Jacques Coetzee | Sam R Morrison, Ed Tiearney | 03/11/2017 | 2100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | John Graham | Lever-man of Dredge Ohio @ 2 years experience; 6 years experience other company. | 0103 | Ohio | Digging at EC2 - OH - CUT3 - Al Naseem Dreding Area (Eastern Channel) | Cutter Motor was inside of Caniter on the ladder - see attachment | PTP - Pre-Task Planning, Step Back for Safety, Stop Work | Mechanical - QA/QC | Removed the motor and send it to the vendor.
139 | MCIA_004_2017_Ohio_Cutter Motor # 6_Failure | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 59842 | 0 |  | 03/20/2017 | Complete | 22582 | James P Arias | Jacques Coetzee | Sam R Morrison, Ed Tiearney | 03/13/2017 | 0300 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | John Graham | Leverman of Dredge Ohio @ 2 years experience; 6 years experience other company. | 0103 | Ohio | Digging at EC2 - OH - CUT3 - Al Naseem Dreding Area (Eastern Channel) | Cutter motor was inside the Canister | Stop Work | Mechanical - QA/QC | Removed the motor and send it to the vendor.
140 | CA Bucket 517 Puncturing a Hole in Scow Hull GL64 | Rene V Fernandez | Mechanical | Mechanical Dredging | 015661 | UPPER CHESAPEAKE BAY MAINT.DREDGING 2017 | NONE | 0 |  | 03/27/2017 | Complete | 0 | Andrew Larkin | Rene V Fernandez | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 03/20/2017 | 2200 | Hopper Barge | Other | No | Dredge | Project - Dredge | In Process | Dark, Fog, Rain | Phil Sanzone | Dredge in active dredging operations. Operator engage in dredge cabin. | 0464 | G.L. 64 | Dredge 55 active dredging in Upper Chesapeake. Digging to 36ft loading the GL64 to 18.5ft Draft. | GL517 Cable Arm Bucket: Open Bucket Stops. Puncture caused by GL517 (last two files). GL515 (first file) and GL516 have caused damage in the past. | PTP - Pre-Task Planning | Mechanical - SOP
146 | Port Breast Winch Shaft Failure | Eugene Corey | Mechanical | Hydraulic Dredging | 015656 | TOWNSENDS & HEREFORD INLETS | NONE | 0 |  | 04/20/2017 | Complete | 337 | Bill Baumann | Eugene Corey | Mark V Outten, Andrew Gillie, David Rappe, Bill Baumann, Mark L. Reid, David J Johanson, Dave Allen | 03/29/2017 | 2200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | Robbie Baker | Normal Dredging operations in the BA | 0118 | Texas | Dredge Texas | Spud Winches | Other | Mechanical - Material Specs
149 | Radial Bearing Failure on Pump Shaft | Chris Faught | Mechanical | Rivers & Lakes Dredging | RR1244 | CHARLOTTE COUNTY EROSION CONTROL | NONE | 0 |  | 04/20/2017 | Complete | R1244 | Christopher Charron | Chris Faught | Steven Lane | 04/13/2017 | 0230 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | R016 | COMMODORE | dredge had just had the heat exchanger installed, and had only been running an hour or so when the radial bearing started running hot | pump shaft is seated onto the pump stand and is secured with fasteners from the two radial bearings and the thrust bearing | JSA - Job Safety Analysis, Mechanical - PM Plan | Mechanical - SOP
151 | R1244 Hydraulic Pump Failure | Chris Faught | Mechanical | Rivers & Lakes Dredging | RR1244 | CHARLOTTE COUNTY EROSION CONTROL | NONE | 0 |  | 04/22/2017 | Complete | 2069 | Christopher Charron | Chris Faught | Russell F. Zimmerman, Steven Lane | 04/19/2017 | 1230 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  | David Balch |  | R016 | COMMODORE | N/A | N/A | Step Back for Safety, Other | Mechanical - Material Specs
153 | Main Engine Failure | Garren Clegg | Mechanical | Rivers & Lakes Dredging | RR1244 | CHARLOTTE COUNTY EROSION CONTROL | NONE | 0 |  | 04/28/2017 | Complete | R1244 | Christopher Charron | Chris Faught |  | 04/27/2017 | 0300 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Cloudy |  | Engineer in the engine room Leverman in the lever room | R016 | COMMODORE | Dredge Commodore | Main Engine | PPE - Personal Protection Equipment | Other | Proper PPE in place during mechanical failure of engine. Engineer was wearing hard hat, glasses, gloves, safety toed boots.
154 | Unloader - Slurry Engine Fire | Andrew Larkin | Mechanical | Mechanical Dredging | 015654 | BALTIMORE HARBOR &CHANNELS - MAINT DRG. | NONE | 0 |  | 05/04/2017 | Complete | 15654 | Rene V Fernandez | Andrew Larkin | Bill Baumann, Christopher Gunsten | 05/02/2017 | 1630 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Cloudy, High Winds | Chris Thorp |  | 0202 | Unloader No. 2 | Slurry pump engine |  | Company Policy | Mechanical - PM Plan | The crew quickly responded as per the vessel's station bill. This quick response was aided by the crew completing a fire drill previously that day. This response to the fire prevented any major damage.
155 | Unloader #2 - Electrical Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015654 | BALTIMORE HARBOR &CHANNELS - MAINT DRG. | NONE | 0 |  | 05/09/2017 | Complete | 15654 | Kurt Hill | Kurt Hill | Bill Baumann, Christopher Gunsten | 05/04/2017 | 1200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Chris Thorp |  | 0202 | Unloader No. 2 | DR 54 & 55 loading scows for the Unloader to pump into Cox Creek disposal area. |  | Other | Mechanical - PM Plan, Mechanical - QA/QC
158 | Cutter Gear Box / Cutter Motor Noise | Terry Wright | Mechanical | Hydraulic Dredging | 072561 | MOREHEAD CITY HARBOR& CUTOFF ANGLE MAINT | NONE | 0 |  | 05/23/2017 | Complete | 72561 | Bill Baumann | Terry Wright | David J Johanson | 04/19/2017 | 1500 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0105 | Illinois |  |  | Other | Mechanical - PM Plan
161 | Liberty Island port main engine | Armand F Riehl | Mechanical | Hopper Dredging | 072506 | DARE COUNTY BEACH RENOURISHMENT | 67240 | 0 |  | 06/02/2017 | Complete | 154521 | Roger Nichols | Mike Kraljevic | Steven W Becker, Russell F. Zimmerman, Paul C Lamourie, James C Gillespie | 05/31/2017 | 1600 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Howard Hawrey | Dredging operations ongoing at borrow area and pump out. At the shipyard the engine was found to be 0.050th. | 0147 | Liberty Island | Port main engine | Propulsion and main pump gear box and shaft. | Step Back for Safety, Stop Work, Mechanical - QA/QC | Mechanical - Material Specs
162 | MCIA_006_2017_CSD Ohio_ Cutter motor # 4 | Joseph Sadiq | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 60182 | 0 |  | 06/04/2017 | Complete | 22582 | Rey Mart Taneo | Jacques Coetzee | Manny Vianzon, Garrett Gibson, Ed Tiearney | 05/15/2017 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Barry Ashton | Leaver-man on the lever-room and some crew member on the ladder near the canister and other crew member were in the engine room. | 0103 | Ohio | Port side Cutter Motor # 4, On CSD Ohio canister and dredge located at PC OH_Cut 01 Digging area in Al Naseem project, Saudi Arabia. | Dredge was anchored at PC OH_CUT 01 (Palace Channel) | Stop Work | Mechanical - QA/QC | Engine room crew removed the heater wire inside the cutter motor # 4, that was the potentially cause for the unstable operation of cutter motor.
167 | MCIA_007_2017_CSD Ohio_ Broken U.W.Pump Impeller | James P Arias | Mechanical | Int'l - Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 60483 | 0 |  | 06/05/2017 | Complete | 22582 | Joseph Sadiq | Sheldon Brooks | Manny Vianzon, Garrett Gibson, Ed Tiearney | 06/02/2017 | 1530 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | High Winds | John Graham | Leverman of Dredge Ohio @ 15 years experience, Leverman in other company for 28 years experience | 0103 | Ohio | Leaver-man on the lever-room operating and deck crew were working on decks and other supporting plants | CSD Ohio Under water pump impeller | Stop Work | Other | The leverman shut down the pumps and raised the ladder for a pump inspection
171 | CRAB 3 Wheel Damage | Washington Bryan | Mechanical | Hopper Dredging | 072506 | DARE COUNTY BEACH RENOURISHMENT | NONE | 0 |  | 06/20/2017 | Complete | 72506 | Matthew O'Neill | Washington Bryan | Chris Roberts | 06/16/2017 | 1000 | Fill Site | Mechanical Breakdown | Yes | Fill Site | Survey | In Process | Sunny | Matthew O'Neill | CRAB Operator - On CRAB3 CRAB Attendant - Watching CRAB Operations | 0772 | Crab-3 | Plant 772 - Wheel stud holes in rims were wallowed out due to the nuts backing off and being too loose. Wheel studs uses were too long and nut did not have nylock to keep it in place. | No tools were involved. Claims of improper torque were not correct. New nuts did not have loctyte or nylock on them and backed off of the bolts. | Stop Work | Other
173 | DR 55 Oil Cooler | Andrew Larkin | Mechanical | Mechanical Dredging | 072553 | MATOC TASK ORDER - US NAVAL ST. MAYPORT | 26388 | 0 |  | 06/19/2017 | Complete | 72553 | Bill Baumann | Bill Baumann | Bill Baumann, Christopher Gunsten | 06/19/2017 | 0030 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | Alex Morris |  | 0132 | GL 55 | DR 55 - EMD12-645-E8 | Oil Cooler | Mechanical - SOP | Mechanical - Material Specs
178 | Memphis rental tow delay. | Robert Kelly | Mechanical | Rivers & Lakes Dredging | RR1229 | MISS RVR & HARBOR; KY; MO; AR; TN | NONE | 0 |  | 06/30/2017 | Complete | 3438 | Christopher Charron | Chris Faught | Chris Faught, Stan Ekren, Nathaniel C Woods, Steven Lane | 06/28/2017 | 0030 | Pipe Raft | Other | No | Pontoon Tank/Pipeline | Mob/Demob | Prep | Sunny | James Woodell | Southern Towing 2 tug Captains. GLDD Deck Captain. GLDD 2 Mates riding the tow. | 0706 | Misc. Equip | M/V Sam Yount, 3 anchor barges, pipe raft, deck barge, Jody Davenport, Coyote State | 7/8" Cables and steamboat rachets | Step Back for Safety | Mechanical - Material Specs
180 | GL65 - Gasket Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072553 | MATOC TASK ORDER - US NAVAL ST. MAYPORT | NONE | 0 |  | 07/06/2017 | Complete | 72553 | Troy Booth | Troy Booth | Bill Baumann, Christopher Gunsten | 07/02/2017 | 0330 | Attendant Plant - Other | Mechanical Breakdown | No | Attendant Plant - Other | Project - Attn.Plant | In Process | Sunny | Kevin Holt | Dredge Mate #1 & Dredge Mate #2, Dredge Engineer were on the deck of the dredge. The tending boat DH was on the deck of the scow. | 0465 | G.L. 65 | Scow GL - 65 alongside DR 55 port side. | None | Safety Rules, Other | Mechanical - PM Plan, Mechanical - QA/QC, Mechanical - Material Specs | The dredge crew was on deck preparing to sail the GL-65 scow. This allowed them to release the lines of the scow quickly preventing the incident from getting worse.
182 | Liberty Island submerged pipeline sand plug | Armand F Riehl | Mechanical | Hopper Dredging | 072506 | DARE COUNTY BEACH RENOURISHMENT | 67362 | 0 |  | 07/08/2017 | Complete | 154521 | Gail Johnson | Matt Ferrell | Russell F. Zimmerman, Paul C Lamourie | 07/01/2017 | 1530 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Howard Hawrey | Dredge pumping through total pipe length of 5,738 feet. See attached pump plot #177 | 0147 | Liberty Island | Dredge pumping through cube, 3,480' of submerged pipeline and 1,900' of shore pipe. | Both dredge main pumps, jet water pumps and collection gates. | Stop Work | Other
183 | GL 65 - Pennant Line Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072553 | MATOC TASK ORDER - US NAVAL ST. MAYPORT | NONE | 0 |  | 07/12/2017 | Complete | Mayport | Troy Booth | Andrew Larkin | Christopher Gunsten | 07/05/2017 | 2200 | Tug | Mechanical Breakdown | No | Tug | Project - Attn.Plant | In Process | Sunny |  | Steve Pippen was in teh wheel house of the tug Indian Dawn towing the GL 65 | 0132 | GL 55 | Rental Tug Indian Dawn towing LG65 scow loaded to the disposal area. | Indian Dawn and GL 65 | Other | Mechanical - PM Plan | The crew of the Indian Dawn acted quickly to save the scow from running aground on the jetty.
189 | Myrtle Beach 'Sink' Hose Failure | Chris Pomfret | Mechanical | Hopper Dredging | 072571 | MYRTLE BEACH REACH 1& 3 -BCH.RENOUR.2017 | NONE | 0 |  | 08/01/2017 | Complete | 72571 | James M Walker | Ed ODowd | James M Walker, David Rappe, Paul C Lamourie, Dave Allen | 07/27/2017 | 1500 | Pontoon Tank/Pipeline | Mechanical Breakdown | No | Pontoon Tank/Pipeline | Project - Pipeline | In Process | High Winds | Ed ODowd |  | 0565 | G.L. 111 | Cube 716 and 2 sink hoses. Booster Reggie and 1 sink hose. | Anchor Barge | Other | Mechanical - SOP, Mechanical - QA/QC
190 | Alaska Swing Drive Issue | Tim Riehl | Mechanical | Hydraulic Dredging | 084414 | NRDA Caillou Lake Headlands; LA | NONE | 0 |  | 08/02/2017 | Complete | 84414 | David J Johanson | Tim Riehl | David J Johanson | 08/01/2017 | 1500 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  |  | 0101 | Alaska | Dredge was preforming dredging operation | N/A | Mechanical - QA/QC, Other | Mechanical - PM Plan
191 | IL Swing Drive | Tim J Kremer | Mechanical | Hydraulic Dredging | 015675 | PHILA TO THE SEA MAINTENANCE DREDGING | 17327 | 0 |  | 08/18/2017 | Complete | 15675 | Cameron R Whitmore | Tim J Kremer | David Rappe, Bill Baumann, David J Johanson | 08/17/2017 | 2330 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | Richard Alexander |  | 0105 | Illinois | Dredge IL with idler barge GL 177 digging in the DE River. Dredge was positioned on the green side of the channel, facing down stream. | Swing winch, custom made DCR ARM amp isolator board | Other |  | There are several factors that prevented this from having a longer delay time. Chris Slimmer answering his phone while on vacation, the combination of Bill English and the Assistant Chief trouble shooting the system over the phone to locate the main issue, and the availability of Bill English to be able to get on a plane and head immediately to the dredge once the issue was identified.
194 | DR 55 Load Drop | Johan VanBladel | Mechanical | Mechanical Dredging | 015666 | BOSTON HARBOR CAD CELL | NONE | 0 |  | 09/04/2017 | Complete | 15666 | Andrew Larkin | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 09/04/2017 | 1530 | Dredge | Mechanical Breakdown | Yes | Dredge | Mob/Demob | Prep | Cloudy | Phil Sanzone | Dredge Captain in the operators chair in the crane Operator on the crane near the PLC cabinet Chief Engineer in the crane engine room Watch Engineer in the crane engine room | 0132 | GL 55 | Dredge 55 on the red side of the Inner Boston harbor in 42' of water with the BTT112 deckbarge on the portside. The 30 cy (#517) environmental bucket on the port side on the deck, with 4 dump truck tires on top and the service crane between 2 tires above the 30 cy bucket. The 18 cy (#510) bucket on the starboard side of the deck to be lifted over the environmental bucket and port spud onto the deck barge | Set of 2 way chains rated for 85,400 lbs hooked to the beckett on the holding wire of the main crane. Closer wire was attached to the holder. Tagline from the crane attached to the becket of the #510 bucket | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, Safety Rules | Mechanical - Material Specs
197 | DR 55 #2 Hoist Motor Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015666 | BOSTON HARBOR CAD CELL | 27046 | 0 |  | 09/08/2017 | Complete | 15666 | Brian Goetchius | Andrew Larkin | Bill Baumann, Christopher Gunsten | 09/08/2017 | 0830 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Prep | Rain | Alex Morris | N/A | 0132 | GL 55 | DR 55 | N/A | Other | Company Policy
200 | Booster Reggie Dropped | William Bradshaw | Mechanical | Hopper Dredging | 072571 | MYRTLE BEACH REACH 1& 3 -BCH.RENOUR.2017 | NONE | 0 |  | 09/05/2017 | Complete | 72571 | Sam R Morrison | William Bradshaw | James M Walker, Bill Baumann, David J Johanson | 09/05/2017 | 0700 | Booster | Mechanical Breakdown | No | Booster | Project - Attn.Plant | In Process | Sunny | Craig Daly |  | 0214 | Reggie | Booster on location | none |  | JSA - Job Safety Analysis, Mechanical - PM Plan, Mechanical - QA/QC
206 | MCIA - Dare county cube set up leak | Armand F Riehl | Mechanical | Hopper Dredging | 072506 | DARE COUNTY BEACH RENOURISHMENT | 67746 | 0 |  | 10/02/2017 | Complete | N/A | Dane Nelson | Armand F Riehl | Russell F. Zimmerman, Dave Allen | 10/02/2017 | 0700 | Attendant Plant - Other | Mechanical Breakdown | Yes | Attendant Plant - Other | Project - Pipeline | In Process | Sunny | Armand F Riehl | Dredge hooked up to the cube 711. four float, one flex hose to the cube. then through turning gland, 90 degree elbow, two sink hoses and a 120' steel riser. | 0147 | Liberty Island | The sea was out of the east putting the dredge facing into the sea. | Dredge hooked up to the cube 711. four float, one flex hose to the cube. then through turning gland, 90 degree elbow, two sink hoses and a 120' steel riser. | Company Policy, Mechanical - QA/QC | Mechanical - Material Specs
207 | Crane Damage Cracked Boom | Robert Kelly | Mechanical | Rivers & Lakes Dredging | RR1201 | DOUBLE CREEK MAINT. DREDGING 2017 | NONE | 0 |  | 10/16/2017 | Complete | 3173 | Christopher Charron | Kevin Holt | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 10/16/2017 | 1500 | Derrick | Mechanical Breakdown | No | Derrick | Project - Attn.Plant | In Process | Sunny | Charles Edwards | Austin Connell Joe Wilson Charles Edwards | 0706 | Misc. Equip | Barge mounted rental crane | Lifting chains Spud |  | Step Back for Safety, Stop Work | Crane was immediately taken out of service.
209 | DR 54 Main Generator Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015666 | BOSTON HARBOR CAD CELL | 32375 | 0 |  | 10/19/2017 | Complete | 15666 | Brian Goetchius | Andrew Larkin | Bill Baumann, Christopher Gunsten | 10/19/2017 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Cloudy | David Burlew |  | 0134 | GL 54 | None | None | Stop Work | Mechanical - PM Plan | None
211 | GL 65 Grounding | Michael Tester | Mechanical | Mechanical Dredging | 015719 | MANHATTAN CRUISE TERMINAL- MAINT.DREDG. | NONE | 0 |  | 10/29/2017 | Complete | 15719 | Andrew Larkin | Matt Jack | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 10/29/2017 | 0230 | Attendant Plant - Other | Vessel Accident -allision / collision, grounding | No | Attendant Plant - Other | Project - Dredge | Idle | Dark, High Winds | Thomas Lawrence | Crew was idle on the Dredge 51 | 0465 | G.L. 65 | Scow 65 was moored on the East side of the North mooring in Newark Bay. | Pictures of lines below | Mechanical - SOP | Company Policy
214 | 22582_MCIA_009_CSD Carolina Cutter Motor No. 4 | James P Arias | Mechanical | Hydraulic Dredging | 022582 | AL NASEEM CENTRAL & EASTERN CHNL DREDGIN | 14829 | 0 |  | 11/15/2017 | Complete | 22582 | Joseph Sadiq | Jacques Coetzee | Manny Vianzon, Garrett Gibson | 10/28/2017 | 2400 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Prep | Dark | Barry Ashton | Not Applicable | 0110 | Carolina | Vessel was located at Western Channel - Sand Mining Barrow Area CAR CUT 3 Al Naseem Dredging Area | Not Applicable | Mechanical - Material Specs | Mechanical - SOP | After shutdown for inspection, it was found that the Port cutter motor sustained severe burnt on the electrical components. The cutter motor was removed in the morning and was replaced with Cutter Motor #2.
217 | Unloader 2, CAT 399 Failure | Matt Ferrell | Mechanical | Mechanical Dredging | 015724 | UPPER CHESAPEAKE MAINTENANCE DREDGING | NONE | 0 |  | 12/05/2017 | Complete | W912BU-17-C-0041 | Andrew Larkin | Wade Eldridge | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 12/05/2017 | 1100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  | Wade Eldridge |  | 0202 | Unloader No. 2 | Main pump connected to rear engine that failed. Failed engine connected directly to second 399 | None | Mechanical - Material Specs
218 | Ohio River Engine Room Fire | Brian C Puckett | Mechanical | Hopper Dredging | 084569 | GULFPORT HARBOR BAR CHANNEL; MS | NONE | 0 |  | 11/17/2017 | Complete | W9127817 | Dave Allen | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/17/2017 | 1530 | Crewboat/Survey Boat | Mechanical Breakdown | No | Crewboat/Survey Boat | Project - Attn.Plant | In Process | Sunny |  |  | 0384 | Ohio River |  |  | Company Policy, Safety Rules | Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC | 1. The Site Engineers spoke up as soon as they noticed something was different 2. The operator shutting the engines down and having the fire extinguisher to put the fire out 3. The site engineers calling the tug McCormick Boys to come over 4. The crew on the McCormick Boys noticed that the there was a fire in the exhaust pipe.
221 | Dredge Liberty Automation Failure Incident | Adolfo Lopez | Mechanical | Hopper Dredging | 072445 | SAVANNAH HARBOR EXPANSION PROJECT (SHEP) | 68074 | 0 |  | 12/23/2017 | Complete | 72445 | Armand F Riehl | Armand F Riehl | Paul C Lamourie | 12/23/2017 | 1000 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Fog | Howard Hawrey | All crew at designated posts on ship. | 0147 | Liberty Island | Liberty Island's automation. | N/A | JSA - Job Safety Analysis, PPE - Personal Protection Equipment, Safety Rules, Mechanical - SOP | Mechanical - Material Specs
225 | Alaska Cutter Motor Failure 12/21/2017 | James C Towner | Mechanical | Hydraulic Dredging | 084414 | NRDA Caillou Lake Headlands; LA | NONE | 0 |  | 12/21/2017 | Complete | 84414 | James C Gillespie | Brian Markey | Steven W Becker, James C Gillespie | 12/21/2017 | 1600 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Idle | Cloudy | Lionell Caroon |  | 0101 | Alaska | Dredge was digging on the Whiskey Island Project | Port and stbd cutter motors were in operation | Other | Mechanical - Material Specs | Vigilant watchstanding. Watchstanders visually noticed the problem with the motors and notified the Captain and the Chief of the issue.
229 | STBD Cutter Motor Failure | Brian Markey | Mechanical | Hydraulic Dredging | 084414 | NRDA Caillou Lake Headlands; LA | NONE | 0 |  | 02/10/2018 | Complete | 84414 | Bill Baumann | Brian Markey | Steven W Becker, Bill Baumann, James C Gillespie | 02/10/2018 | 1230 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Brian Markey | Dredge was digging on the Whiskey Island project | 0101 | Alaska | Dredge was digging with 2 main engines running 1 main generator and 2 cutter motors running | 2 cutter motors | Other | Mechanical - Material Specs
233 | Noon Island_Generator Engine Overspeed_02252018 | Alvin Reyes | Mechanical | Int'l - Hopper Dredging | 000000 | Off Project | NONE | 0 |  | 02/25/2018 | Complete | 00026 | Joseph Sadiq | Jose Gracia | Manny Vianzon | 02/25/2018 | 1230 | Dredge | Other | Yes | Dredge | Layup/Shipyard | In Process | Cloudy | Maksim Shliapnikov | Chief Engineer and the engine crew with the assistance of electrical superintendent working in the engine center room at the generator # 1 - | 0150 | NOON ISLAND | No Operation - MV Noon Island currently in lay up status | No tools the generator # 1 Engine room crew warm up the engine. on Generator #1 unstable frequency they stopped for further troubleshooting. | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, SALT Recommended Practice, Stop Work | PTP - Pre-Task Planning, Mechanical - QA/QC | Employee managed to shut down immediately the fuel valve supply to prevent more damage of the engine.
235 | Broken Tail Shaft Coupling 2/1/2018 | James C Towner | Mechanical | Hydraulic Dredging | 084414 | NRDA Caillou Lake Headlands; LA | NONE | 0 |  | 02/01/2018 | Complete | 84414 | Bill Baumann | Lionell Caroon | Steven W Becker, Tim Riehl, Bill Baumann, James C Gillespie | 02/01/2018 | 1000 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  |  | 0101 | Alaska | The Dredge Alaska was digging offshore in the Borrow Area. During routine ladder inspection, the crack was found | Shaft was not in operation when the crack was found. | Mechanical - PM Plan | Mechanical - Material Specs | Due to routine ladder maintenance / inspections, the crack was caught early before a worse outcome.
238 | Cutter Gearbox Bearing Failure | Mark V Outten | Mechanical | Hydraulic Dredging | 015687 | BEACH HAVEN & HOLGATE BEACHES; NJ | NONE | 0 |  | 04/01/2018 | Complete | 1 | Bill Baumann | Mark V Outten | Steven W Becker, Bill Baumann | 04/01/2018 | N/A | Dredge | Mechanical Breakdown | No | Dredge | Layup/Shipyard | In Process |  |  |  | 0118 | Texas | Cutter Gearbox | Bearing Failure | Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC, Mechanical - Material Specs
240 | DR 53 - Reactor Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 084609 | FREEPORT LNG MAINT.DREDGING | NONE | 0 |  | 04/21/2018 | Complete | 84609 | Sherif Abdelgafar | Andrew Larkin | Chris Ameika, Bill Baumann, James C Gillespie, Steven R Auernhamer | 04/21/2018 | 1100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Wade Eldridge | Dredge crew was configured with 4 members of the crew and the Captain. | 0133 | GL 53 | Dredge 53 | DR 53 Holder AC/DC Drives | JSA - Job Safety Analysis | Mechanical - Material Specs | The reactor was able to be repaired by Global Tech was the main factor in decreasing the downtime.
242 | Padre Island Dredge Pump Coupling Failure | James M Walker | Mechanical | Hopper Dredging | 072601 | FORT PIERCE-BEACH RENOURISHMENT | 47763 | 0 |  | 04/30/2018 | Complete | 72601 |  | James M Walker | Paul C Lamourie | 04/30/2018 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0143 | Padre Island | Port Dredge Pump | Dredge Pump Coupling | Stop Work | Mechanical - SOP, Mechanical - QA/QC
243 | Dredge Carolina cutter gearbox failure May 2018 | Bill Baumann | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 10091 | 0 |  | 05/02/2018 | Complete | 72584 | Mike Hungerford | Bill Baumann | Steven W Becker, Russell F. Zimmerman, David J Johanson, James C Gillespie | 05/02/2018 | N/A | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0110 | Carolina |  |  | Mechanical - SOP | Mechanical - PM Plan
244 | 22711_180413_Ohio_DC Contactor | James P Arias | Mechanical | Int'l - Hydraulic Dredging | 022711 | Oceanus & GSC&E Trenching & Backfilling | NONE | 0 |  | 04/13/2018 | Complete | 22711 | Joseph Sadiq | Alexanders Andrezens | Manny Vianzon, Garrett Gibson | 04/13/2018 | 0230 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Transition |  | Sheldon Brooks |  | 0103 | Ohio | Dredge was digging on the BLNG project digging area. | Dredge was under operation. | Mechanical - Material Specs | Mechanical - SOP, Mechanical - QA/QC | the employee immediately grabbed the 5 lbs. dry powder portable fire extinguisher (2 steps-distances from the incident area) he open the panel door and extinguished the fire by using fire extinguisher. The Asst. watch engineer stayed in the area while the watch engineer informed the leverman about the incident, then proceeded to run the emergency generator.
246 | Dredge 53 Boom Hoist Gear Box Failure | Michael Jimenez | Mechanical | Mechanical Dredging | 084609 | FREEPORT LNG MAINT.DREDGING | NONE | 0 |  | 05/17/2018 | Complete | Freeport LNG 01 | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 05/17/2018 | 0100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Transition | Dark |  | Operator, Mate, Engineer, Deckhand | 0133 | GL 53 | Dredge 53 | None | Other | Stop Work, Mechanical - PM Plan, Mechanical - SOP | Video of incident provided evidence of the cause of the failure.
248 | DR 55 - Hoist Generator #2 Breakdown | Andrew Larkin | Mechanical | Mechanical Dredging | 084609 | FREEPORT LNG MAINT.DREDGING | 28263 | 0 |  | 06/01/2018 | Complete | 84609 | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 06/01/2018 | 0400 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Alex Morris | Standard Mech Dredge Crew - Operator, Mate, Enginer, Deckhand | 0132 | GL 55 | DR 55 | Dredging in FLNG Basin | Other | Mechanical - SOP | Troubleshooting by outside technician revealed a loose connection.
253 | GL-10 Port Side Pin Connection Failure | Mike Hungerford | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | NONE | 0 |  | 07/03/2018 | Complete | 72584 | William Bradshaw | Mike Hungerford | Steven W Becker, David J Johanson, James C Gillespie | 07/03/2018 | 2030 | Idler/Power Barge | Mechanical Breakdown | No | Idler/Power Barge | Project - Dredge | In Process | Dark, High Winds, Severe Storms | Robbie Baker | Dredge was in normal operation dredging within Acceptance Section 3 when pin failure occurred on Port connection | 0595 | G.L. 10 | Dredge Carolina & Idler Barge GL-10 | Pin connection of GL-10 came free from housing while in normal operation. | Stop Work | Mechanical - SOP, Mechanical - Material Specs
254 | 20180702 LI PME Turbo Catastrophic Failure | Jeremy Remme | Mechanical | Hopper Dredging | 084510 | MSCIP PHASE 1;BARRIER ISLAND;CAMILLE CUT | 68665 | 0 |  | 07/02/2018 | Complete | 84510 | James M Walker | James M Walker | Steven W Becker, Paul C Lamourie | 07/02/2018 | 1930 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Extreme Heat |  | Dredge was pumping out. | 0147 | Liberty Island | Port main engine turbo chargers. Right and Left Banks | Port main engine turbo chargers. Right and Left Banks | Other | Mechanical - PM Plan, Mechanical - Material Specs
258 | Texas Broken Port Spud Winch | James C Towner | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1745500 | 0 |  | 08/11/2018 | Complete | 72584 | David J Johanson | James C Towner | Russell F. Zimmerman, David J Johanson, James C Gillespie | 08/11/2018 | 1030 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  | Normal Dredge ops in Dig Area | 0118 | Texas | Dredge Texas | Port Spud Winch | Other | Mechanical - Material Specs
259 | Cavalier State Grounding | Matt Ferrell | Mechanical | Hopper Dredging | 072623 | MYRTLE BEACH RENOURISHMENT | NONE | 0 |  | 08/21/2018 | Ready for Edits | 2552 | Ed ODowd | Matt Ferrell | Chris Roberts | 08/13/2018 | 0300 | Tug | Vessel Accident -allision / collision, grounding | No | Tug | Project - Attn.Plant | In Process | Dark |  | Michael Rice capt. Tug Hardhead | 0340 | Cavalier State | Tug hardhead AB-107, AC Barge and Cavalier State | Tug hardhead AB-107, AC Barge and Cavalier State | PTP - Pre-Task Planning | Other
261 | Booster 9 Generators | James P Arias | Mechanical | Int'l - Hydraulic Dredging | 000000 | Off Project | NONE | 0 |  | 07/26/2018 | Complete | 26T | James P Arias | Jacques Coetzee | Manny Vianzon, Christopher Gunsten, Garrett Gibson | 07/26/2018 | N/A | Booster | Mechanical Breakdown | No | Booster | Layup/Shipyard | Idle | Sunny | Rodel Alagao | Not Applicable | 0219 | Booster #9 | Vessel is alongside to Buster (Booster 6) at ASRY shipyard inner anchorage. | Megger test device | Mechanical - SOP, Mechanical - QA/QC, Other | Company Policy, Mechanical - PM Plan | The both AC alternators were isolated to prevent more dust to contaminate the area. Both generators were subjected for general overhauling.
263 | DR 54 - Stbd Spud Gear Box Shaft Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015765 | Hydrohammer Rock With NY | 33710 | 0 |  | 09/19/2018 | Complete | 15765 | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 09/15/2018 | 1000 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  | Normal dredging operations. Captain, Chief Engineer, Operator, MAte, Deckhand & Engineer. | 0134 | GL 54 | DR 54 operating on the Delaware River | None | Other | Mechanical - PM Plan | Operations were stopped when the damage was discovered and sourcing of replacement parts started. The ability to find a replacement input shaft reduced the downtime dramatically.
270 | AB 118 Damage | Brian C Puckett | Mechanical | Hopper Dredging | 084510 | MSCIP PHASE 1;BARRIER ISLAND;CAMILLE CUT | NONE | 0 |  | 10/14/2018 | Complete | 84510 | Jeremy Remme | Brian C Puckett | David Rappe, Steven R Auernhamer, Dave Allen | 10/15/2018 | 0230 | Anchor Barge | Vessel Accident -allision / collision, grounding | No | Anchor Barge | Project - Attn.Plant | Clean Up |  |  |  | 0118 | Texas | See the attached PDF's for the AB and tug configuration | See the attached PDF's for the configuration | Other | JSA - Job Safety Analysis, PTP - Pre-Task Planning, Company Policy | Spoke to all of the tug boats about the proper way to secure two barges.
273 | Alaska anchor contact with hull | Tim J Kremer | Mechanical | Hydraulic Dredging | 072606 | TAMPA HARBR.-BIG BEND CHANL-NEW WORK DRG | 24568 | 0 |  | 11/27/2018 | Complete | 72606 | Mike Gerlach | Tim J Kremer | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie, Dave Allen | 11/27/2018 | 1400 | Dredge | Vessel Accident -allision / collision, grounding | Yes | Dredge | Project - Dredge | In Process | Sunny | Lionell Caroon | Leverman in Alaska leverroom Captain of the Evergreen State in wheelhouse Captain of the KJ in wheelhouse | 0101 | Alaska | See attached sketch of vessel configuration. See anchor and hanger cable picture | 1 1/4" hanger cable 1 1/4" shackle | Mechanical - PM Plan, Other |  | Bilge alarms working correctly identified the problem before too much water was taken on board or water rose to a level that damaged other equipment.
274 | Booster Jack Spud Foot / Hull/ and hose Damage | Mathew Bishop | Mechanical | Hydraulic Dredging | 015771 | FIRE ISLAND INLET; NY | NONE | 0 |  | 12/08/2018 | Complete | 15771 | Shawn Boynton | Mathew Bishop | David Rappe, James C Gillespie, Dave Allen | 12/08/2018 | 1000 | Booster | Caught in | No | Booster | Mob/Demob | In Transition | Cloudy, High Winds | Hosiah Thompson | One engineer port side watching the spud go down The other engineer on stnd side Chief engineer at the controls | 0211 | Jack | Jacking the spuds down it was notice the float hose was caught between the spud and the barge.Signal was given to raise spud to get the hose out. Couldn't see the flange which was caught under the barge on top of the foot | Hose assembly consisting of a Float hose, a sink hose, and a riser pipe attached to both the suction and discharge side of the booster while under tow. | Stop Work | JSA - Job Safety Analysis, PTP - Pre-Task Planning
278 | Dredge Carolina Suction Hose Failure | Mike Hungerford | Mechanical | Hydraulic Dredging | 072606 | TAMPA HARBR.-BIG BEND CHANL-NEW WORK DRG | 11215 | 0 |  | 12/19/2018 | Complete | 72606 | Tim J Kremer | Mike Hungerford | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie | 12/19/2018 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Gudalupe Benevides | Dredge was in normal operations during time of failure. | 0110 | Carolina | Dredge Carolina was in normal operations during time of failure | Dredge Carolina was in normal operations during time of failure | Mechanical - SOP | Mechanical - PM Plan
279 | DR 55 - Brake Band Actuator Foundation Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015765 | Hydrohammer Rock With NY | 28616 | 0 |  | 01/09/2019 | Complete | 15765 | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 01/01/2019 | 0100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  |  | 0132 | GL 55 | DR 55 dredging on the Delaware River. | None | Other | Mechanical - SOP | None
282 | DB 186 Hull/Deck Damage | Mike Gerlach | Mechanical | Hydraulic Dredging | 072606 | TAMPA HARBR.-BIG BEND CHANL-NEW WORK DRG | NONE | 0 |  | 12/21/2018 | Complete | 72606 | David J Johanson | Mike Gerlach | David Rappe, James C Gillespie, Dave Allen | 12/21/2018 | 1000 | Deck or Ramp Barge | Struck against | No | Deck or Ramp Barge | Project - Attn.Plant | In Process | Cloudy, High Winds, Rain, Severe Storms | Armando Rios | The dredge Alaska and Carolina were digging in the Big Bend channel. The deck barges were located in the nearby staging area. Both the bullgang and dredge deck crews were assigned to oversee the staging area operations. Bullgang crews were pulled from the project several times to assist with Egmont Mob/demob. | 0706 | Misc. Equip | The starboard side of the DB 186 was tied to the port side of the 172. No fendering between the barges. PDF of the layout attached |  |  | PTP - Pre-Task Planning
283 | Apache Tower Damage | Andrew Larkin | Mechanical | Mechanical Dredging | 015765 | Hydrohammer Rock With NY | NONE | 0 |  | 02/04/2019 | Complete | 15765 | Mark L. Reid | Andrew Larkin | Kyle Johnson, Bill Baumann, James C Gillespie | 02/04/2019 | 1830 | Drillboat | Other | No | Attendant Plant - Other | Mob/Demob | Prep | Dark | Chris Thorp | No crew on board at the time of the incident. | 0229 | Apache | The apache and the Derrick 68 were tied side to side as the Gulf Dawn started to tow them away from the yard with the tug Foxy 3 assisting. | Nonce | Other | Mechanical - SOP, Mechanical - QA/QC | Tower was recovered when the Apache was brought back to the SI yard. Damages to the tower were repaired and the tower was trucked to Philadelphia.
286 | DR 53 - Bucket Drop | Andrew Larkin | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 22224 | 0 |  | 02/21/2019 | Complete | 72957 | James C Gillespie | Andrew Larkin | Bill Baumann, James C Gillespie | 02/21/2019 | 1800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Wade Eldridge | Incident occurred during crew change from day-shift to night shift. Typical 4 man crew for both shifts (operator, engineer, mate, deckhand) | 0133 | GL 53 | normal operations in Jacksonville, FL | None | Other | Mechanical - PM Plan, Mechanical - SOP | Outlined in incident response
290 | DBM STBD M/E Foundation Failure | Jeremy Remme | Mechanical | Hopper Dredging | 072584 | Charleston Entrance Channel; Contract 2 | NONE | 0 |  | 03/04/2019 | Complete | 072584 | Giacomo Albanese | Mike Kraljevic | Steven W Becker, Paul C Lamourie | 03/04/2019 | 1330 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  | Mike Kraljevic |  | 0302 | Mackie | Dredge just finished dumping and began sailing back to the dig site. | N/A | Mechanical - SOP | Mechanical - QA/QC
291 | Dredge 53 Fire | Michael Jimenez | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 22254 | 0 |  | 03/08/2019 | Complete | 1 | Garren Clegg | Wade Eldridge | Bill Baumann, James C Gillespie, Christopher Charron, Jason Campbell | 03/08/2019 | 1430 | Dredge | Other | Yes | Dredge | Project - Dredge | In Process | Sunny |  | Welder was in the sheave room. The fire watch was going between sheave room and PPE room. | 0133 | GL 53 | sheave and PPE room. | burning torch was being used. | Company Policy | JSA - Job Safety Analysis, SALT - Save A Life Today Rule | JSA and SALT were reviewed but the JSA failed to highlight fire risk and all SALT rules were not followed.
293 | DR NY Main Engine PP1 Seal Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | NONE | 0 |  | 03/23/2019 | Complete | 72957 | Brian Goetchius | Andrew Larkin | Bill Baumann | 03/23/2019 | 0830 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Richard Millis | Normal dredging operations. | 0120 | New York | Dredge New York PP1 Main Engine Seal | NA | Other | Mechanical - SOP | Replacement of engine
298 | Stbd Cutter Motors Overheating | William Bradshaw | Mechanical | Hydraulic Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 42841 | 0 |  | 04/26/2019 | In Progress | 72597 | Mark V Outten | Kurt Hill | Bill Baumann, Armand F Riehl, James C Gillespie | 04/26/2019 | 1800 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny |  | Milton Garcia (watch engineer) & Roger Hancock (oiler) on watch during failure. | 0118 | Texas | Rock chopping | Milling cutter | Stop Work, Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC, Mechanical - Material Specs, Other |  | Check and address all possible cause for failure. Monitor closer during run conditions for symptoms that indicates any warning sign/s.
301 | Dredge New York A-frame Damage | Jaclyn Abrams | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | NONE | 0 |  | 05/09/2019 | Complete | 72597 | Andrew Larkin | Jaclyn Abrams | Bill Baumann, Russell F. Zimmerman, James C Gillespie | 05/09/2019 | 0930 | Dredge | Other | Yes | Dredge | Project - Dredge | In Process | Sunny | Joseph Rye | Employee was located at the front of the observation house at the A-frame controls. | 0120 | New York | A-frame was being pulled back, it went past its normal stopping point. The pull back wires went slack, and the a-frame fell back into the stops. | N/A | Other | Mechanical - SOP
302 | 20190523 Ellis Island Hull Damage | James M Walker | Mechanical | Hopper Dredging | 072616 | NAGS HEAD BEACH RENOURISHMENT | 73495 | 0 |  | 05/23/2019 | Complete | 1823 | Jeremy Remme | James M Walker | George Strawn, Russell F. Zimmerman, Paul C Lamourie | 05/23/2019 | 1700 | Dredge | Vessel Accident -allision / collision, grounding | No | Dredge | Project - Dredge | In Process |  | Chris Harvey | Mate on watch at vessel controls Dragtender on watch at dredge controls | 0151 | Ellis Island | ATB Douglas B Mackie/Ellis Island dredging on Nag's Head project. (see attached map of borrow area/vessel track) | Dredge was in the digging cycle of the load. | Company Policy, Regulations | Other | Dragarm was recovered, so no salvage operation needed. No fuel was leaked and the breach was only to the cofferdam.
308 | Dredge 54 - Boom Damage | Armand F Riehl | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 36230 | 0 |  | 07/31/2019 | Complete | 72597 | Andrew Larkin | David Burlew | Andrew Larkin, Bill Baumann, Russell F. Zimmerman, James C Gillespie | 07/31/2019 | 0030 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | David Burlew | Operator was in the cab. The mate and deck hand were preparing to sail the scow. | 0134 | GL 54 | scow 602 and dredge 54. | 21 cubic yard. | Step Back for Safety, Stop Work | PTP - Pre-Task Planning
311 | Calcasieu River Multibeam Head Damage | Claire Bradford | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | NONE | 0 |  | 08/22/2019 | Complete | 72597 | Andrew Larkin | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 08/22/2019 | 0800 | Crewboat/Survey Boat | Vessel Accident -allision / collision, grounding | Yes | Crewboat/Survey Boat | Survey | In Process | Sunny | Raeford Millis | Tyler Maiers (1yr)-Surveyor in the below cabin at the computer/survey station (stbd side) Cody Chambers(1yr)-Surveyor in the below cabin at the computer/survey station (stbd side) Raeford Millis (+15 yrs)-Boat Captain at the inside controls Deck Hand (4-5 yrs) | 0380 | Calcasieu River | The operator sits on the upper deck of the cabin.The surveyors/deckhand sit in the bottom level of the cabin. The multibeam head is on the bow in the direct view of the operator. | The multibeam head is mounted to a hydraulic lever arm at the bow of the Calcasieu River. When deployed the draft of the head is about 4.2'. | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, Company Policy | PTP - Pre-Task Planning, Other
314 | DR 58 - Boom Point Sheave Bearing Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 38362 | 0 |  | 08/17/2019 | Complete | 3111 | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 08/17/2019 | 2000 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0138 | GL 58 | DR 58 | DR 58 | Other | Mechanical - SOP, Mechanical - QA/QC, Mechanical - Material Specs
316 | DR 54 - Broken Spud Adjustment Bolts | Andrew Larkin | Mechanical | Mechanical Dredging | 015822 | Boston Harbor Maintenance | 34127 | 0 |  | 10/01/2019 | Complete | 15822 | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 10/01/2019 | 0530 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  | David Burlew |  | 0134 | GL 54 | DR 54 - dredging of | Stern Spud | Other | Mechanical - Material Specs | None
319 | 191031 Ellis Bottom Dump Door #5 | Jeremy Remme | Mechanical | Hopper Dredging | 084608 | Corpus Christi Ent Channel Deepening | 74968 | 0 |  | 10/31/2019 | Complete | 084608 | David Mills | Jeremy Remme | Steven W Becker, Paul C Lamourie | 10/31/2019 | 2200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  | Mate and Dragtender operating vessel. | 0151 | Ellis Island | Dredge was involved in bottom dump project | Bottom dump system | Other | Mechanical - Material Specs | Crews professionalism and experience enabled them to identify the problem and react quickly.
320 | DRG 58 #2 Swing pinion shaft bearing failure | Armand F Riehl | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | 38860 | 0 |  | 11/06/2019 | Complete | 72597 | Christopher Charron | Brian Goetchius | James C Gillespie | 11/06/2019 | 1200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  | Phil Sanzone | Operator was in the cab and mate was on the stern of the scow. The mate heard loud noise coming from the crane and smoke. | 0706 | Misc. Equip | Drg 58 was digging with scow along side with no signs of an issue when the noise was heard and all stop called. | crane was functioning normally when the failure occurred. | Stop Work | Mechanical - SOP | SOP to grease the bearing is to be done at installation which was 2014 by Marinex.
323 | Unloader 398 Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 015863 | IWW Delaware River to Chesapeake | NONE | 0 |  | 11/25/2019 | Complete | 15863 | Sherif Abdelgafar | Sherif Abdelgafar | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie | 11/25/2019 | 1100 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Prep | Sunny | Chris Thorp | 1st Astt Engineer - Fred Ofei Electrician - Ahmed Eissa Engineer - Chance Fryar | 0202 | Unloader No. 2 | Unloader #2 398 Generator Engine | Woodward Type UG 8 Governor | Other | JSA - Job Safety Analysis, New Hire Orientation, Safety Rules, Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC, Mechanical - Material Specs
324 | Dredge Illinois Fuel Spill | Sherry Turner | Mechanical | Hydraulic Dredging | 015860 | Sea Isle to Ocean City; NJ | 21029 | 0 |  | 11/28/2019 | Ready for Edits | 15860 | Keith Pearse | Sherry Turner | Dave Allen | 11/28/2019 | 2030 | Dredge | Other | Yes | Dredge | Project - Dredge | In Process |  | David Blackmon | David Blackmon - Oiler : at the valves to open Crew Boat Deckhand: On crew boat waiting to fuel up Watch Engineer: Restroom | 0105 | Illinois | Crew boat Muskegon River was sterned up against the starboard side of the dredge near the fueling station preparing to be fueled. |  |  | JSA - Job Safety Analysis | Emergency fuel shut off was engaged; valve was turned off and clean-up quickly began. All authorities were notified by Leverman while Engine Room crew cleaned the spill. Dredge was tilted to the port side most of the fuel stayed on the deck.
326 | Carolina Port Cutter Motor | Scott Baumann | Mechanical | Hydraulic Dredging | 084608 | Corpus Christi Ent Channel Deepening | 1002284 | 0 |  | 12/07/2019 | Complete | 1913 | James C Gillespie | Kurt Hill | Steven W Becker, Bill Baumann, James C Gillespie, Steven R Auernhamer | 12/07/2019 | 2230 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark, High Winds | Scott Baumann | Leverman was digging at night, deck crew were performing housekeeping and Engine room crew were in Engine room control room | 0110 | Carolina |  |  | Stop Work | Mechanical - PM Plan, Mechanical - SOP, Mechanical - QA/QC
327 | Alaska Christmas Tree Failure | Tim Riehl | Mechanical | Hydraulic Dredging | 072714 | TYBEE ISLAND; GA | 25034 | 0 |  | 12/10/2019 | Ready for Edits | 2247 | Timothy Fleming | Tim Riehl | Bill Baumann, Russell F. Zimmerman, James C Gillespie | 12/10/2019 | 0800 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Lionell Caroon |  | 0101 | Alaska |  |  | Other
328 | DR 55 Fuel Spill | Andrew Larkin | Mechanical | Mechanical Dredging | 015837 | Port of Davisville; RI Maint / New Work | NONE | 0 |  | 12/13/2019 | Complete | 15837 |  | Andrew Larkin | Bill Baumann, James C Gillespie | 12/11/2019 | 1000 | Dredge | Other | Yes | Dredge | Project - Dredge | In Process | Cloudy, Snow | Thomas Lawrence | Normal crew onboard the dredge. The dredge was not operational due to a weather delay. | 0132 | GL 55 | DR 55 | None |  | JSA - Job Safety Analysis, PTP - Pre-Task Planning, Company Policy, Life Saving Absolutes | The crew responded quickly to limit the environmental impact and followed correct communication procedures.
329 | UWP Blown Out Seal Dredge Illinois | Terry Wright | Mechanical | Hydraulic Dredging | 015860 | Sea Isle to Ocean City; NJ | 21106 | 0 |  | 12/18/2019 | Complete | 015860 |  | Terry Wright | David Rappe, Bill Baumann | 12/18/2019 | 1030 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Lanny Lawrence |  | 0105 | Illinois |  |  | JSA - Job Safety Analysis, Safety Rules, Mechanical - PM Plan | Mechanical - SOP, Mechanical - QA/QC
331 | Carolina cutter tailshaft / coupling failure | Bill Baumann | Mechanical | Hydraulic Dredging | 084608 | Corpus Christi Ent Channel Deepening | 1012133 | 0 |  | 01/28/2020 | Complete | 084608 | Mike Gerlach | Bill Baumann | Steven W Becker, James C Gillespie | 01/28/2020 | 2000 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0110 | Carolina | Carolina was dredging | N/A |  | Mechanical - SOP, Mechanical - QA/QC
332 | Swing Motor Failure Dredge Illinois | Terry Wright | Mechanical | Hydraulic Dredging | 015860 | Sea Isle to Ocean City; NJ | 21180 | 0 |  | 12/31/2019 | Ready for Edits | 15860 | James C Gillespie | Terry Wright | Bill Baumann, James C Gillespie | 12/31/2019 | 1200 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Cloudy | Craig Daly |  | 0105 | Illinois |  |  | JSA - Job Safety Analysis
333 | Terrapin Trunnion slide | Mike Kraljevic | Mechanical | Hopper Dredging | 084608 | Corpus Christi Ent Channel Deepening |  | 0 |  | 12/20/2019 | Ready for Edits | 1913 | James M Walker | Mike Kraljevic | Paul C Lamourie | 12/20/2019 |  |  |  | No
336 | Dredge New York Generator Failure | Brian Goetchius | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | NONE | 0 |  | 02/19/2020 | Complete | 72597 | Andrew Larkin | Brian Goetchius | Brian Bickford, Paul C Lamourie | 02/19/2020 | 0800 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Joseph Rye | Minimal crew while the dredge was laid up in Moorhead City, NC due to weather | 0120 | New York | Prepped for tow completing maintenance in Moorhead City, NC | NA | Other | Mechanical - SOP
345 | 20200510 Terrapin Island Hopper Open/Close Damage | James M Walker | Mechanical | Hopper Dredging | 015865 | York Spit; Baltimore Harbor; MD & VA | 65264 | 0 |  | 05/10/2020 | Complete | 15865 | Mike Kraljevic | James M Walker | Chris Roberts, Mark L. Reid | 05/10/2020 | 1530 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  | Dragtender assisting ESO with skimmer controls while bottom dumping during the dredging cycle. | 0148 | Terrapin Island | Terrapin Island in process of disposing a load of sand. | N/A |  | Mechanical - PM Plan, Mechanical - QA/QC
346 | Columbia River Main Engines Damage | Nathan Stevick | Mechanical | Hydraulic Dredging | 084608 | Corpus Christi Ent Channel Deepening | NONE | 0 |  | 05/15/2020 | Complete | 1913 | Nathan Stevick | Nathan Stevick | Dave Allen | 04/27/2020 | N/A | Crewboat/Survey Boat | Mechanical Breakdown | No | Crewboat/Survey Boat | Survey | Idle |  | Michael Brown | Rafael Estrada | 0378 | Columbia River | Columbia River, 40ft Crew/Survey Vessel. Main Engines - 2 Detroit Diesel 8V71 | Starter Fluid | Company Policy, Mechanical - SOP | Mechanical - QA/QC | N/A
347 | Dredge Carolina Cutter Thrust Bearing Failure | Bill Baumann | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1062275 | 0 |  | 05/13/2020 | Complete | 72584 |  | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 05/13/2020 | 0900 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0110 | Carolina | Dredge was working dredging hard material in Charleston entrance channel. | None | Stop Work | Mechanical - SOP, Mechanical - QA/QC | When the ladder was raised for cutter motor troubleshooting, the deck department noticed the thrust bearing was hot (steaming) and reported it to the Chief engineer. This prompted the inspection and discovery of the failure before further damage could occur. Past failures have resulted in much more damage to the housing and shaft.
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Sheldon Brooks | Mechanical | Int'l - Hydraulic Dredging | 022694 | Investment Gateway Bahrain (IGB2) | NONE | 0 |  | 03/02/2020 | Ready for Edits | 00026T | Alexanders Andrezens | Alexanders Andrezens | Brian Bickford | 03/02/2020 | N/A | Booster | Mechanical Breakdown | No | Booster | Project - Dredge | In Process |  |  | Stand by | 0219 | Booster #9 | N/A | N/A | Stop Work, Mechanical - SOP | Mechanical - PM Plan | Internal inspection by 3rd party. Identification of failure, preparation to replace unit
354 | Carolina Port Main pump drive coupling failure | Kurt Hill | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1062537 | 0 |  | 06/19/2020 | Complete | 72584 | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 06/19/2020 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0110 | Carolina | Dredge working on anchors in the Charleston entrance channel | N/A | Stop Work | Company Policy, Mechanical - PM Plan, Mechanical - QA/QC, Mechanical - Material Specs
355 | Carolina UWPS coupling failure | Kurt Hill | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1062397 | 0 |  | 06/03/2020 | Complete | 72584 | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 06/03/2020 | 0900 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0110 | Carolina | Dredge working on anchors in the Charleston entrance channel. | Coupling failed on the ladder pump shaft. | Stop Work | Mechanical - PM Plan, Mechanical - QA/QC, Mechanical - Material Specs | A complete spare shaft with a new flex coupling half installed was on site and ready for installation. This expedited the repair.
358 | DR 53 Swing Gearbox Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072597 | Jacksonville Harbor Deepening Contract B | NONE | 0 |  | 07/27/2020 | Ready for Review | 3111 | Brian Goetchius | Holt Hartung | Brian Bickford, Steven W Becker, James C Gillespie | 07/26/2020 | 0800 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Extreme Heat | Wade Eldridge |  | 0133 | GL 53 | DR 53 | DR 53 | Mechanical - PM Plan | Mechanical - QA/QC | DR 53 digging in Jacksonville wiht 18 cyd bucket.
361 | Carolina Plugged Service water line | Scott Baumann | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1244386 | 0 |  | 08/23/2020 | Ready for Edits | 2445 | Holt Hartung | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie | 08/23/2020 | 2230 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Transition | Dark | Dwight Davis | 2 Watch Engineers and Oiler working on the replacement of the gasket after oil leak found | 0110 | Carolina |  |  | Stop Work, Mechanical - QA/QC | JSA - Job Safety Analysis, Mechanical - SOP, Mechanical - Material Specs
362 | Dr 54 - Holding Drum Brake | Andrew Larkin | Mechanical | Mechanical Dredging | 015896 | Port Jersey Channel; NJ | 1234227 | 0 |  | 08/19/2020 | Ready for Edits | 15896 | Brian Goetchius | Brian Goetchius | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie | 08/19/2020 | 0600 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Extreme Heat | David Burlew | Normal dredging Ops | 0134 | GL 54 | Dredging Port Jersey | None | Step Back for Safety | Mechanical - PM Plan | Southern Services rebuilding foundation.
363 | Ohio Cutter Gearbox Contamination | Jose Gracia | Mechanical | Hydraulic Dredging | 015860 | Sea Isle to Ocean City; NJ | 65651 | 0 |  | 08/26/2020 | In Progress | 015860 | Alexanders Andrezens | Jose Gracia | Brian Bickford, Steven W Becker, James C Gillespie | 08/26/2020 | 0100 | Dredge | Struck against | No | Dredge | Project - Dredge | Clean Up | Dark | Hector Gonzales | The crew involved was the watch engineer and oiler. | 0103 | Ohio | Standard dredging | No tools were used. | Other
364 | 22694_Port Engine Gear Box Bearing Failure | Sheldon Brooks | Mechanical | Int'l - Hopper Dredging | 022694 | Investment Gateway Bahrain (IGB2) | NONE | 0 |  | 05/09/2020 | Ready for Edits | 1117 | Alexanders Andrezens | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson | 05/09/2020 | 1600 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Igor Shlyapnikov | Chief Engineer(+3years); Watch Engineer(+2years); Oiler(+2years) | 0141 | Sugar Island | TSHD Sugar Island arranged for over-bow pump-out configuration through floating swivel(cube); started pump-out | N/A | Mechanical - SOP | Mechanical - Material Specs | Internal inspection by 3rd party. Identification of failure, immediate required repairs of unit.
365 | Ohio Auxiliary Winch Damages | Jose Gracia | Mechanical | Hydraulic Dredging | 015860 | Sea Isle to Ocean City; NJ | NONE | 0 |  | 09/07/2020 | In Progress | 015860 | Sherif Abdelgafar | Jose Gracia | Brian Bickford, Steven W Becker, David Rappe, James C Gillespie | 09/07/2020 | 0700 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | High Winds | Hector Gonzales | Dredge Captain Levermen | 0103 | Ohio | Dredge was operating on wires with the new xmas tree arrangement for the first time. Standard vessel configuration for dredging. | Two breast winches / one sten winch / 2 swing winches and installed wire rope and anchors. Did any of th anchors have chain or directly attached by cable? | Mechanical - PM Plan | Mechanical - Material Specs | Vessel equipment performance to be reviewed and equipment to be upgraded to achieve required parameters for dredging
366 | DR 54 - Boom Heel Pin | Andrew Larkin | Mechanical | Mechanical Dredging | 015845 | Baltimore Harbor and Channels; MD | 1076313 | 0 |  | 04/12/2020 | In Progress | 15845 | Brian Goetchius | Brian Goetchius |  | 04/12/2020 | 0300 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark | Alex Morris | Normal dredging operations | 0134 | GL 54 | Normal dredging operations in Baltimore using the 47 cyd bucket | None | Step Back for Safety | Mechanical - PM Plan | Damage to the bushings was discovered prior to a catastrophic failure.
368 | Alaska M/P Thrust Bearing Failure | Jose Gracia | Mechanical | Hydraulic Dredging | 084604 | Sabine LNG | 1194178 | 0 |  | 09/26/2020 | Complete | 6359 |  | Jose Gracia | Brian Bickford, James C Gillespie | 09/26/2020 | 1200 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Lionell Caroon | Dredge captain | 0101 | Alaska | Dredge pump thrust bearing failure. | Impact gun Wrenches Measurement tools Cleaning consumables | Mechanical - PM Plan | Other
369 | Booster Jessie Starboard Gearbox Bearing Failure | Nicholas D Williams | Mechanical | Hydraulic Dredging | 084727 | MSCIP Ship Island Restoration; PH 3&4 | NONE | 0 |  | 10/22/2020 | Complete | 1914 | Shawn Boynton | Kurt Hill | Steven W Becker, David Rappe, James C Gillespie | 10/22/2020 | 0900 | Booster | Mechanical Breakdown | No | Booster | Project - Dredge | In Process | Sunny | Nicholas D Williams | none | 0212 | Jessie | Stbd main pump gear box and shafting | None | Mechanical - PM Plan, Other | Mechanical - QA/QC | With the new set up on the Jessie there are couplings that are suppose to let shaft slide . The coupling is not suppose to corrode or rust but it had become so rusted that it did not slide. There was to much load placed on the thrust bearing for gear box so it failed. A line has been added into the work order to take coupling apart and inspect them every time the thrust bearing is moved.
371 | Unloader Snorkel Drift | Andrew Larkin | Mechanical | Mechanical Dredging | 000000 | Off Project | NONE | 0 |  | 11/12/2020 | In Progress | 111111 | Brian Goetchius | Andrew Larkin |  | 11/04/2020 | 2400 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | Idle | High Winds, Rain, Severe Storms | Chris Thorp | No crew on board. | 0202 | Unloader No. 2 | NA | NA | Other | Mechanical - SOP | NA
374 | Cape Girardeau Yard- Crane Boom Failure | Christopher Charron | Mechanical | Rivers & Lakes Dredging | 000000 | Off Project | NONE | 0 |  | 12/01/2020 | Complete | 111 | Everett Reed | Christopher Charron | Steven Lane, Jason Campbell | 12/01/2020 | 1200 | Yard | Other | Yes | Land-Other | Yard | In Process | Sunny |  |  | 0706 | Misc. Equip | Crane was position to the left and slightly aft of the truck's trailer, appx 2/3 way back. see attached document | see attached document | JSA - Job Safety Analysis, Other | PTP - Pre-Task Planning | Personnel were alert and were not standing in any potential danger zones
375 | Liberty Is Uncommand Stops Gen + Main Eng | Chris Roberts | Mechanical | Hopper Dredging | 015914 | Great Egg Harbor Inlet to Absecon Island; NJ | 70789 | 0 |  | 10/13/2020 | Ready for Edits | 6370 | Chris Roberts | Chris Roberts | James M Walker | 10/13/2020 | N/A | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Cloudy |  | N/A | 0147 | Liberty Island | ~ October 9, sometime before leaving Norfolk there was reports by Carter ~October 11, the Liberty arrived to Absecon project and commenced project ~October 15 afternoon the Liberty’s port main engine and starboard generators were experiencing uncommand shutdowns. ~October 20, the ECMs replaced but there were still weird alarms occurring ~October 21, PLC controls replaced, the E-Stop system had replaced diodes, a short on an old guillotine (?) switch located as issue – disconnected solenoid compromised and removed. ~Restart on Absecon project | N/A | PTP - Pre-Task Planning | Mechanical - PM Plan
376 | Dredge Texas fuel tank vent plugs incident | Jose Gracia | Mechanical | Hydraulic Dredging | 015914 | Great Egg Harbor Inlet to Absecon Island; NJ | NONE | 0 |  | 12/07/2020 | Ready for Edits | 6370 |  | Bill Baumann | Brian Bickford, James C Gillespie | 12/07/2020 | N/A | Dredge | Other | No | Dredge | Project - Dredge | In Process |  |  |  | 0118 | Texas | NA | NA | Step Back for Safety | Mechanical - SOP, Mechanical - QA/QC
377 | Dredge Texas internal fuel leak incident | Robert Kelly | Mechanical | Hydraulic Dredging | 072584 | Charleston Entrance Channel; Contract 2 | 1248760 | 0 |  | 12/15/2020 | In Progress | 2445 |  | Bill Baumann | Brian Bickford, James C Gillespie | 10/13/2020 | 0930 | Dredge | Other | No | Dredge | Project - Dredge | In Process |  |  |  | 0118 | Texas | Dredge on project | N/A | Regulations | Mechanical - QA/QC
378 | Terrapin Island-Deck Generator (Cat 3516) Failure | Nilene Brunslik | Mechanical | Hopper Dredging | 072569 | Charleston Harbor Deepening/Widening Con. 1 | NONE | 0 |  | 12/10/2020 | Complete | 072569 | Chris Roberts | Chris Roberts | Mike Kraljevic, James M Walker, Chris Roberts | 12/10/2020 | N/A | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process |  |  |  | 0148 | Terrapin Island | 1. Foundation Wastage caused flexing. Inadequately Engineered platform to begin with. 2. Start up Overloaded. 3. Jet Valve Leaks 4. Production demand, Production estimates / project completion schedule 5. Full understanding of what to check alignment wise and how to check it. | n/a | PTP - Pre-Task Planning | Mechanical - Material Specs
382 | GL 501 - Cylinder Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072727 | Jacksonville Harbor Deepening Contract C | NONE | 0 |  | 12/21/2020 | Ready for Review | 6383 | Holt Hartung | Brian Goetchius | Brian Bickford, Steven W Becker, James C Gillespie | 12/17/2020 | 0330 | Hopper Barge | Mechanical Breakdown | No | Hopper Barge | Project - Dredge | In Process | Dark | Richard Millis | Normal Operations | 0451 | G.L. 501 | Dredge NY loading the GL 501 scow | NA | Other | Mechanical - PM Plan, Mechanical - QA/QC | NA
383 | DR New York Boom Cylinder Failure | Andrew Larkin | Mechanical | Mechanical Dredging | 072727 | Jacksonville Harbor Deepening Contract C | NONE | 0 |  | 01/06/2021 | In Progress | 72727 | Brian Goetchius | Brian Goetchius |  | 12/27/2020 | 1330 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Joseph Rye | Normal operations | 0120 | New York | Dredging on the Jacksonville C deepening project. | NA | Mechanical - QA/QC | Mechanical - Material Specs | The Dredge NY crew is very skilled in changing out cylinders which limited the downtime to less than 30 hours.
384 | Pass A'Loutre Survey | William Bradshaw | Mechanical | Hydraulic Dredging | 000000 | Off Project | NONE | 0 |  | 01/15/2021 | Complete | 1 | Dane Nelson | William Bradshaw | David J Johanson, Christopher Gunsten, Garrett Gibson | 01/15/2021 | 1500 | Crewboat/Survey Boat | Other | No | Crewboat/Survey Boat | Survey | In Process | Cloudy, Dark | Sydcarl Thwaits | Surveyors on survey boat Hollie Belle conduction channel surveys. PE, PM, SM onboard Dredge Illinois observing dredging operations | 0706 | Misc. Equip | Hypack 2018. Hi and Lo frequency transducers. | tape measure, RTK, lead line | Company Policy | PTP - Pre-Task Planning, Mechanical - SOP, Mechanical - QA/QC
386 | Scow 66 #1 Closing Cylinder Failure 210127 | Jeremy Remme | Mechanical | Mechanical Dredging | 072732 | Post 45 Lower Charleston Harbor; Contract 4 | NONE | 0 |  | 01/27/2021 | In Progress | 072732 | Holt Hartung | Robert Kelly | Andrew Larkin, Russell F. Zimmerman | 01/27/2021 | 1130 | Hopper Barge | Mechanical Breakdown | No | Hopper Barge | Project - Dredge | In Process | Cloudy |  |  | 0466 | G.L. 66 | Scow was under tow from the Anne Jarrett and dumped remotely. No one was onboard the scow. | Tug Anne Jarrett with Scow 66 under tow for disposal operations. | Stop Work | Mechanical - PM Plan
389 | Crane Boom Failure | Terreo Hathorn | Mechanical | Rivers & Lakes Dredging | RR1428 | Yazoo River Basin | NONE | 0 |  | 03/05/2021 | Complete | 6388 | Christopher Charron | Chris Faught | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 03/05/2021 | 1630 | Attendant Plant - Other | Mechanical Breakdown | Yes | Attendant Plant - Other | Project - Dredge | In Process | Sunny | James Woodell | James Woodell was on the crew/deck boat supervising the operation. Fabian Lozano was the mate on the Plowboy directly on the port side of the crane barge as the signal person. Ricky Crayton was the mate on the Plowboy assisting with connecting the float hose together. Kessel Ebanks was the crane operator in the Omega Crane. | 0706 | Misc. Equip | Omega Crane Barge | N/A | JSA - Job Safety Analysis, SALT - Save A Life Today Rule | PTP - Pre-Task Planning, Company Policy, Stop Work | N/A
391 | Cutter Gear Box Input Shaft Bearing Failure | Terry Wright | Mechanical | Hydraulic Dredging | 000000 | Off Project | 1358318 | 0 |  | 02/25/2021 | Complete | 1 | Dave Allen | Jose Gracia | Jose Gracia, Brian Bickford, Steven W Becker | 02/24/2021 | 1130 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | Sunny | Lanny Lawrence |  | 0105 | Illinois | Dredge IL Cutter Gearbox Input Shaft Bearing Failure- Port Side | Dredge was digging in normal operation | Stop Work | Mechanical - SOP, Mechanical - Material Specs
394 | Jax Yard Marina Damage | Steve W Lawrence | Mechanical | Mechanical Dredging | 000000 | Off Project | NONE | 0 |  | 04/02/2021 | In Progress | 1 | christopher Miller | Steve W Lawrence | Gail Johnson | 04/02/2021 |  |  |  | No
398 | GL10 Idler Barge | Shawn Boynton | Mechanical | Hydraulic Dredging | 084815 | Freeport Harbor Lower Stauffer C | 1264325 | 0 |  | 05/11/2021 | Ready for Review | 6392 | Scott Baumann | Tim Riehl | Jose Gracia, Brian Bickford | 05/05/2021 | 0900 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  |  | 0105 | Illinois | Dredge and GL10 normal dredging operations | Bearing failure normal Dredging operation | Stop Work | Mechanical - QA/QC, Mechanical - Material Specs
399 | Ellis Island Miss Dump | Nicholas D Williams | Mechanical | Hopper Dredging | 084863 | Mobile Harbor Deepening & Widening; Phase 3 | NONE | 0 |  | 05/21/2021 | Complete | 84863 | Jeremy Remme | Crystopher Barnett | George Strawn, James M Walker, Chris Roberts, Garrett Gibson | 05/21/2021 | 0130 | Dredge | Other | No | Dredge | Project - Dredge | In Process | Dark, High Winds | Chris Harvey | Vessel was operational with full crew | 0151 | Ellis Island | Vessel was in transit from dredging area to the disposal area. Vessel was operating as ATB with no other support equipment |  | Other | Mechanical - QA/QC | After observing alarm crew pressed bottom dump cylinder back up to close bottom dump doors
401 | Liberty Island Main STBD Engine Turbo Failure | Chris Pomfret | Mechanical | Hopper Dredging | 072759 | South Atlantic Regional Harbor Dredging | 71644 | 0 |  | 06/08/2021 | Complete | 6393 | James M Walker | James M Walker | George Strawn, Mike Kraljevic, James M Walker, Chris Roberts | 06/08/2021 | 1830 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Cloudy | Michael Las Dulce |  | 0147 | Liberty Island | Stbd M/E running | Turbo | Mechanical - SOP | Mechanical - QA/QC | 10 May 2022 - As per Mike K. the report from CAT indicated that "something, some object, could have hit the blades and caused the failure." So... there is no next step.
405 | Pass A'Loutre GL 660 Dozer Sinking | William Bradshaw | Mechanical | Hydraulic Dredging |  |  | 1 | 0 |  | 07/01/2021 | Complete | 6377 | Mike Huebsch | William Bradshaw | David Rappe, Garrett Gibson, Dave Allen | 07/01/2021 | 1600 | Fill Site | Other | No | Fill Site | Project - Land/Disposal Area | In Transition | Cloudy | James Ganus | GL 660 was working at spreader location 1 and began to move to spreader location 2. GL 661 working at spreader location 1. Marsh buggy not operational. Komatsu D61 down. | 0706 | Misc. Equip | Dozers setup at spreader locations. As the y-valves were switched, dozers moved over to the current line | D6 LGP bulldozer | PPE - Personal Protection Equipment | PTP - Pre-Task Planning, Stop Work | Due to weather and other non-functional equipment, removal of the dozer was delayed. Eventually, 3 snatch blocks were used in conjunction with the dozers and marsh buggy. Rain delayed the recovery as the hole where the dozer was consistently filled with water and had to be drained prior to recovery efforts.
406 | Dr 58 Boom Drop | Andrew Larkin | Mechanical | Mechanical Dredging | 072727 | Jacksonville Harbor Deepening Contract C | 1632216 | 0 |  | 08/01/2021 | In Progress | 6383 | Brian Goetchius | Andrew Larkin | Steven W Becker, James C Gillespie | 08/01/2021 |  |  |  | No | [6 empty] | 0138 | GL 58
407 | Starboard Main Pump | Wade Smith | Mechanical | Hydraulic Dredging | 084815 | Freeport Harbor Lower Stauffer C | 1540107 | 0 |  | 06/15/2021 | Complete | 6392 | Wade Smith | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl | 06/15/2021 | 0130 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Scott Baumann | Captain Chief Engineer Deck Captain Mates Crew | 0110 | Carolina | GL10 is attached to the Dredge Carolina | Ordered new pump shell and elbow. | Stop Work |  | Dredge personnel did not foresee the alignment issue on the elbow. Not sure as to why alignment was not correct.
408 | Ladder Pump / Gear Box | Wade Smith | Mechanical | Hydraulic Dredging | 084815 | Freeport Harbor Lower Stauffer C | 1264272 | 0 |  | 04/26/2021 | In Progress | 084815 | Scott Baumann | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl | 04/26/2021 | 1730 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny |  |  | 0110 | Carolina | GL10 is connected to the Dredge Carolina | None were involved. | Step Back for Safety, Mechanical - SOP | Other | Captain heard noise coming from the gear box and investigated. Maintenance departed shut project down until repairs could be made.
409 | Main Pump Thrust Bearings Port side | Wade Smith | Mechanical | Hydraulic Dredging | 084815 | Freeport Harbor Lower Stauffer C | 1512128 | 0 |  | 05/28/2021 | In Progress | 084815 | Wade Smith | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl | 05/28/2021 | 0730 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Sunny | Scott Baumann | Captain Chief Deck Captain Mate Crew | 0110 | Carolina | GL10 attached to the Dredge Carolina | None Noted. | Mechanical - SOP | Other
412 | Dredge Carolina MP Thrust Bearing Coupling | Wade Smith | Mechanical | Hydraulic Dredging | 084815 | Freeport Harbor Lower Stauffer C | 1622726 | 0 |  | 09/03/2021 | Complete | 084815 | Wade Smith | Thomas Christenson | Jose Gracia, Brian Bickford, Steven W Becker | 09/03/2021 | 2000 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Extreme Heat | Thomas Christenson | Captain Chief Deck Captain Mate Crew | 0110 | Carolina | GL10 attached to the dredge. | None | Mechanical - SOP | Mechanical - Material Specs | Project down for more than 24 hours due to project had to have replacement part trucked from out of state.
418 | Liberty Island Turbo Failure | Mike Gerlach | Mechanical | Hopper Dredging | 084826 | Panama City Beaches; FL | 1660594 | 0 |  | 10/14/2021 | Ready for Edits | 84826 | Mike Gerlach | Jason Mixon | George Strawn, James M Walker, Chris Roberts, James C Gillespie, Garrett Gibson | 10/14/2021 | 0430 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process |  |  |  | 0147 | Liberty Island |  | CAT Engine Turbo having 7000 hours use. Normal PM is 18,000 swap out. | Mechanical - PM Plan | Mechanical - Material Specs
419 | R032 Booster 3516 engine failure | Terry Newberry | Mechanical | Rivers & Lakes Dredging | RR1428 | Yazoo River Basin | 1660978 | 0 |  | 10/25/2021 | In Progress | 6388 | Eric Perez | Terry Newberry |  | 10/25/2021 | 1200 | Booster | Mechanical Breakdown | Yes | Booster | Project - Dredge | In Process | Sunny | Greg Bell | Greg Bell booster operator | R032 | Booster 32-20 | R032 is a 20" skid mounted 2000hp booster | None | JSA - Job Safety Analysis, SALT - Save A Life Today Rule, SALT Recommended Practice, Life Saving Absolutes | Mechanical - PM Plan | Install spare engine
425 | Ellis Island Overbow Elbow Failure | David Dye | Mechanical | Hopper Dredging | 016003 | Sandy Hook to Barnegat Inlet; NJ | 1777103 | 0 |  | 02/18/2022 | Complete | 6424 | Matt Ferrell | David Dye | George Strawn, Mike Kraljevic, James M Walker, Chris Roberts, David Rappe, Mark L. Reid, Dave Allen | 02/18/2022 | 0600 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | In Process | High Winds | Chris Harvey |  | 0151 | Ellis Island | Ellis Island hooked up to pumpout location | Float hose with probe hooked up to overbow elbow | JSA - Job Safety Analysis, Mechanical - SOP, Mechanical - Material Specs, Other |  | Recommend analysis of overbow assembly looking at adding additional supports similar to other hopper dredges.
432 | Dodge Island - Rudder Damage / Loss | Chris Roberts | Mechanical | Hopper Dredging | 084820 | Mobile Harbor Deepening & Widening; AL | 12345678 | 0 |  | 08/25/2021 | Complete | 6402 |  | Chris Roberts | Mike Kraljevic, James M Walker | 08/25/2021 | 0330 | Dredge | Other | No | Dredge | Project - Dredge | In Process | Dark | George Hofmann | Mate - Cory Gallagher | 0142 | Dodge Island | Vessel | None |  | Other
436 | Ohio Plugged Subline | Brandon Suire | Mechanical | Hydraulic Dredging | 084837 | Corpus Christi Ship Channel Upper Bay Reach | 27262329 | 0 |  | 06/16/2022 | Complete | 6418 | Nick Yancy | Nick Yancy | Jose Gracia, David Rappe, David J Johanson, Scott Baumann, Dave Allen | 06/17/2022 | 0030 | Pontoon Tank/Pipeline | Other | No | Pontoon Tank/Pipeline | Project - Dredge | In Process | Dark |  | LM was at the dredge controls actively digging the dredge. Booster Engineer attending Booster controls. | 0103 | Ohio | Dredge Ohio was digging inbound on the green side of the channel STA 109+100. Dredge ladder depth at 53' and up to 38'. Box cutting as slope program not working. Digging on 18,000' of Subline. About 8,000' of line before Booster . Booster inline at STA 102+200, running properly at time of incident. | Dredge Ohio and Booster 9. | Other
437 | Ohio UWP Gearbox & Thrust Bearing Failures | Brandon Suire | Mechanical | Hydraulic Dredging | 084837 | Corpus Christi Ship Channel Upper Bay Reach | 27262197 | 0 |  | 05/31/2022 | In Progress | 6418 | Mark Manfredi | Mark Manfredi | Jose Gracia, Brian Bickford, Scott Baumann, Dave Allen | 05/31/2022 |  |  |  | No
438 | Ohio UWP GB Intermediate Bearing Failure | Brandon Suire | Mechanical | Hydraulic Dredging | 084837 | Corpus Christi Ship Channel Upper Bay Reach | 27262367 | 0 |  | 06/25/2022 | In Progress | 6418 | Mark Manfredi | Mark Manfredi | Jose Gracia, Brian Bickford, Scott Baumann, Dave Allen | 06/25/2022 |  |  |  | No
446 | Ohio Ladder Damage from Swing Wire | Wade Smith | Mechanical | Mechanical Dredging | 084837 | Corpus Christi Ship Channel Upper Bay Reach | 27263081 | 0 |  | 08/27/2022 | In Progress | 6418 | Nick Yancy | Nick Yancy | Thomas Salter, David Mills, Jose Gracia, David Rappe, Scott Baumann, Dave Allen | 08/27/2022 | 0430 | Dredge | Mechanical Breakdown | No | Dredge | Project - Dredge | In Process | Dark |  | Deck crew was on AB103 with Tug Eliana, Dredge Leverman was at the dredge controls. | 0103 | Ohio | Dredge was digging inbound on the red side of the channel between buoy marker R50 and R56. At time of incident the dredge was moving the port anchor. The dredge deck crew was on the AB103 with the Tug Eliana. This incident happened at about 4:30AM | Anchor barge, Dredge Ohio, Tug Eliana | Other
448 | R010 Iowa Dredge Ladder Cable Failure | Terry Newberry | Mechanical | Rivers & Lakes Dredging | RR1453 | Memphis District SATOC 24-29 inch CSD Rental |  | 0 |  | 09/07/2022 | In Progress | 6405 | Chad Bourg | Terry Newberry | Stan Ekren | 09/07/2022 |  |  |  | No
450 | GL-10 GE-752 Motor Coupling Failure | Bobby Conners Jr | Mechanical | Hydraulic Dredging | 084889 | HSC Expansion Channel Improvments | 27,423,526 | 0 |  | 09/17/2022 | In Progress | 6429 | Christopher Martin | Bobby Conners Jr | Thomas Peyton, Steven W Becker, David J Johanson, Dave Allen | 09/17/2022 | 1930 | Idler/Power Barge | Mechanical Breakdown | Yes | Idler/Power Barge | Project - Dredge | In Process | Dark |  |  | 0595 | G.L. 10
451 | Ohio Ladder Winch | Jose Gracia | Mechanical | Hydraulic Dredging | 084608 | Corpus Christi Ent Channel Deepening |  | 0 |  | 10/08/2022 | In Progress | 1913 | Christopher Martin | Jose Gracia | Steven W Becker | 10/08/2022 | 1700 | Dredge | Mechanical Breakdown | Yes | Dredge | Project - Dredge | Clean Up | Sunny | Zachary Price | Corpus Christi Channel | 0103 | Ohio |  |  | Mechanical - PM Plan, Other

## MCIA Corrective Actions
Case ID | Case Title | Case Status | Corrective Action | Responsible Party | Verification Manager | Lead Contact | Executive Review Team | Due Date | Pilot Status | Priority | Roll Out Sites | Roll Out Status | Validated | Authenticated
30 | Equipment Damage Survey Boat Hallets Point | Complete | Standard Operating Procedure (SOP) must be written for these type of vessels to include ensuring a mooring plan is made for each class of vessel at the beginning of each project which is site specific and contains inclement weather contingencies and proper mooring configuration/procedures. Also important that the crew is shown the plan and is made readily available to them. | Chris C Harris | Ed Tiearney | Ed ODowd | Steve O'Hara, Sam R Morrison, Ed Tiearney | 03/15/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
30 | Equipment Damage Survey Boat Hallets Point | Complete | WO to be created to install a automatic float switch on the bilge pump | Chris C Harris | Ed Tiearney | Ed ODowd | Steve O'Hara, Sam R Morrison, Ed Tiearney | 03/15/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
30 | Equipment Damage Survey Boat Hallets Point | Complete | The written SOP must include instructions for Boat Operators to observe the vessel binder each shift to ensure availability of relevant documentation. Perform Vessel inspections and submit the maintenance checklist to the Technical Department on a daily basis. | Chris C Harris | Ed Tiearney | Ed ODowd | Steve O'Hara, Sam R Morrison, Ed Tiearney | 03/15/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
30 | Equipment Damage Survey Boat Hallets Point | Complete | WO to be created for the drain holes with one way scuppers and close off the side scuppers and drain holes with one way scuppers and close off the side scuppers. | Chris C Harris | Ed Tiearney | Ed ODowd | Steve O'Hara, Sam R Morrison, Ed Tiearney | 03/15/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
31 | GL67 Boom Damage | Complete | Make SOP for all divisions that all cranes are not to tow anywhere outside of immediate dredging work area unless the boom is in the saddled or lowered to lowest level and secured. | Dave Allen | Matt Ferrell | Matt Ferrell | Chris Faught, Steven Lane, David J Johanson, Andrew M Funke | 07/28/2017 | CA Incident Prevention Confirmed | High | Hydraulic, Rivers & Lakes, Hopper, Mechanical | 100% complete | Yes | No
31 | GL67 Boom Damage | Complete | Develop new Voyage Plans for inshore towing. SMS voyage plan does not apply to inland hazards. | Chris Faught | Matt Ferrell | Matt Ferrell | Chris Faught, Steven Lane, David J Johanson, Andrew M Funke | 07/28/2017 | CA Incident Prevention Confirmed | High | Rivers & Lakes | 100% complete | Yes | No
33 | MCIA 053 Dozer Sinking | Complete | Review Incident with all shifts and display "Prevent Sinkings" poster. | Barry Jones | Bryan P Dast | Manny Vianzon | Christopher M Wire, Steve O'Hara | 12/31/2016 | CA Incident Prevention Confirmed | High |  | 100% complete | Yes | No
33 | MCIA 053 Dozer Sinking | Complete | Develop a training program to be used during the orientation process, prior to job startup, which includes adding pipeline, moving equipment, hazard recognition and accountability policies. | Manny Vianzon | Steve O'Hara | Manny Vianzon | Christopher M Wire, Steve O'Hara | 05/01/2017 | CA Incident Prevention Confirmed | High | Hydraulic, Hopper | 100% complete | No | No
33 | MCIA 053 Dozer Sinking | Complete | Develop SOP for General / Assistant Foremen to ensure operators are operating or standing-by away from hazards prior to being "out of sight". (Check-in communication system) | Barry Jones | Manny Vianzon | Manny Vianzon | Christopher M Wire, Steve O'Hara | 08/14/2016 | CA Incident Prevention Confirmed | High |  | 100% complete | Yes | No
33 | MCIA 053 Dozer Sinking | Complete | Develop JSA for piping up near the waterline at night. | Barry Jones | Bryan P Dast | Manny Vianzon | Christopher M Wire, Steve O'Hara | 02/28/2017 | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
64 | MCIA 005_2016 | Complete | Re-design discharge pipe adapters or an additional rubber hose connection between the pump casing and discharge adapter required. | Mike Hungerford | Sheldon Brooks | Mike Hungerford | Steve O'Hara, Sam R Morrison | 03/15/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
64 | MCIA 005_2016 | Complete | Develop a JSA for specific pump pipe adapters | Hector Gonzales | Mike Hungerford | Mike Hungerford | Steve O'Hara, Sam R Morrison | 01/31/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | project orientation for each employee prior to starting work on new projects | Dave Johanson | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | JSA template for on the job equipment moves. Safety Alert - When JSA appropriate | Roger Nichols | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | post job specific hazards on all vessels and support equipment on project | Dave Johanson | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | Remind Captain / Crane Operators to complete a JSA for all support equipment moves; to include (Derrick, Barge, etc..) Fleet and Project wide assessment | David Rappe | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | Instruct Derrick Operator to always cradle the boom of the derrick during transit away from immediate dredge work area. If not, provide reason per crane operator or tug captain for advance approval by dredge manager | David Rappe | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
71 | MCIA 001 - Crane Collision 72464 | Complete | consult navigation charts or chart plotters per USCG regulations | David Rappe | David J Johanson | Dave Johanson | David Rappe, Russell F. Zimmerman, Dave Allen | 02/28/2017 | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
79 | Dredge 54 Boom Hoist - Philadelphia | In Progress | Instruct Operators to cease use of the boom dog during the dredging cycle. | Brian Goetchius | Steve W Lawrence | Steve W Lawrence | Mark L. Reid, Christopher Gunsten, Jason Campbell |  | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
79 | Dredge 54 Boom Hoist - Philadelphia | In Progress | Instruct Operators to cease use of the boom dog during the dredging cycle. | Brian Goetchius | Steve W Lawrence | Steve W Lawrence | Mark L. Reid, Christopher Gunsten, Jason Campbell |  | CA Incident Prevention Confirmed | Critical | Mechanical | 100% complete | Yes | No
79 | Dredge 54 Boom Hoist - Philadelphia | In Progress | Design and install a suitable boom brake that will slow or stop the boom from falling | Brian Goetchius | Christopher Gunsten | Steve W Lawrence | Mark L. Reid, Christopher Gunsten, Jason Campbell |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
81 | Padre Island dredge pump cleanout door failure | Complete | Change type of connector for this type of clean out door. | Mike Kraljevic | James M Walker | Paul C Lamourie | James C Gillespie | 12/01/2016 | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
81 | Padre Island dredge pump cleanout door failure | Complete | Engineering and Division review of drawings sent to/received from vendors. | Mike Kraljevic | James M Walker | Paul C Lamourie | James C Gillespie | 12/01/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Send out all 4 Magotteaux impellers to be QC'ed and repaired so that they fit on a proper thread gauge and incorporate the register fit on the impeller hub as indicated in the drawings. | Joe Moon | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen | 04/15/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Require written confirmation that manufacturers have received and properly use all supplied drawings. | Joe Moon | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Require Magotteaux to build a proper shaft thread gauge | Joe Moon | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Stop use of the blue coated liners until it can be determined/confirmed why it failed. | Joe Moon | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen | 05/15/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Investigate and confirm why the blue coating on the liners failed | Joe Moon | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen | 04/15/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
83 | FL MP Thrust Bearing Failure | Complete | Determine if the thread specifications on the drawings are correct or if they need to modified. | Tim Riehl | Bill Baumann | Eugene Corey | David Rappe, Bill Baumann, David J Johanson, Dave Allen | 05/15/2017 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
95 | MCIA_012_2016_CSD Ohio Broken STBD Pump Shell | Complete | Review Pump Program recommendations for location of Booster 9 behind Dredge Ohio | Michael Bermeo | Sheldon Brooks | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 10/31/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
95 | MCIA_012_2016_CSD Ohio Broken STBD Pump Shell | Complete | Review dig instructions and patterns of lever-man(recommendations on dig method needed?) | Michael Bermeo | Sheldon Brooks | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney |  | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
95 | MCIA_012_2016_CSD Ohio Broken STBD Pump Shell | Complete | A - Review Casting/QC Procedures with manufacture B - Send damaged pump shell for UT Investigation | Joe Moon | Sheldon Brooks | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney |  | CA Incident Prevention Confirmed | Low | Int'l - Hydraulic | 100% complete | Yes | No
99 | Derrick 65 - Bent Boom Chord and Lacing | Complete | Draft and broadcast an action alert for proper rigging points including air compressor barges. | David Rappe | Stuart Hilgendorf | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 02/12/2019 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
99 | Derrick 65 - Bent Boom Chord and Lacing | Complete | Write a specific JSA and Pre-Lift plan for Lifting AC barge out of water | Stuart Hilgendorf | David Rappe | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 03/20/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
99 | Derrick 65 - Bent Boom Chord and Lacing | Complete | Specify in the JSA that there may be a hazard if there is water in any air compressor barge tanks and its presence will add to the estimated weight of the barge and may result in possible shifting of the load. | Stuart Hilgendorf | David Rappe | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 03/20/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
99 | Derrick 65 - Bent Boom Chord and Lacing | Complete | Specify in the JSA that Saddle pin holes are not proper lifting points for picking up AC Barge instead lift by rigging straps or cable to choke the pipe | Stuart Hilgendorf | David Rappe | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 03/20/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
99 | Derrick 65 - Bent Boom Chord and Lacing | Complete | Specify in the JSA the estimated load of a 5 tank compressor barge and the practice of knowing and not exceeding 75% of the maximum load at the boom angle you are intending to make the lift. | Stuart Hilgendorf | David Rappe | Stuart Hilgendorf | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 03/20/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
100 | MB1706 Derrick - Lifting Cube | Ready for Edits | The operator shall check to ensure the load weight and radius in within the crane capacity chart prior to making any lift. |  |  | Rodney Fromenthal Jr. | Mark L. Reid |  | Not Started |  |  |  | No | No
100 | MB1706 Derrick - Lifting Cube | Ready for Edits | A critical lift plan shall be completed prior to lifting the cube. |  |  | Rodney Fromenthal Jr. | Mark L. Reid |  | Not Started |  |  |  | No | No
100 | MB1706 Derrick - Lifting Cube | Ready for Edits | The hoses connected to the cube shall be aligned parallel to the barge as to prevent the load drifting further away from the crane. In addition the cube (lifting point) shall be placed as close to the crane as possible prior to rigging and lifting the cube. |  |  | Rodney Fromenthal Jr. | Mark L. Reid |  | Not Started |  |  |  | No | No
105 | MCIA_003_2016_Lake Michigan Grounding | Complete | 1- For "deep water vessels", the engineering department will provide an updated survey as and when its available. JSA to confirm that this has been done. An IIF action Alert will be drafted. 2- Site Manager / Safety Department will provide coaching to the Captain and will assist him in writing a JSA for general vessel navigation. | Sheldon Brooks | Ed Tiearney | Sheldon Brooks | Sam R Morrison, Ed Tiearney | 02/03/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
105 | MCIA_003_2016_Lake Michigan Grounding | Complete | JSA to include requesting the dredge crew to provide a safe passage to the dredge for when operating in a confined area | Ivan Urrutia | Ed Tiearney | Sheldon Brooks | Sam R Morrison, Ed Tiearney | 02/03/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Develop and implement daily & monthly crane inspection sheets based on OEM's recommendations for the DR 55. | Andrew Larkin | Christopher Gunsten | Andrew Larkin | Bill Baumann, Christopher Gunsten | 10/13/2017 | CA Incident Prevention Confirmed | High | Local Only, Mechanical | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Implement OEM annual audit on the DR 55. Items to be audited include NDT testing of shafts, inspection of brakes and drums, boom and turning circle inspection. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 04/19/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Replace emergency switch and associated wiring. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | High | Mechanical | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | OEM representative and electrical department to inspect the machine prior to resuming weight testing. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Standard job will be written to define procedure used for crane weight tests including inspections to be completed prior to test and a step by step detail of weights and booms angles to be tested. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 08/14/2017 | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Determine if additional spring releasing the digging brake is detrimental to the operation of the parking brake. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 02/03/2017 | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
108 | DR 55 - Load Drop | Complete | Develop a standard job for adjusting the parking brake using procedure supplied by OEM. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 04/19/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Design and install an auxiliary brake on the hoist drum. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 07/20/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Investigate and risk asses an automated dog system to insure the boom dog is engaged at all times when the boom is not changing angles. (est completion date 9/1/16) | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 09/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Create and input a standard job for a gear box shaft inspection procedure. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 09/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Analyze the failed gear box shaft to determine type/cause of failure. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 07/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Create and input a standard job for a gear box shaft inspection procedure. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 09/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
110 | Dredge 54 Boom Dropped | Complete | Investigate and risk assess an automated dog system to insure the boom dog is engaged at all times when the boom is not changing angles. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Andrew Larkin, Christopher Gunsten, Christopher Charron | 09/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
112 | MCIA_015_2016_UWP Knife Brook_CSD Carolina_161201 | Complete | 1- Review the specification for the Impellers with Oak Brook. | Mike Hungerford | Ed Tiearney | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 03/31/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
112 | MCIA_015_2016_UWP Knife Brook_CSD Carolina_161201 | Complete | 2- Review the knife design with the Oak Brook mechanical department for approval. | Mike Hungerford | Ed Tiearney | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 06/08/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
112 | MCIA_015_2016_UWP Knife Brook_CSD Carolina_161201 | Complete | 4- Project team to review site conditions and determine when the rock cages and/or deflector plates are needed. | Sheldon Brooks | Scott Baumann | Mike Hungerford | Sam R Morrison, Chris C Harris, Ed Tiearney | 06/28/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
114 | Booster Jack stern spud failure / drop | Complete | Design chocks as per those added during the repairs made. Update drawings to include chocks and weld details. | David B Coombs | Mark V Outten | Mark V Outten | David J Johanson |  | CA Incident Prevention Confirmed |  | Local Only | 100% complete | Yes | No
114 | Booster Jack stern spud failure / drop | Complete | Develop a PM plan for the jacking system to include standard jobs for periodic inspections, checks, and adjustments of the entire system. List each gearbox / motor assembly as a component of the spud. Items to be addressed in Standard Jobs: Oil analysis of gearboxes and hydraulic system Brake component inspection System pressure / relief valve check and adjustment Hydraulic hose replacement Lubrication of pinion and bushings | Sherif Abdelgafar | Bill Baumann | Mark V Outten | David J Johanson |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
114 | Booster Jack stern spud failure / drop | Complete | Review and update jacking procedure to include more details. Include safety concerns and instructions for closing watertight doors. Also address jacking down booster. Procedure should address the need for a JSA | Sherif Abdelgafar | Bill Baumann | Mark V Outten | David J Johanson | 04/30/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
114 | Booster Jack stern spud failure / drop | Complete | Develop a standard job for the installation of jacking gearbox and motor including all materials required (Bolts, washers, nuts, grease), torque specs, pinion engagement criteria, brake checks, lubrication, chock installation, etc. | Mark V Outten | Bill Baumann | Mark V Outten | David J Johanson | 05/31/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
116 | Dredge Illinois Stbd Main Engine Turbo Failure | Complete | review and edit pm plan for 20-645 EMD engines to include detailed turbo charger inspections and required turbo charger inspection findings (4K hours) | Terry Wright | Bill Baumann | Terry Wright | David J Johanson |  | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
116 | Dredge Illinois Stbd Main Engine Turbo Failure | Complete | Review the maintenance history of all 20 cy EMD turbo engine applications for life history both dredge pump and generator. | Terry Wright | Bill Baumann | Terry Wright | David J Johanson | 04/28/2017 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
117 | MCIA_001_2017_Stern Swivel Vertical Inlet Broke | Complete | Need to train lever-man on proper priming procedure | Barry Ashton | Ed Tiearney | Robert pierce | Bill Baumann, Sam R Morrison, Chris C Harris, Ed Tiearney | 02/28/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
117 | MCIA_001_2017_Stern Swivel Vertical Inlet Broke | Complete | Need to modify the system so that UWP can't be engaged while main pumps are running | Jacques Coetzee | Scott Baumann | Robert pierce | Bill Baumann, Sam R Morrison, Chris C Harris, Ed Tiearney | 04/03/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
120 | Equipment Damage - Boat Operator | Complete | Safety accountability and terminate letter to be issued to the boat operator due to negligence | Barry Ashton | Joseph Sadiq | Sheldon Brooks | Sam R Morrison, Chris C Harris, Ed Tiearney | 02/26/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
120 | Equipment Damage - Boat Operator | Complete | Coaching to be provided to all boat operators with respect to safe navigation around site, with emphasis being placed on the use of the technological aids on board, namely the survey positioning computer and the GPS tracker | Barry Ashton | Sheldon Brooks | Sheldon Brooks | Sam R Morrison, Chris C Harris, Ed Tiearney |  | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
122 | Crane 63 Boom Damage | Complete | Send out a notice to all Derrick Operators and Deck Captains that all loads need to be centered for a straight-up lifting. If the load is not centered Call An All Stop. | David Rappe | David J Johanson | Terry Wright | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 03/30/2017 | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
122 | Crane 63 Boom Damage | Complete | Create an Action Alert that instructs Derrick Operators and Deck Captains that pontoon tanks are only to be lifted using pad eyes that are designed for lifting or using a basket hitch to cradle the tank. Under no circumstances should the bits be used as lifting points as they are not designed for vertical stresses. | David Rappe | David J Johanson | Terry Wright | David Rappe, David J Johanson, Steven R Auernhamer, Dave Allen | 05/30/2017 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
123 | Subline tow - lost raft incident | Complete | Develop a standard rigging procedure for subline raft tows. | Dave Allen | David J Johanson | Dave Allen | David Rappe, David J Johanson, James C Gillespie | 11/20/2019 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Yard/Bull Gang | 100% complete | Yes | No
123 | Subline tow - lost raft incident | Complete | Complete engineering analysis of subline tow arrangement in order to complete procedure with accurate data. | Sean Raines | David B Coombs | Dave Allen | David Rappe, David J Johanson, James C Gillespie |  | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
124 | Columbia River Multi Beam Head Damage | Complete | Refrain from using a multibeam boat as a 24 hour crew boat. If a Multibeam boat is to be used as a 24 hour crew boat, only operators who are familiar with the multibeam system and how to protect it should be allowed to operate the boat. | Eugene Corey | Dave Allen | Eugene Corey | Washington Bryan, Chris Roberts, David Rappe, Mark L. Reid, Dave Allen |  | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
124 | Columbia River Multi Beam Head Damage | Complete | Discuss incident with the Captain and Tug Owner. | Eugene Corey | Chris Roberts | Eugene Corey | Washington Bryan, Chris Roberts, David Rappe, Mark L. Reid, Dave Allen |  | CA did not solve the problem | Low |  | 100% complete | Yes | No
125 | Dredge New York Boom Assist Mid Platform | Complete | Finalize standard methodology for changing boom assist wire and document in SOP. | Richard Millis | Jaclyn Abrams | Jaclyn Abrams | Andrew Larkin, Christopher Gunsten | 03/02/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
125 | Dredge New York Boom Assist Mid Platform | Complete | Update JSA as needed and review RAC Codes. | Richard Millis | Jaclyn Abrams | Jaclyn Abrams | Andrew Larkin, Christopher Gunsten | 03/15/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
125 | Dredge New York Boom Assist Mid Platform | Complete | Toolbox updated SOP & JSA with entire crew and distribute | Cecil Constanzi | Jaclyn Abrams | Jaclyn Abrams | Andrew Larkin, Christopher Gunsten | 03/11/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
128 | GL702 Headlog Repairs | Complete | Create detailed procedure for recording headlog measurements which will include required materials, wire installation instructions, drawings, data collection methodology and personnel required to be present. SOP to be included with future drydock specifications as an attachment. | Troy Booth | Christopher Gunsten | Christopher Gunsten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
128 | GL702 Headlog Repairs | Complete | Distribute SOP to Maintenance Managers, Mechanical Dredging Division Manager, Mechanical Dredging Division Dredge Manager, Fleet Maintenance Manager and SVP Plant and Equipment | Troy Booth | Christopher Gunsten | Christopher Gunsten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
128 | GL702 Headlog Repairs | Complete | Devise Quality Control checks and Quality Control reports for recording headlog measurements and incorporate into SOP for recording headlog measurements. | Troy Booth | Christopher Gunsten | Christopher Gunsten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
128 | GL702 Headlog Repairs | Complete | Devise Quality Assurance checks and Quality Assurance reports regarding headlog measurements and incorporate into SOP for recording headlog measurements. | Troy Booth | Christopher Gunsten | Christopher Gunsten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
132 | Buried Bulldozer | Complete | Create a Mob/Demob Best Practice Procedure for Fill Site and post to Bullseye-Project Management Folder. | William E Mitchell | Dave Allen | William E Mitchell | Chris Ameika, David J Johanson, James C Gillespie, Dave Allen | 06/10/2017 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
132 | Buried Bulldozer | Complete | Conduct Formal JSA Training with crew | Wade Smith | Dave Allen | William E Mitchell | Chris Ameika, David J Johanson, James C Gillespie, Dave Allen |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
132 | Buried Bulldozer | Complete | Create JSA for working without a spreader and distribute to all GLDD Fill Sites/Foreman. | James Ganus | William E Mitchell | William E Mitchell | Chris Ameika, David J Johanson, James C Gillespie, Dave Allen |  | CA Incident Prevention Confirmed | Medium | Yard/Bull Gang | 100% complete | Yes | No
132 | Buried Bulldozer | Complete | Review Fill Site Training Presentation. Post Presentation to Bullseye-Project Management Folder. | James Ganus | Chris Ameika | William E Mitchell | Chris Ameika, David J Johanson, James C Gillespie, Dave Allen |  | CA Incident Prevention Confirmed | Low | Company All | 100% complete | Yes | No
133 | DR 55 Tagline Motor | Complete | Install a temperature monitor circuit in all 4 tagline motors to alert the watch engineer to excessive temperatures. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten | 07/20/2017 | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
133 | DR 55 Tagline Motor | Complete | Establish a standard job detailing the procedure and QC process for installing a cooling fan and checking for proper rotational direction. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
133 | DR 55 Tagline Motor | Complete | Define test procedure for tagline motors upon repair and document this in NS5 as part of the motor repair standard job. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
133 | DR 55 Tagline Motor | Complete | Adjust the taps on the rotor circuit grid resistor to keep motor current and load to a minimum while still maintaining proper bucket control. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten | 05/01/2017 | CA Incident Prevention Confirmed | Low | Mechanical | 100% complete | Yes | No
133 | DR 55 Tagline Motor | Complete | Install stickers indicating the direction the fan is to rotate. | Alex Morris | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 07/06/2017 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
136 | DR 55 - Gusset Crack | Complete | Develop and implement daily & monthly crane inspection sheets based on OEM's recommendations on DR 55. | Andrew Larkin | Christopher Gunsten | Andrew Larkin | Bill Baumann, Christopher Gunsten | 10/13/2017 | CA Incident Prevention Confirmed | Medium | Local Only, Mechanical | 100% complete | Yes | No
137 | Unloader # 2 - CAT 398 Gasket | Complete | Inspect cooling system to determine if cooling pump needs to be replaced to match aftercooler flow specifications. | Kurt Hill | Andrew Larkin | Kurt Hill | Bill Baumann, Christopher Gunsten | 05/22/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
137 | Unloader # 2 - CAT 398 Gasket | Complete | Consult with Goulds pump regarding the manufacturer's recommendations regarding reducing the the flow to the pump to determine if current size pump is acceptable. If current size pump is acceptable install an orifice to limit the pressure to 15 psi in the cooling piping system. | Kurt Hill | Andrew Larkin | Kurt Hill | Bill Baumann, Christopher Gunsten | 08/16/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
138 | MCIA_003_2017_CSD Ohio_Cutter Motor # 2 Failure | Complete | Test run motors prior to installation | Jacques Coetzee | Sheldon Brooks | Jacques Coetzee | Sam R Morrison, Ed Tiearney |  | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
138 | MCIA_003_2017_CSD Ohio_Cutter Motor # 2 Failure | Complete | Re-insulate the lugs prior to each cutter motor installation and fabricate bottom plate non-conductive for the junction box | Jacques Coetzee | Sheldon Brooks | Jacques Coetzee | Sam R Morrison, Ed Tiearney | 05/09/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
138 | MCIA_003_2017_CSD Ohio_Cutter Motor # 2 Failure | Complete | QC checks from a GLDD representative to be done | Jacques Coetzee | Sheldon Brooks | Jacques Coetzee | Sam R Morrison, Ed Tiearney |  | CA Incident Prevention Confirmed | Medium | Int'l - Hopper | 100% complete | Yes | No
139 | MCIA_004_2017_Ohio_Cutter Motor # 6_Failure | Complete | Vendor to provide the coil specification and information when replacing armature windings | Jacques Coetzee | Ed Tiearney | Jacques Coetzee | Sam R Morrison, Ed Tiearney | 05/09/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
139 | MCIA_004_2017_Ohio_Cutter Motor # 6_Failure | Complete | Q.C checks to be done from GLDD representative | Jacques Coetzee | Sheldon Brooks | Jacques Coetzee | Sam R Morrison, Ed Tiearney |  | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
140 | CA Bucket 517 Puncturing a Hole in Scow Hull GL64 | Complete | Written Warning directed to operators to follow dig instructions and procedures | Phil Sanzone | Andrew Larkin | Rene V Fernandez | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 04/19/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
140 | CA Bucket 517 Puncturing a Hole in Scow Hull GL64 | Complete | Develop pre-job risk assessment for equipment damage due to bucket dig depth and scow draft | Rene V Fernandez | Steve W Lawrence | Rene V Fernandez | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 04/06/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
140 | CA Bucket 517 Puncturing a Hole in Scow Hull GL64 | Complete | Develop pre-job risk assessment for equipment damage due to bucket dig depth and scow draft | Rene V Fernandez | Steve W Lawrence | Rene V Fernandez | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 04/06/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
146 | Port Breast Winch Shaft Failure | Complete | Limit swing tonnage as not to exceed 75 tons while digging on the Xmas tree. | Robbie Baker | Eugene Corey | Eugene Corey | Mark V Outten, Andrew Gillie, David Rappe, Bill Baumann, Mark L. Reid, David J Johanson, Dave Allen | 05/03/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
149 | Radial Bearing Failure on Pump Shaft | Complete | A grease schematic and checklist needs to be implemented for confirming and verifying the Preventive Maintenance on the equipment | Bill Daisey | Christopher Charron | Chris Faught | Steven Lane | 05/02/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
149 | Radial Bearing Failure on Pump Shaft | Complete | new daily greasing check list should have a signature for both the watch engineer, and the Chief Engineer and/or Site Superintendent to sign for verification that the work is being completed correctly | Bill Daisey | Christopher Charron | Chris Faught | Steven Lane | 05/02/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
149 | Radial Bearing Failure on Pump Shaft | Complete | The engineer daily log inspection needs to have temperature readings on the log the same as the other machinery so that the watch engineer has a measurement to know when the bearing is bad | Bill Daisey | Christopher Charron | Chris Faught | Steven Lane |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
151 | R1244 Hydraulic Pump Failure | Complete | The engineers and site superintendent have been made aware to inspect all hydraulic pumps rotation by visually inspecting/checking the arrow rotation of the old pump and the new pump | Bill Daisey | Christopher Charron | Chris Faught | Russell F. Zimmerman, Steven Lane | 05/31/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
151 | R1244 Hydraulic Pump Failure | Complete | A new proportional relief valve was installed | Bill Daisey | Christopher Charron | Chris Faught | Russell F. Zimmerman, Steven Lane | 05/31/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
153 | Main Engine Failure | Complete | Engine was reworked to fix broken internal piston pins | Chris Faught | Christopher Charron | Chris Faught |  | 05/31/2017 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
154 | Unloader - Slurry Engine Fire | Complete | Inspect all fuel lines on the dredge for contact with other lines or any damage. | Kurt Hill | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 06/01/2017 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
154 | Unloader - Slurry Engine Fire | Complete | Modify 750 hour and 1,500 hour standard job to include further inspection of the high pressure fuel lines. Wording would will be similar to the following "Visually inspect all fuel injection lines for chaffing and proper bracing. Verify all high pressure fuel lines are covered in sheathing. Replace any damaged fuel lines. Install rackets / chaffing gear as required" | Kurt Hill | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
154 | Unloader - Slurry Engine Fire | Complete | Install protective sheathing on all single walled high pressure fuel lines on the Unloader. | Kurt Hill | Bill Baumann | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
155 | Unloader #2 - Electrical Failure | Complete | Move Toshiba Over-current Relay out of high voltage cabinet and install a sign to designate the switch should be on run not test. | Kurt Hill | Andrew Larkin | Kurt Hill | Bill Baumann, Christopher Gunsten | 09/29/2017 | CA Incident Prevention Confirmed |  | Local Only | 100% complete | Yes | No
155 | Unloader #2 - Electrical Failure | Complete | Label all PLC fuses with the proper size and model. | Chris Thorp | Andrew Larkin | Kurt Hill | Bill Baumann, Christopher Gunsten | 09/29/2017 | CA Incident Prevention Confirmed |  | Local Only | 100% complete | Yes | No
155 | Unloader #2 - Electrical Failure | Complete | Conduct an electrical training course. Include troubleshooting techniques as one of the class lessons. | Andrew Larkin | Bill Baumann | Kurt Hill | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
158 | Cutter Gear Box / Cutter Motor Noise | Complete | create a SJ for the overhaul of the cutter motors that includes a check list for fasteners and torque settings and QC/ QA details. SJ must have checkpoints for possible owners rep attendance. | Terry Wright | Bill Baumann | Terry Wright | David J Johanson |  | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
158 | Cutter Gear Box / Cutter Motor Noise | Complete | Have a meeting with Keystone (CR) to discuss the factors that led up to the fasteners not being installed and what steps can we implement to prevent this form happening in the future. | Terry Wright | Bill Baumann | Terry Wright | David J Johanson | 12/31/2017 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
158 | Cutter Gear Box / Cutter Motor Noise | Complete | Edit the 750 hour SJ for the cutter motors to include inspection of the brush rigging and mounting bolts. Include photos in the SJ of the correct installation with highlighted items of detailed inspections. | Terry Wright | Bill Baumann | Terry Wright | David J Johanson | 12/31/2017 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
161 | Liberty Island port main engine | Complete | If steel replacement is done under the engine, alignment will be checked and blots re-torqued prior to sailing. | Mike Kraljevic | Steven W Becker | Mike Kraljevic | Steven W Becker, Russell F. Zimmerman, Paul C Lamourie, James C Gillespie | 07/07/2017 | Not Started |  |  |  | No | No
161 | Liberty Island port main engine | Complete | Add a standard job in NS-5 to check the engine torque on bolts and foundation footing. | Jason Mixon | Mike Kraljevic | Mike Kraljevic | Steven W Becker, Russell F. Zimmerman, Paul C Lamourie, James C Gillespie | 07/07/2017 | Not Started |  |  |  | No | No
162 | MCIA_006_2017_CSD Ohio_ Cutter motor # 4 | Complete | QC checks procedure for Cutter Motor Inspection at the vendor facility to be implemented Company-wide | Jacques Coetzee | Brian Bickford | Jacques Coetzee | Manny Vianzon, Garrett Gibson, Ed Tiearney | 06/22/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
162 | MCIA_006_2017_CSD Ohio_ Cutter motor # 4 | Complete | QC checks procedure for Cutter Motor Inspection at the vendor facility to be implemented Company-wide | Jacques Coetzee | Brian Bickford | Jacques Coetzee | Manny Vianzon, Garrett Gibson, Ed Tiearney | 06/22/2017 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
167 | MCIA_007_2017_CSD Ohio_ Broken U.W.Pump Impeller | Complete | A debris / foreign object risk assessment to be included as part of the pre work planning. This risk assessment to be added to CSD Premobilization Checklist. | Sheldon Brooks | Manny Vianzon | Sheldon Brooks | Manny Vianzon, Garrett Gibson, Ed Tiearney | 06/15/2019 | Not Started | Medium | Int'l - Hydraulic | 100% complete | Yes | No
167 | MCIA_007_2017_CSD Ohio_ Broken U.W.Pump Impeller | Complete | Magnotometer survey to be performed prior to commencing dredging operations. Each ping should be analysed on a case by case basis and site management/engineering will determine which pings require further investigation. Diving inspection, clamshell etc... Note: A magnetometer will not be of any help in detecting non-ferrous metals. | Scott Baumann | Manny Vianzon | Sheldon Brooks | Manny Vianzon, Garrett Gibson, Ed Tiearney | 06/15/2019 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
171 | CRAB 3 Wheel Damage | Complete | Checking wheel studs is now included in the daily check of the CRAB. | Jesus Espinosa | Washington Bryan | Washington Bryan | Chris Roberts |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
171 | CRAB 3 Wheel Damage | Complete | Nyloc nuts with the correct bolt length were used so the operators could tell with a quick examination if the bolts had backed off. | Jesus Espinosa | Washington Bryan | Washington Bryan | Chris Roberts |  | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
173 | DR 55 Oil Cooler | Complete | Send oil cooler for testing to determine failure cause. | Brian Goetchius | Bill Baumann | Bill Baumann | Bill Baumann, Christopher Gunsten | 07/19/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
173 | DR 55 Oil Cooler | Complete | Distribute RAM Action alert to vessel management teams outlining the need for detailed written instructions for all tasks especially in the case of outside vendors. Alert to include some "what if" examples and guidelines for writing quality, detailed SR's and how to get them to the vendors. | Brian Goetchius | Bill Baumann | Bill Baumann | Bill Baumann, Christopher Gunsten | 10/16/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
173 | DR 55 Oil Cooler | Complete | Analyze purchase of a new oil cooler assembly based on oil cooler failure testing and TE analysis. | Andrew Larkin | Bill Baumann | Bill Baumann | Bill Baumann, Christopher Gunsten | 08/01/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
173 | DR 55 Oil Cooler | Complete | Standard job to complete monthly PH testing on coolant. | Brian Goetchius | Andrew Larkin | Bill Baumann | Bill Baumann, Christopher Gunsten | 11/22/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
178 | Memphis rental tow delay. | Complete | Split equipment into two tows | Chris Faught | Christopher Charron | Chris Faught | Chris Faught, Stan Ekren, Nathaniel C Woods, Steven Lane | 07/01/2017 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
180 | GL65 - Gasket Failure | Complete | Develop a standard job detailing the bolt torquing procedure including methods for visually identifying the bolts have been torqued properly. | Troy Booth | Bill Baumann | Troy Booth | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Low | Mechanical | 100% complete | Yes | No
182 | Liberty Island submerged pipeline sand plug | Complete | Increase frequency of hazard signage and verbal warring with a goal to keep the public greater than 50' from the shore pipe. | Bryan Johanson | Matt Ferrell | Matt Ferrell | Russell F. Zimmerman, Paul C Lamourie | 07/12/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
182 | Liberty Island submerged pipeline sand plug | Complete | Explore other locations in the borrow area with a goal to find material less likely to stand on a steep slope and cave in. | Dane Nelson | Matt Ferrell | Matt Ferrell | Russell F. Zimmerman, Paul C Lamourie | 07/09/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
182 | Liberty Island submerged pipeline sand plug | Complete | Review the Incident Alert with the entire site team focusing on site specific hazards related to each position. The message of discussions to be positive reinforcement of hazard awareness. | Roger Nichols | Armand F Riehl | Matt Ferrell | Russell F. Zimmerman, Paul C Lamourie | 09/15/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
182 | Liberty Island submerged pipeline sand plug | Complete | Redistribute, post and review Fill Site shutdown codes. (Red, Orange and Yellow) | Roger Nichols | Armand F Riehl | Matt Ferrell | Russell F. Zimmerman, Paul C Lamourie | 09/15/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
183 | GL 65 - Pennant Line Failure | Complete | Create a standard job for all bottom dumping scows to have the towing pennant wire changed on a yearly basis. | Troy Booth | Andrew Larkin | Andrew Larkin | Christopher Gunsten | 08/16/2017 | CA Incident Prevention Confirmed | Low | Mechanical | 100% complete | Yes | No
189 | Myrtle Beach 'Sink' Hose Failure | Complete | Request to Sr. Operations Manager that a proper handling procedure for float hoses be re-distributed to the fleet Deck Captains and Site Managers. If one is not in place, ask that one be written. | Joe Moon | James M Walker | Ed ODowd | James M Walker, David Rappe, Paul C Lamourie, Dave Allen | 05/27/2020 | CA Incident Prevention Confirmed | Medium | Local Only, Hydraulic, Rivers & Lakes, Hopper, Mechanical, Yard/Bull Gang, Int'l - Hopper, Int'l - Hydraulic | 100% complete | Yes | No
189 | Myrtle Beach 'Sink' Hose Failure | Complete | Provide Deck Captains Site Managers a proper inspection methodology and procedure. | James M Walker | David Rappe | Ed ODowd | James M Walker, David Rappe, Paul C Lamourie, Dave Allen | 12/17/2019 | CA Incident Prevention Confirmed | Low | Hydraulic, Hopper | 100% complete | Yes | No
189 | Myrtle Beach 'Sink' Hose Failure | Complete | Request that the Wear Group and Sr. Management research as to whether it makes sense to re-purpose float hoses into sink hoses and for what project purposes. | David Rappe | James M Walker | Ed ODowd | James M Walker, David Rappe, Paul C Lamourie, Dave Allen | 12/17/2019 | CA Incident Prevention Confirmed | Low | Hydraulic, Hopper | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Instruct the dredge crew on proper inventory maintenance (receiving parts, reconciliation, usage tab Etc.), & to use the inventory to find parts not by memory. | Brian Markey | Tim Riehl | Tim Riehl | David J Johanson | 09/06/2017 | CA Incident Prevention Confirmed |  | Hydraulic | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Create a policy for unplanned downtime including initial steps, chain of command, help network etc. | Brian Markey | Tim Riehl | Tim Riehl | David J Johanson | 05/09/2019 | Not Started | High | Local Only | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Create PM plan for the M/G set. | Brian Markey | Tim Riehl | Tim Riehl | David J Johanson |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Create plan for to be written jobs creation. | Bill Baumann | David J Johanson | Tim Riehl | David J Johanson | 09/22/2017 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical, Int'l - Hopper, Int'l - Hydraulic, Int'l - Mechanical | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Create a Ram note for WO to be written at or before time of repair. | Bill Baumann | David J Johanson | Tim Riehl | David J Johanson |  | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical, Int'l - Hopper, Int'l - Hydraulic, Int'l - Mechanical | 100% complete | Yes | No
190 | Alaska Swing Drive Issue | Complete | Create a basic trouble shooting guide that can be used for all systems. | Tim Riehl | Bill Baumann | Tim Riehl | David J Johanson | 09/29/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
191 | IL Swing Drive | Complete | Procure replacement boards and take the time with Bill English to pre-calibrate and label replacement boards. | Sam Radjenovich | Bill Baumann | Tim J Kremer | David Rappe, Bill Baumann, David J Johanson |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
191 | IL Swing Drive | Complete | Evaluate board design and determine if additional adhesive will aid in making more robust. | Sam Radjenovich | Bill Baumann | Tim J Kremer | David Rappe, Bill Baumann, David J Johanson |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
194 | DR 55 Load Drop | Complete | Add to the Standard Job of all critical components a QA/QC procedure to require the Captain or Chief to QC the job prior completing the standard job. Critical Jobs this will be done for are the brake adjustment on the Holder, Closer, Boom hoist and air compressor | Andrew Larkin | Christopher Gunsten | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 05/15/2019 | CA Incident Prevention Confirmed | High | Local Only |  | Yes | No
194 | DR 55 Load Drop | Complete | Developed a time based standard job for maintenance of air pots. Time frame to be calendar based. | Brian Goetchius | Bill Baumann | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
194 | DR 55 Load Drop | Complete | Develop a Standard Job for lubricating the air pots during periods of extended downtime or mobilization. | Brian Goetchius | Bill Baumann | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 11/14/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
194 | DR 55 Load Drop | Complete | Research and install a hydraulic unloader valve that can be locked. | Brian Goetchius | Andrew Larkin | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 10/02/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
194 | DR 55 Load Drop | Complete | Implement a test procedure for load testing the brake adjustments prior to resuming operations. | Brian Goetchius | Andrew Larkin | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 11/22/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
194 | DR 55 Load Drop | Complete | Install an audible alarm to alert of low air pressure prior to the machine shutting down. | Brian Goetchius | Andrew Larkin | Johan VanBladel | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten | 10/23/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
197 | DR 55 #2 Hoist Motor Failure | Complete | Create a standard job to be used for prepping for tow. Include requirement to cover all electrical motors and mg sets with tarps. | Andrew Larkin | Christopher Gunsten | Andrew Larkin | Bill Baumann, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only |  | Yes | No
197 | DR 55 #2 Hoist Motor Failure | Complete | Develop an electrical and visual inspection procedure for the dredge motors after the vessel is towed. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 11/16/2017 | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
200 | Booster Reggie Dropped | Complete | Establish a maintenance plan for jacking system bladders, grippers, air controls, and cylinders,. The plan shall identify each gripper, bladder, and cylinder as individual units in order to track life cycles. The retract and jacking cylinders shall be tracked as serialized items. The Plan will include inspection processes and intervals. | Sherif Abdelgafar | Bill Baumann | William Bradshaw | James M Walker, Bill Baumann, David J Johanson |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
200 | Booster Reggie Dropped | Complete | Bladders were not always sourced from a reputable dealer. With many bladders being patched or possibly used, new vendors should be sourced for a reliable bladder that can be purchases as needed. | Sherif Abdelgafar | Bill Baumann | William Bradshaw | James M Walker, Bill Baumann, David J Johanson | 11/28/2018 | CA Incident Prevention Confirmed | High |  | 100% complete | Yes | No
200 | Booster Reggie Dropped | Complete | Establish a means to track the life of the bladders in NS5. Identify each component individually so work orders can be attached for the given system and bladder life/gripper damage can be identified over time. | Craig Daly | Bill Baumann | William Bradshaw | James M Walker, Bill Baumann, David J Johanson |  | Testing Underway | High |  | 100% complete | Yes | No
200 | Booster Reggie Dropped | Complete | Write a standard job for jacking the booster up and down noting the system abilities and methodologies for operating the all 4 spuds simultaneously. | Craig Daly | Bill Baumann | William Bradshaw | James M Walker, Bill Baumann, David J Johanson |  | Testing Underway | Medium |  | 100% complete | Yes | No
206 | MCIA - Dare county cube set up leak | Complete | Post severe weather the horizontal position of the cube will be check and the anchors will be reset as soon as conditions allow. Include this in the severe weather plan as part of storm recovery. | Armand F Riehl | Jack Winn | Armand F Riehl | Russell F. Zimmerman, Dave Allen |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
207 | Crane Damage Cracked Boom | Complete | Replaced spud winched with new units and instructed operators to only utilize the new winches to lift the spuds. | Terry Wright | Christopher Charron | Kevin Holt | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 10/30/2017 | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
207 | Crane Damage Cracked Boom | Complete | Create an SOP for Lifting Barge Spuds with Crane. | Chris Faught | Christopher Charron | Kevin Holt | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 09/05/2018 | CA Incident Prevention Confirmed | Medium | Rivers & Lakes | 100% complete | Yes | No
209 | DR 54 Main Generator Failure | Complete | Fabricate and install improved generator foundation per engineering design. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, Christopher Gunsten | 04/16/2018 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
211 | GL 65 Grounding | Complete | Develop a project specific mooring procedure for securing scows which should be added to the Pre Mob Checklist to ask if the mooring plan is in place prior to starting a project. This mooring plan should detail the minimum requirements for tying up vessels. Specifically, the type of lines to be used, the method of wrapping the line and the number of lines to be used based on the type of vessel being secured. Rental tugs should be required to inform Great Lakes management immediately if they are unable to meet these requirements at any time during the contracted project. | Andrew Larkin | Christopher Gunsten | Matt Jack | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 03/14/2018 | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
211 | GL 65 Grounding | Complete | The SI severe weather plan should be revised to clearly define at what level of wind speed, in mph, the additional precautions stated in the plan should be implemented. | Stephan Brogna | Andrew Larkin | Matt Jack | Andrew Larkin, Steve O'Hara, Christopher Gunsten | 12/08/2017 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
214 | 22582_MCIA_009_CSD Carolina Cutter Motor No. 4 | Complete | Standard Job need to create for "Taking the addition insulation resistance measurements from the SCR room to determine if the insulation resistance is decreasing due to carbon build up. Do these tests when the dredge is shutdown for 2 hours or longer, by measuring the insulation resistance in the SCR room rather than at the motor also help to reduce the frequency of opening Cutter Canister. | Hector Gonzales | Joseph Sadiq | Jacques Coetzee | Manny Vianzon, Garrett Gibson | 12/16/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
214 | 22582_MCIA_009_CSD Carolina Cutter Motor No. 4 | Complete | Install additional cameras to verify the wear of the brushes by looking at the wear indicators without opening the canister. | Jacques Coetzee | Joseph Sadiq | Jacques Coetzee | Manny Vianzon, Garrett Gibson | 12/16/2017 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic | 100% complete | Yes | No
217 | Unloader 2, CAT 399 Failure | Complete | Update the alarms on all 399 engines to shutdown both the engine's in series automatically. | Sherif Abdelgafar | Bill Baumann | Wade Eldridge | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten |  | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
217 | Unloader 2, CAT 399 Failure | Complete | Investigate the ability to install new electronic governors. | Sherif Abdelgafar | Andrew Larkin | Wade Eldridge | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten |  | Not Started | High |  | Implementation Design Underway | Yes | No
217 | Unloader 2, CAT 399 Failure | Complete | Add 399 as a critical spare to Norfolk yard and maintain a minimum of 1 on hand and a maximum of 2. | Sherif Abdelgafar | Bill Baumann | Wade Eldridge | Andrew Larkin, Bill Baumann, Steve O'Hara, Christopher Gunsten |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
218 | Ohio River Engine Room Fire | Complete | The maintenance group to train the crew boat operators in how to take the cover of the impellor off, what to look for and how to determine the condition of the impellor. | Michael Brown | Brian C Puckett | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/21/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical | 100% complete | Yes | No
218 | Ohio River Engine Room Fire | Complete | Once the crew boat operators are trained to inspect the pump impellor, the maintenance department will determine which parts and how many parts the boat will need to have on hand to be able to perform these inspections | Michael Brown | Brian C Puckett | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/21/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical | 100% complete | Yes | No
218 | Ohio River Engine Room Fire | Complete | Maintenance Department to determine which boats do and do not have alarms on the raw water pumps for the exhaust. | Michael Brown | Brian C Puckett | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/21/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical | 100% complete | Yes | No
218 | Ohio River Engine Room Fire | Complete | Install an alarm to notify the operator that the pump is not working | Michael Brown | Brian C Puckett | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/21/2018 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
218 | Ohio River Engine Room Fire | Complete | Install heat sensors on the exhaust | Michael Brown | Brian C Puckett | Brian C Puckett | James M Walker, David Rappe, Bill Baumann, Steven R Auernhamer, Dave Allen | 11/21/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic, Hopper, Mechanical | 100% complete | Yes | No
221 | Dredge Liberty Automation Failure Incident | Complete | Upgrade the PLC to reduce risk of having automation failures. | Armand F Riehl | Mike Kraljevic | Armand F Riehl | Paul C Lamourie | 01/31/2022 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
225 | Alaska Cutter Motor Failure 12/21/2017 | Complete | Add the correct electrical grade sealant material (for sealing motor access points ) to the cutter motor installation Standard job - this is to address the fact that silicone was found to be a CF to this incident | Tim Riehl | Bill Baumann | Brian Markey | Steven W Becker, James C Gillespie | 09/10/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
225 | Alaska Cutter Motor Failure 12/21/2017 | Complete | Establish Standard jobs for cutter motors to cover 1. Inspection 2. Removal 3. Installation | Tim Riehl | Bill Baumann | Brian Markey | Steven W Becker, James C Gillespie | 09/10/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
225 | Alaska Cutter Motor Failure 12/21/2017 | Complete | Engine room personnel need to be properly trained on implementing the 3 standard jobs associated with cutter motor inspections / removals / installations. This should be part of an authorized and qualified process. | Tim Riehl | Bill Baumann | Brian Markey | Steven W Becker, James C Gillespie | 09/10/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
225 | Alaska Cutter Motor Failure 12/21/2017 | Complete | Create a standard work / service order for servicing cutter motors at outside shops - to include adjusting the brush neutral setting to remove amperage from the system. | Tim Riehl | Bill Baumann | Brian Markey | Steven W Becker, James C Gillespie | 09/10/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
229 | STBD Cutter Motor Failure | Complete | Add QC steps of inspection of the motor during reassembly and all cabling to include pictures. | Sam Radjenovich | Bill Baumann | Brian Markey | Steven W Becker, Bill Baumann, James C Gillespie | 11/20/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
233 | Noon Island_Generator Engine Overspeed_02252018 | Complete | Need to add physical means of stopping the engine, such as fuel pump manual shut off(back-up of existing solenoid), fuel shut off valve after secondary filters. | Alexanders Andrezens | Jose Gracia | Jose Gracia | Manny Vianzon |  | CA Incident Prevention Confirmed | High | Int'l - Hopper |  | Yes | No
233 | Noon Island_Generator Engine Overspeed_02252018 | Complete | Need to modify the present standard job for Engine testing interval from Quarterly to Monthly and review / add the checklist the testing procedure and parameters (Temperature, pressure, RPM). | Alexanders Andrezens | Jose Gracia | Jose Gracia | Manny Vianzon |  | CA Incident Prevention Confirmed | Medium | Int'l - Hopper | 100% complete | Yes | No
233 | Noon Island_Generator Engine Overspeed_02252018 | Complete | Need to modify the present standard job for Engine testing interval from Quarterly to Monthly and review / add the checklist with testing procedure and parameters. | Alexanders Andrezens | Jose Gracia | Jose Gracia | Manny Vianzon |  | CA Incident Prevention Confirmed | Medium | Int'l - Hopper |  | Yes | No
233 | Noon Island_Generator Engine Overspeed_02252018 | Complete | Need to compile Start-up procedure list with necessary pre-start checklist and emergency engine shutting down procedures. | Jacques Coetzee | Jose Gracia | Jose Gracia | Manny Vianzon |  | CA Incident Prevention Confirmed | Medium | Int'l - Hopper | 100% complete | Yes | No
235 | Broken Tail Shaft Coupling 2/1/2018 | Complete | Enter all tailshafts and couplings as serialized items in NS to track all repairs, installations, etc. | Tim Riehl | Bill Baumann | Lionell Caroon | Steven W Becker, Tim Riehl, Bill Baumann, James C Gillespie | 01/01/2019 | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
235 | Broken Tail Shaft Coupling 2/1/2018 | Complete | Edit standard job for tailshaft / coupling rebuilds to include a mag particle or dye test with photos of the test in the findings. | Tim Riehl | Bill Baumann | Lionell Caroon | Steven W Becker, Tim Riehl, Bill Baumann, James C Gillespie | 11/25/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
235 | Broken Tail Shaft Coupling 2/1/2018 | Complete | Create a standard job for cutter tailshaft / coupling installation based on the Technical Procedure we currently have. | Tim Riehl | Bill Baumann | Lionell Caroon | Steven W Becker, Tim Riehl, Bill Baumann, James C Gillespie | 10/31/2018 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
238 | Cutter Gearbox Bearing Failure | Complete | Engineer oil cooler for gearbox for shallow water digging. | Carl Pfeil | Bill Baumann | Mark V Outten | Steven W Becker, Bill Baumann | 02/15/2019 | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
238 | Cutter Gearbox Bearing Failure | Complete | Engineer / design seal assembly to eliminate water intrusion. | Carl Pfeil | Bill Baumann | Mark V Outten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
238 | Cutter Gearbox Bearing Failure | Complete | Updating all drawings using one specific mfg data. | Kurt Hill | Bill Baumann | Mark V Outten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
238 | Cutter Gearbox Bearing Failure | Complete | Add to reassembling procedures to take measurement of sleeve, bearing and flange spigot to confirm fits are the same as they were installed prior reassembling. | Mark V Outten | Kurt Hill | Mark V Outten | Steven W Becker, Bill Baumann | 07/15/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
238 | Cutter Gearbox Bearing Failure | Complete | Change the part hierarchy to reference OEM parts with no substitutions. | Kurt Hill | Bill Baumann | Mark V Outten | Steven W Becker, Bill Baumann |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
240 | DR 53 - Reactor Failure | Complete | Visually inspect other reactors for cracking or signs of damage due to vibration when dredge is not running. | chris slimmer | Andrew Larkin | Andrew Larkin | Chris Ameika, Bill Baumann, James C Gillespie, Steven R Auernhamer | 07/02/2018 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
240 | DR 53 - Reactor Failure | Complete | Evaluate the electrical systems on the DR 53 for obsolete components. | Sam Radjenovich | Andrew Larkin | Andrew Larkin | Chris Ameika, Bill Baumann, James C Gillespie, Steven R Auernhamer | 10/11/2018 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
242 | Padre Island Dredge Pump Coupling Failure | Complete | Write procedure for changing tolerance bands on newly installed equipment. | Giacomo Albanese | Mike Kraljevic | James M Walker | Paul C Lamourie |  | CA Incident Prevention Confirmed | Low | Local Only |  | No | No
243 | Dredge Carolina cutter gearbox failure May 2018 | Complete | Provide training and instruction to dredge leadership teams on the expectations of Standard job performance. Including findings, feedback on job requirements, etc.to all dredges in the RAM program. | Bill Baumann | James C Gillespie | Bill Baumann | Steven W Becker, Russell F. Zimmerman, David J Johanson, James C Gillespie | 10/15/2018 | CA Incident Prevention Confirmed | High | Hydraulic, Mechanical | 100% complete | Yes | No
243 | Dredge Carolina cutter gearbox failure May 2018 | Complete | Work with Total oil to provide a system to monitor sample due dates and provide reports on overdue samples. | Jose Gracia | Bill Baumann | Bill Baumann | Steven W Becker, Russell F. Zimmerman, David J Johanson, James C Gillespie | 08/31/2018 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
243 | Dredge Carolina cutter gearbox failure May 2018 | Complete | Create and implement a SJ audit program focused on crew performed, critical equipment inspections and condition based maintence jobs. | Bill Baumann | James C Gillespie | Bill Baumann | Steven W Becker, Russell F. Zimmerman, David J Johanson, James C Gillespie | 10/15/2018 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
243 | Dredge Carolina cutter gearbox failure May 2018 | Complete | Research and implement a method to install sensors in order to monitor and record oil and critical bearing temperatures | Kurt Hill | Bill Baumann | Bill Baumann | Steven W Becker, Russell F. Zimmerman, David J Johanson, James C Gillespie |  | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
244 | 22711_180413_Ohio_DC Contactor | Complete | Create a standard job for the Maintenance procedure on the DC contactor and control circuit. | Jacques Coetzee | Jose Gracia | Alexanders Andrezens | Manny Vianzon, Garrett Gibson | 05/28/2018 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic |  | Yes | No
244 | 22711_180413_Ohio_DC Contactor | Complete | Create a standard job for the Maintenance procedure on the DC contactor and control circuit. | Jacques Coetzee | Jose Gracia | Alexanders Andrezens | Manny Vianzon, Garrett Gibson | 05/28/2018 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
244 | 22711_180413_Ohio_DC Contactor | Complete | Shielding the contactor to prevent damages/injury of possible arc flash | Jacques Coetzee | Jose Gracia | Alexanders Andrezens | Manny Vianzon, Garrett Gibson |  | CA Incident Prevention Confirmed | High | Int'l - Hydraulic |  | Yes | No
244 | 22711_180413_Ohio_DC Contactor | Complete | Training on DC motor and contactor inspection and maintenance by DM+ | Jacques Coetzee | Jose Gracia | Alexanders Andrezens | Manny Vianzon, Garrett Gibson | 05/28/2018 | CA Incident Prevention Confirmed | High | Int'l - Hydraulic | 100% complete | Yes | No
244 | 22711_180413_Ohio_DC Contactor | Complete | Create a work order to replace the dresser coupling with SS flex type hose (this type is more flexible and will last long) | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Manny Vianzon, Garrett Gibson | 07/08/2018 | CA Incident Prevention Confirmed | Medium | Int'l - Hydraulic |  | Yes | No
246 | Dredge 53 Boom Hoist Gear Box Failure | Complete | Fabricate and install a wire mesh guard over the output shaft to allow for visual inspection of the shaft. | Wade Eldridge | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 06/12/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
246 | Dredge 53 Boom Hoist Gear Box Failure | Complete | Install collision blocks on side of bearing foundation to prevent movement. Also use nyloc nuts with witness marks to secure pillow block bearing. | Wade Eldridge | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 09/18/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
246 | Dredge 53 Boom Hoist Gear Box Failure | Complete | Create a standard job for inspecting gear box assembly and pillow block bearing on a time based increment. | Sherif Abdelgafar | Bill Baumann | Andrew Larkin | Bill Baumann, James C Gillespie |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
246 | Dredge 53 Boom Hoist Gear Box Failure | Complete | Provide information supporting the benefits of a record able camera system to all Mechanical Division dredges. | Andrew Larkin | Bill Baumann | Andrew Larkin | Bill Baumann, James C Gillespie |  | CA Incident Prevention Confirmed | Medium | Mechanical | 100% complete | Yes | No
248 | DR 55 - Hoist Generator #2 Breakdown | Complete | Revise megging standard job to include QC procedure for all connections that are disturbed during the megging process. | Alex Morris | Andrew Larkin | Brian Goetchius | Bill Baumann, James C Gillespie | 08/22/2018 | Not Started | Medium |  | 100% complete | Yes | No
253 | GL-10 Port Side Pin Connection Failure | Complete | Maintenance Manager for dredge to review Min/Max levels for pins and update as necessary | Kurt Hill | Bill Baumann | Mike Hungerford | Steven W Becker, David J Johanson, James C Gillespie |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
253 | GL-10 Port Side Pin Connection Failure | Complete | Develop a standard job or procedure for installing pins, sleeve, and end caps. Ensure that the correct materials are noted for install, i.e. bolts. | Kurt Hill | Bill Baumann | Mike Hungerford | Steven W Becker, David J Johanson, James C Gillespie |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
253 | GL-10 Port Side Pin Connection Failure | Complete | Review if GL-10 is needed to continue digging in Charleston during Season II | David J Johanson | Russell F. Zimmerman | Mike Hungerford | Steven W Becker, David J Johanson, James C Gillespie | 07/17/2019 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
254 | 20180702 LI PME Turbo Catastrophic Failure | Complete | None. | James M Walker | Jeremy Remme | James M Walker | Steven W Becker, Paul C Lamourie | 09/04/2019 | Testing Underway | Low |  | 100% complete | Yes | No
258 | Texas Broken Port Spud Winch | Complete | Engineer and requisition new winch | David J Johanson | James C Towner | James C Towner | Russell F. Zimmerman, David J Johanson, James C Gillespie | 06/01/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
259 | Cavalier State Grounding | Complete | remove tug capt. from project as he is deemed unsuitable, capt had already left the site. | Ed ODowd | Matt Ferrell | Matt Ferrell | Chris Roberts | 08/13/2018 | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
259 | Cavalier State Grounding | Complete | consult with all parties as to the planning and ensure all agree. | Ed ODowd | Matt Ferrell | Matt Ferrell | Chris Roberts | 08/17/2018 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
259 | Cavalier State Grounding | Complete | Ensure the tug Capt. has a alternate plan in event of sudden adverse weather. | Ed ODowd | Matt Ferrell | Matt Ferrell | Chris Roberts | 07/11/2022 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
261 | Booster 9 Generators | Complete | Routine inspection procedures for an unmanned vessel | Alexanders Andrezens | Jose Gracia | Jacques Coetzee | Manny Vianzon, Christopher Gunsten, Garrett Gibson |  | CA Incident Prevention Confirmed | High | Int'l - Hydraulic |  | Yes | No
261 | Booster 9 Generators | Complete | Purchase or fabricate container that will allow to protect generators for dust or moisture while not in operation. | Jacques Coetzee | Jose Gracia | Jacques Coetzee | Manny Vianzon, Christopher Gunsten, Garrett Gibson |  | CA Incident Prevention Confirmed | High | Int'l - Hydraulic |  | Yes | No
263 | DR 54 - Stbd Spud Gear Box Shaft Failure | Complete | Revise standard job to include internal inspection of gear assembly to document wear patterns and backlash. | Douglas Wittwer | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 01/22/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
263 | DR 54 - Stbd Spud Gear Box Shaft Failure | Complete | Inform site administrators of the requirement to ship oil samples immediately. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | Bill Baumann, James C Gillespie | 01/09/2019 | CA Incident Prevention Confirmed | High | Local Only |  | Yes | No
263 | DR 54 - Stbd Spud Gear Box Shaft Failure | Complete | Design and propose the install of a secondary brake in all spud systems. | Brian Goetchius | Bill Baumann | Brian Goetchius | Bill Baumann, James C Gillespie | 01/09/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
270 | AB 118 Damage | Complete | Have a JSA training session with the Bullgang | Adolfo Lopez | Jeremy Remme | Brian C Puckett | David Rappe, Steven R Auernhamer, Dave Allen | 12/01/2018 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
270 | AB 118 Damage | Complete | Have a training session with the Bullgang on JSA's and review the SALT section on JSA requirements. | Adolfo Lopez | Jeremy Remme | Brian C Puckett | David Rappe, Steven R Auernhamer, Dave Allen | 12/01/2018 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
270 | AB 118 Damage | Complete | Have a training session with the Bullgang on JSA's and review the SALT section on JSA requirements. | Adolfo Lopez | Jeremy Remme | Brian C Puckett | David Rappe, Steven R Auernhamer, Dave Allen | 12/01/2018 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
270 | AB 118 Damage | Complete | A JSA done for securing all of the equipment at the end of the day. | Charles Kelly | Jeremy Remme | Brian C Puckett | David Rappe, Steven R Auernhamer, Dave Allen | 11/15/2018 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
273 | Alaska anchor contact with hull | Complete | Prepare action alert for the fleet reviewing hazards of hanging anchors and moving the dredge. Including hazards such as: ground contact with the anchor, failed rigging, slack in the anchor wire. | Mike Gerlach | Tim J Kremer | Tim J Kremer | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie, Dave Allen | 02/15/2019 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
273 | Alaska anchor contact with hull | Complete | Updated instructions on the dredges to ensure if a phone call is received from the pilots that the dredge confirms via VHF that all parties are up to date. (call the other dredge and confirm) | Mike Gerlach | Tim J Kremer | Tim J Kremer | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie, Dave Allen | 02/15/2019 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
274 | Booster Jack Spud Foot / Hull/ and hose Damage | Complete | Addition to Booster placement JSA should be added to entail acknowledgement of hose positions during operation of spuds. | Shawn Boynton | Sherif Abdelgafar | Mathew Bishop | David Rappe, James C Gillespie, Dave Allen | 06/30/2019 | Not Started |  |  |  | No | No
274 | Booster Jack Spud Foot / Hull/ and hose Damage | Complete | Revised JSA to include additional step focused on hose locstion during entire evolution. |  |  | Mathew Bishop | David Rappe, James C Gillespie, Dave Allen |  | Not Started |  |  |  | No | No
278 | Dredge Carolina Suction Hose Failure | Complete | Write a standard job for removing / replacing hose and pipe under the ladder. Include instructions to not tighten up the flanges fully until the vitalic coupling connection is secured. | Scott Baumann | Mike Hungerford | Mike Hungerford | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie | 04/01/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
278 | Dredge Carolina Suction Hose Failure | Complete | Write a standard job for inspection of hose and pipe to include gauging the pipe and bands on the hose. | Scott Baumann | Mike Hungerford | Mike Hungerford | David Rappe, Bill Baumann, Lynn Nietfeld, James C Gillespie |  | CA Incident Prevention Confirmed | High |  | 100% complete | Yes | No
279 | DR 55 - Brake Band Actuator Foundation Failure | Complete | Add inspection of the air pot foundation to the annual OEM machine audit. | Thomas Lawrence | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 02/08/2019 | CA Incident Prevention Confirmed | Low | Mechanical | 100% complete | Yes | No
282 | DB 186 Hull/Deck Damage | Complete | Hold a meeting with crew about never tying barges steel to steel, no matter how long the barges are expected to be tied together | Mike Gerlach | David Rappe | Mike Gerlach | David Rappe, James C Gillespie, Dave Allen | 06/10/2019 | Not Started |  |  |  | No | No
282 | DB 186 Hull/Deck Damage | Complete | Oak Brook management to have a discussion with design engineers about adding fendering to all new barges moving forward | Mike Gerlach | David Rappe | Mike Gerlach | David Rappe, James C Gillespie, Dave Allen | 02/20/2019 | Not Started |  |  |  | No | No
283 | Apache Tower Damage | Complete | Update SMS Checklist for Tow to include a section to evaluate how a tandem tow is being prepared. | Christopher M Wire | Andrew Larkin | Andrew Larkin | Kyle Johnson, Bill Baumann, James C Gillespie |  | Not Started |  |  |  | No | No
283 | Apache Tower Damage | Complete | Create and distribute an IIF Bulletin detailing mooring lines can only be tied on proper deck fittings. | Chris Thorp | Andrew Larkin | Andrew Larkin | Kyle Johnson, Bill Baumann, James C Gillespie | 05/29/2019 | Not Started |  |  |  | No | No
283 | Apache Tower Damage | Complete | Update SMS Checklist for Tow to verify mooring lines are only tied to proper deck fittings. | Christopher M Wire | Andrew Larkin | Andrew Larkin | Kyle Johnson, Bill Baumann, James C Gillespie |  | CA Incident Prevention Confirmed | Low | Company All |  | No | No
286 | DR 53 - Bucket Drop | Complete | Implement a policy that the bucket is never to be left open when stopping that machine. Create a sign to be placed in all Mechanical Division dredges (53, 54, 55, 58) stating this policy. | Andrew Larkin | James C Gillespie | Andrew Larkin | Bill Baumann, James C Gillespie | 08/28/2019 | Testing Underway |  |  |  | Yes | No
286 | DR 53 - Bucket Drop | Complete | Assign maintenance manager of the 53, 54, 55 & 58 to review the maintenance procedure of air valves for holder, closer & boom hoist systems. Is maintenance of the valve covered adequately in current standard jobs. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 08/28/2019 | Not Started |  |  |  | No | No
286 | DR 53 - Bucket Drop | Complete | Create a functional description of the PLC logic for Dredge 53 operations. | Brian Goetchius | Brian Bickford | Andrew Larkin | Bill Baumann, James C Gillespie | 08/28/2019 | Not Started |  |  |  | No | No
286 | DR 53 - Bucket Drop | Complete | Change all brake setting valves to ASCO 1/2" 3 port valves with quick release valves. (holding, closing, boom hoist & swing brakes) Update drawings to note this change. | Benjamin Tuffias | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 08/28/2019 | Testing Underway | Critical |  |  | No | No
286 | DR 53 - Bucket Drop | Complete | Make the ASCO 1/2" 3 port valve a critical spare with a minimum inventory max of 4 and a min of 2. | Benjamin Tuffias | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie |  | Testing Underway | Critical |  |  | No | No
286 | DR 53 - Bucket Drop | Complete | Hold training on board the Dredge 53 with all crew members outlining that work on any critical lifting equipment (holder, closer, boom hoist) has to be authorized by the Captain or Chief prior to commencing the work. | Wade Eldridge | Gail Johnson | Andrew Larkin | Bill Baumann, James C Gillespie |  | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
290 | DBM STBD M/E Foundation Failure | Complete | New brackets were made in the USA and blessed by ABS. Plates were increased slightly in size because they were built from imperial sizes instead of the metric original. | Mike Kraljevic | Jeremy Remme | Mike Kraljevic | Steven W Becker, Paul C Lamourie | 07/04/2019 | Testing Underway | High |  | 100% complete | Yes | No
290 | DBM STBD M/E Foundation Failure | Complete | Failed brackets were sent to Metallurgical Technologies, INC P.A. to get a failure analysis performed. | Mike Kraljevic | Jeremy Remme | Mike Kraljevic | Steven W Becker, Paul C Lamourie | 09/03/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
290 | DBM STBD M/E Foundation Failure | Complete | MSI inspected gearbox, input bearing and internals all looked OK. New shaft to be ordered. | Mike Kraljevic | Jeremy Remme | Mike Kraljevic | Steven W Becker, Paul C Lamourie | 07/04/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
290 | DBM STBD M/E Foundation Failure | Complete | After re-alignment, initial readings were recorded and a tracking spreadsheet was created. A standard job is to be written to inspect the clearances and mount settings annually and document it in the tracking spreadsheet and attach to the Standard Job Work Order in NS5. | Mike Kraljevic | Jeremy Remme | Mike Kraljevic | Steven W Becker, Paul C Lamourie | 09/03/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
291 | Dredge 53 Fire | Complete | Elevate the accountability consequences for failure to follow and enforce company procedures with respect to hot work operations. | Armand F Riehl | James C Gillespie | Wade Eldridge | Bill Baumann, James C Gillespie, Christopher Charron, Jason Campbell | 05/29/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
291 | Dredge 53 Fire | Complete | Dredge 53 crew to receive training on SMS and hot work permit by site management or SSHO. | Rene V Fernandez | Armand F Riehl | Wade Eldridge | Bill Baumann, James C Gillespie, Christopher Charron, Jason Campbell | 05/01/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
291 | Dredge 53 Fire | Complete | Train dredge 53 crew using the Hot Work powerpoint and mentor them using the MCIA for this incident by management or SSHO. | Michael Jimenez | Armand F Riehl | Wade Eldridge | Bill Baumann, James C Gillespie, Christopher Charron, Jason Campbell | 05/01/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
291 | Dredge 53 Fire | Complete | Elevate the accountability consequences for failure to follow and enforce company procedures with respect to hot work operations. | Armand F Riehl | Andrew Larkin | Wade Eldridge | Bill Baumann, James C Gillespie, Christopher Charron, Jason Campbell | 10/02/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
293 | DR NY Main Engine PP1 Seal Failure | Complete | Create and distribute a RAM bulletin detailing how to prepare a engine for long term storage including freeze protection. | Brian Goetchius | Jose Gracia | Andrew Larkin | Bill Baumann |  | Not Started |  |  |  | No | No
293 | DR NY Main Engine PP1 Seal Failure | Complete | Create a standard job for maintenance of the main coupling based on the OEM published service manuals. Ensure all maintenance standard jobs for the coupling includes a step to verify the coupling type based on the p/n on the coupling. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
293 | DR NY Main Engine PP1 Seal Failure | Complete | Create a s/r template that includes a line item for preparing overhauled engines for long term storage. | Brian Goetchius | Bill Baumann | Andrew Larkin | Bill Baumann |  | CA Incident Prevention Confirmed | Low | Hydraulic, Mechanical | 100% complete | Yes | No
301 | Dredge New York A-frame Damage | Complete | Create a JSA for operating the A-frame to include testing operation of the limit switch and proximity switch to show they are both operational. Also include a statement that says the winch will not be operated if either of the limit switches are not working. Also install a sign on the winch controls stating the SOP for operating the winch includes testing the operation of both limit switches prior to use. | Richard Millis | Andrew Larkin | Jaclyn Abrams | Bill Baumann, Russell F. Zimmerman, James C Gillespie | 12/13/2019 | CA Incident Prevention Confirmed | Critical | Local Only | 100% complete | Yes | No
301 | Dredge New York A-frame Damage | Complete | Reinforce with project management team and vessel managers that employees reporting to work need to be fit for duty. Reinforce in Mechanical Fleet SLT and follow up with an email. | Brian Goetchius | Andrew Larkin | Jaclyn Abrams | Bill Baumann, Russell F. Zimmerman, James C Gillespie | 01/31/2020 | CA Incident Prevention Confirmed | High | Mechanical |  | Yes | No
301 | Dredge New York A-frame Damage | Complete | Develop an standard job to inspect the limit switch and the proximity switch to inspect the condition and operation of the limit switches. | Joseph Rye | Brian Goetchius | Jaclyn Abrams | Bill Baumann, Russell F. Zimmerman, James C Gillespie |  | Testing Underway | Medium |  | 100% complete | Yes | No
301 | Dredge New York A-frame Damage | Complete | Install a proximity sensor at A-frame stops. (redundant mechanical system) | Joseph Rye | Brian Goetchius | Jaclyn Abrams | Bill Baumann, Russell F. Zimmerman, James C Gillespie |  | CA Incident Prevention Confirmed | Medium |  | 100% complete | Yes | No
302 | 20190523 Ellis Island Hull Damage | Complete | Division Management to draft a Operational Guidelines document for Douglas Mackie/Ellis Island | James M Walker | James M Walker | James M Walker | George Strawn, Russell F. Zimmerman, Paul C Lamourie | 09/30/2019 | Not Started | Medium |  |  | No | No
302 | 20190523 Ellis Island Hull Damage | Complete | Division Management to draft a Operational Guidelines document for Douglas Mackie/Ellis Island | James M Walker | James M Walker | James M Walker | George Strawn, Russell F. Zimmerman, Paul C Lamourie | 09/30/2019 | Not Started | Medium |  |  | No | No
302 | 20190523 Ellis Island Hull Damage | Complete | Angle sensor to be moved to the top of the gimbal | Mike Kraljevic | James M Walker | James M Walker | George Strawn, Russell F. Zimmerman, Paul C Lamourie | 12/01/2019 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
308 | Dredge 54 - Boom Damage | Complete | Create a flyer detailing scow washing best practices and procedure. | Nick Callahan | Andrew Larkin | David Burlew | Andrew Larkin, Bill Baumann, Russell F. Zimmerman, James C Gillespie | 12/31/2019 | Not Started |  |  |  | No | No
308 | Dredge 54 - Boom Damage | Complete | Determine a product or method to reduce condensation. | David Burlew | Armand F Riehl | David Burlew | Andrew Larkin, Bill Baumann, Russell F. Zimmerman, James C Gillespie | 08/29/2019 | CA Incident Prevention Confirmed | Low | Local Only |  | Yes | No
311 | Calcasieu River Multibeam Head Damage | Complete | Aluminum bolts and nuts have been ordered for the new head connections. | Claire Bradford | Armand F Riehl | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 09/23/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
311 | Calcasieu River Multibeam Head Damage | Complete | The side mount will be reviewed with the subject matter experts and the survey team in Oakbrook. If decided this is necessary, the side mount can be installed at the next longer dry dock time period. | christopher Miller | Andrew Larkin | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 10/29/2020 | Not Started | Medium |  |  | No | No
311 | Calcasieu River Multibeam Head Damage | Complete | Operator will be given performance accountability and coaching on situational awareness. | Armand F Riehl | Dave Allen | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl |  | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
311 | Calcasieu River Multibeam Head Damage | Complete | Add that the depth sounder of the navigation will be the only part of the navigational system turned off to the JSA. | Claire Bradford | Armand F Riehl | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 08/24/2019 | CA Incident Prevention Confirmed | Low | Local Only |  | Yes | No
311 | Calcasieu River Multibeam Head Damage | Complete | Adding that the matrix only be loaded from the main Hypack screen to the JSA. During this time, the boat operator can turn the depth finder back on if not in the channel. | Claire Bradford | Armand F Riehl | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 08/24/2018 | CA Incident Prevention Confirmed | Low | Local Only | 100% complete | Yes | No
311 | Calcasieu River Multibeam Head Damage | Complete | Review SALT book and coach of the Captain/Engineers of the expectations to completing/running a survey. | Claire Bradford | Armand F Riehl | Christopher Latino | Chris Roberts, Russell F. Zimmerman, Armand F Riehl | 01/25/2020 | CA Incident Prevention Confirmed | Low | Local Only |  | Yes | No
314 | DR 58 - Boom Point Sheave Bearing Failure | Complete | Update boom point sheave drawing to include installation instructions and include in the SJ. | Sudhir Shroff | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 12/31/2019 | CA Incident Prevention Confirmed |  | Local Only | 100% complete | Yes | No
314 | DR 58 - Boom Point Sheave Bearing Failure | Complete | Develop and distribute a RAM note detailing the failure and the need to get subject matter experts involved in complex tasks. Step back and identify who the SME prior to completing a task and have them own the installation. | Brian Goetchius | Jose Gracia | Brian Goetchius | Bill Baumann, James C Gillespie | 12/31/2019 | Not Started |  |  |  | No | No
314 | DR 58 - Boom Point Sheave Bearing Failure | Complete | Create a SJ detailing the installation procedure for the boom point sheaves and bearings. | Douglas Wittwer | Brian Goetchius | Brian Goetchius | Bill Baumann, James C Gillespie | 12/31/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
316 | DR 54 - Broken Spud Adjustment Bolts | Complete | Include note in the Standard Job to tighten lower nut tight and verify this added to all wire adjustment standard jobs. | David Burlew | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 10/30/2019 | CA Incident Prevention Confirmed |  | Local Only | 100% complete | Yes | No
316 | DR 54 - Broken Spud Adjustment Bolts | Complete | Order and install the same wire guard on the DR 53 & 55. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 06/01/2020 | Not Started |  |  |  | No | No
316 | DR 54 - Broken Spud Adjustment Bolts | Complete | Design and install a wire guard that is opened end to allow the spud wire to be installed by the dredge crew. | Brian Goetchius | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 11/29/2019 | CA Incident Prevention Confirmed | High | Mechanical |  | Yes | No
316 | DR 54 - Broken Spud Adjustment Bolts | Complete | Incorporate the requirement that two hex nuts are installed on the load side of the adjustment bolt in the spud wire change standard job. | David Burlew | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 10/30/2019 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
319 | 191031 Ellis Bottom Dump Door #5 | Complete | Redesign and install new guide supports to make them stronger. | Mike Kraljevic | Jeremy Remme | Jeremy Remme | Steven W Becker, Paul C Lamourie | 11/07/2019 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
320 | DRG 58 #2 Swing pinion shaft bearing failure | Complete | Add greasing to the semi-annual swing gear box maintenance standard job. | Douglas Wittwer | Brian Goetchius | Brian Goetchius | James C Gillespie | 10/31/2020 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
320 | DRG 58 #2 Swing pinion shaft bearing failure | Complete | Cut a hole for the grease fitting and extend it through the cover. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | James C Gillespie |  | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
320 | DRG 58 #2 Swing pinion shaft bearing failure | Complete | Cut an inspection window and weld protective grating in. | Douglas Wittwer | Andrew Larkin | Brian Goetchius | James C Gillespie | 03/05/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
323 | Unloader 398 Failure | Complete | Performance accountability to be given to dredge management for lack of enforcement of JSA use on board. | Andrew Larkin | Harold E Valentine | Sherif Abdelgafar | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie |  | Not Started |  |  |  | Yes | No
323 | Unloader 398 Failure | Complete | Develop document detailing the different emergency shutdowns on the 398 and 399 engines. Documented training to be completed with all watch engineers and oilers on board. | Chris Thorp | Brian Goetchius | Sherif Abdelgafar | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie |  | Testing Underway | High |  |  | No | No
323 | Unloader 398 Failure | Complete | Maintenance Manager to distribute a memorandum prohibiting dredge crew from completing non routine maintenance tasks on the 398/399 engines. CAT Tech's will be brought out to complete all major services. | Benjamin Tuffias | Brian Goetchius | Sherif Abdelgafar | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie | 08/06/2020 | Testing Underway | High |  |  | No | No
324 | Dredge Illinois Fuel Spill | Complete | Accountability consequences should be assigned to the Supervisor (Watch Engineer) and crew member (Oiler) | Lanny Lawrence | Keith Pearse | Sherry Turner | Dave Allen | 10/06/2022 | Testing Underway |  |  |  | Yes | No
326 | Carolina Port Cutter Motor | Complete | Chief / First Assistant to document all work, including outside vendor service in NS. Find out if the Chief / 1st Assistant know how to manipulate documentation for Serialized parts (Cutter Motors) | DeVos Pieter | Jose Gracia | Kurt Hill | Steven W Becker, Bill Baumann, James C Gillespie, Steven R Auernhamer | 04/01/2020 | Not Started |  |  |  | No | No
326 | Carolina Port Cutter Motor | Complete | develop a plan to megger motors anytime the dredge sit idle for period of 24 hours or more. | Thomas Christenson | Jose Gracia | Kurt Hill | Steven W Becker, Bill Baumann, James C Gillespie, Steven R Auernhamer | 11/15/2021 | Not Started | High |  |  | No | No
327 | Alaska Christmas Tree Failure | Ready for Edits | Update existing drawings with better and more clear detail. Such as "100% weld penetration". | Thomas C Hoag | Tim Riehl | Tim Riehl | Bill Baumann, Russell F. Zimmerman, James C Gillespie | 11/30/2021 | Testing Underway | Medium |  | 100% complete | Yes | No
328 | DR 55 Fuel Spill | Complete | Install an audible and visual high level alarm to alert operator. | Cecil Constanzi | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 10/01/2020 | Not Started |  |  |  | No | No
328 | DR 55 Fuel Spill | Complete | Install a high level shutoff switch in the fuel tank. | Cecil Constanzi | Brian Goetchius | Andrew Larkin | Bill Baumann, James C Gillespie | 09/03/2020 | Not Started |  |  |  | No | No
328 | DR 55 Fuel Spill | Complete | Complete training with all Mechanical Fleet Captains & Chiefs on proper procedure for completing Oil record book. | Harold E Valentine | Andrew Larkin | Andrew Larkin | Bill Baumann, James C Gillespie | 10/01/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
329 | UWP Blown Out Seal Dredge Illinois | Complete | create a new standard job to include the proper procedure to not only change the existing filter but the newly installed secondary filter and proper valve opening and closing procedures | Craig Daly | Terry Wright | Terry Wright | David Rappe, Bill Baumann | 02/14/2020 | Not Started | High |  |  | No | No
331 | Carolina cutter tailshaft / coupling failure | Complete | Create a policy / procedure to vet any drawing going out for quotes or other actions | Thomas C Hoag | Steven W Becker | Bill Baumann | Steven W Becker, James C Gillespie |  | Testing Underway | High |  |  | No | No
331 | Carolina cutter tailshaft / coupling failure | Complete | Update drawings for the Carolina, Texas, and Ohio cutter tail shafts to show proper coupling to shaft fit and draw. Remove / archive all related drawings that contain inaccuracies. | Thomas C Hoag | Steven W Becker | Bill Baumann | Steven W Becker, James C Gillespie |  | CA Incident Prevention Confirmed | High | Office |  | No | No
331 | Carolina cutter tailshaft / coupling failure | Complete | Create a Standard Job for the installation of the cutter tail shaft. Include details for coupling / shaft fit, coupling draw, bolt torque, etc. Include required findings e.g. as measured final coupling draw, cutlass bearing clearance readings, radial bearing clearance readings, | Tim Riehl | Jose Gracia | Bill Baumann | Steven W Becker, James C Gillespie |  | CA Incident Prevention Confirmed | Low | Hydraulic |  | No | No
332 | Swing Motor Failure Dredge Illinois | Ready for Edits | All increase in swing radius shall be discussed with the captain and chief to ensure no undo stress is put on the associated swing assemblies. |  | Jose Gracia | Terry Wright | Bill Baumann, James C Gillespie |  | Not Started |  |  |  | No | No
336 | Dredge New York Generator Failure | Complete | Develop a standard job for installation of the boom assist generator and include megging prior to startup. | Joseph Rye | Brian Goetchius | Brian Goetchius | Brian Bickford, Paul C Lamourie | 07/31/2020 | Not Started |  |  |  | No | No
336 | Dredge New York Generator Failure | Complete | Evaluate the need to include high potential testing in the overhaul standard job of the boom assist generator. | Brian Goetchius | Brian Bickford | Brian Goetchius | Brian Bickford, Paul C Lamourie | 07/31/2020 | Not Started |  |  |  | No | No
345 | 20200510 Terrapin Island Hopper Open/Close Damage | Complete | Chief Engineer and EOT on board will install a "cut off switch" in the main console. This will cut power to the system automatically. | Mike Barron | James M Walker | James M Walker | Chris Roberts, Mark L. Reid | 07/01/2020 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
345 | 20200510 Terrapin Island Hopper Open/Close Damage | Complete | Chief Engineer and EOT will install an alarm when the ship opens to greater than 20 degrees. The procedure will then be for the dragtender to hit the "cut off switch" and disconnect power from the open/close system, which will stop the ship from opening further. | Mike Barron | James M Walker | James M Walker | Chris Roberts, Mark L. Reid | 07/01/2020 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
346 | Columbia River Main Engines Damage | Complete | Develop system in which fleet management can easily and frequently qc vessel logs and PMS Book | David Delp | Nathan Stevick | Nathan Stevick | Dave Allen | 06/12/2022 | CA Incident Prevention Confirmed |  | Hydraulic, Hopper | 100% complete | Yes | No
346 | Columbia River Main Engines Damage | Complete | Develop an on boarding process which provides training and hard copy resources to provide to operators in regards to all Maintenance SOPs and role specific responsibilities. | David Delp | Nathan Stevick | Nathan Stevick | Dave Allen | 06/12/2022 | CA Incident Prevention Confirmed | Medium | Hydraulic, Mechanical | 100% complete | Yes | No
346 | Columbia River Main Engines Damage | Complete | Clearly define in new SOP what maintenance activities vessel operators are responsible for and what they are not | David Delp | Nathan Stevick | Nathan Stevick | Dave Allen | 06/12/2022 | CA Incident Prevention Confirmed | Medium | Hydraulic, Mechanical | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Review all SJ's that involve assembly of the bearing (shop rebuild, Assembly installation, rotating element installation, 5,000 hour PM) and edit the same to include detailed steps that we have learned from past experience. These include; checking the anti-rotation pin clearance, thrust clearance and setting, loading springs install, bushing clearance checks, correct seal installation, housing alignment, housing dimensional checks, sealant, etc. | Alexanders Andrezens | Bill Baumann | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie |  | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Review current spare assemblies and correct / address any discrepancies from the current drawing. (Currently there is a spare being assembled at SPI, One at Progress Machine, and one in stock in Norfolk) | Kurt Hill | Bill Baumann | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 07/15/2020 | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Enter request in SmartSheet to perform a review of the current bearing vs functionality and research a better fitting option. What do the European dredging companies use? Could we incorporate two radial roller bearings and back to back tapered thrust bearings? | Bill Baumann | Thomas C Hoag | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie |  | CA Incident Prevention Confirmed | High | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Update all assembly procedures to address the possibility of bearing discrepancies. If the correct slot is not in the bearing it must be added as per drawing / description. | Alexanders Andrezens | Bill Baumann | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 07/15/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Develop a detailed SJ for commissioning of the cutter thrust bearing to be completed after all installations. Shall include operating parameters, test times, what checks are made and when, required findings, checklist, etc. | Alexanders Andrezens | Bill Baumann | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 07/15/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Update the part description to include specific details of; the anti-rotation slot (Depth, width, and slot not a hole), bearing shall have "three roller style" instead of the two rollers, roll pins , not screws holding the bearing cage together. | Bill Baumann | Kurt Hill | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 07/15/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
347 | Dredge Carolina Cutter Thrust Bearing Failure | Complete | Work with engineering to review all of the drawings for the Texas, Carolina, and Ohio Cutter Thrust bearing assembly and update / delete as needed to have only one current drawing. Should include slotted bearing, check housing pin hole dimensions, pin size, seals, bronze bushing diameter and retainers, etc. | Kurt Hill | Jose Gracia | Bill Baumann | Brian Bickford, Steven W Becker, James C Gillespie | 07/15/2020 | Not Started | Medium |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | SJ to be created and implemented for all installed equipment. Crew must be familirazid with NS5 system on how to use it and perfrom required tasks. Ensure that all communication methods such as internet connection, mail box and NS5 apps are properly configured and are operational. | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Brian Bickford | 09/15/2020 | Testing Underway |  |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Employment of proper crew such as asst. Chief or similar with good mechanical background and communication capabilities. | Sherif Abdelgafar | Jose Gracia | Alexanders Andrezens | Brian Bickford |  | Testing Underway | High |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Create standard procedures to all installed equipment. Review existing SJ's and SP's to see if any can be implemented for this particular vessel. | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Brian Bickford | 09/15/2020 | Testing Underway | Medium |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Crew to be instructed/coached by assigned Maintenance Superintendent on how to act in case of alarms and how to identify possible issues. Create check lists for on board crew for easy identification of possible issues and troubleshooting | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Brian Bickford | 09/15/2020 | Testing Underway | Medium |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Superseded By RC#1 Corrective Action: Employment of proper crew such as asst. Chief or similar with good mechanical background and communication capabilities. | Sherif Abdelgafar | Jose Gracia | Alexanders Andrezens | Brian Bickford | 06/30/2021 | CA Incident Prevention Confirmed | Medium | Local Only |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Checklist to be created that will reflect all necessary checks and inspections of installed equipment. Check list should reflect current project required equipment configuration such as use of multiple generators or gland seal pumps, automatic or manual flow/pressure control. | Sherif Abdelgafar | Jose Gracia | Alexanders Andrezens | Brian Bickford |  | Testing Underway | Medium |  |  | No | No
352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | Ready for Edits | Coaching on board crew on proper action in case of faulty condition. Making sure onboard crew is well instructed on how and to whom to report on all performed repairs or troubleshooting. Ensure that shift supervisors are relaying information to each other and keeping proper logging of the same. | Sherif Abdelgafar | Jose Gracia | Alexanders Andrezens | Brian Bickford | 06/30/2021 | CA Incident Prevention Confirmed | Low | Local Only |  | No | No
354 | Carolina Port Main pump drive coupling failure | Complete | Create standard job(s) for maintenance of the port and starboard main pump couplings. Including the one at the gearbox. | Dwight Davis | Jose Gracia | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie |  | Not Started | High |  |  | No | No
354 | Carolina Port Main pump drive coupling failure | Complete | Create standard job for pump bearing assembly overhaul including details of coupling inspection and requalification criteria. | Kurt Hill | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/30/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
354 | Carolina Port Main pump drive coupling failure | Complete | Serialize bearing assemblies and have each assembly with a hub, sleeve and protective cover. | Kurt Hill | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/23/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
354 | Carolina Port Main pump drive coupling failure | Complete | Hold a training session onboard or virtual with the supervisors addressing work assignments with an emphasis on assigning and authorizing a task leader that will be accountable for the successful outcome of the task. Include a discussion on using references and resources. | Bill Baumann | David Rappe | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 11/30/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic |  | No | No
354 | Carolina Port Main pump drive coupling failure | Complete | Request engineering to review design for Atra-flex type coupling to allow for total axial movement greater than the travel of the pump bearing assembly. | Bill Baumann | Thomas C Hoag | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/31/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
355 | Carolina UWPS coupling failure | Complete | Request engineering to review the coupling for replacement with a sliding coupling allowing axial adjustment greater than the total adjustment of the bearing foundation. | Bill Baumann | Thomas C Hoag | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/31/2020 | CA Incident Prevention Confirmed | High | Local Only | 100% complete | Yes | No
355 | Carolina UWPS coupling failure | Complete | Create a SJ for the installation of ladder pump bearing assembly including details for the impeller adjustment and coupling end play adjustment. | Kurt Hill | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/10/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
355 | Carolina UWPS coupling failure | Complete | Create a SJ for the set up / installation of the line shafts and couplings include details on; coupling assembly, end play, thrust buttons and plates and initial lubrication. | Kurt Hill | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/10/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
355 | Carolina UWPS coupling failure | Complete | Create a SJ for coupling maintenance. Shall include details on checking end play, thrust components, gear teeth, and lubrication. | Kurt Hill | Bill Baumann | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 07/10/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic | 100% complete | Yes | No
355 | Carolina UWPS coupling failure | Complete | Hold a training session with supervisors on the workflow of tasks and the need for detailed work orders. Specifically addressing growth work and when a new "related work" work order is required. | Bill Baumann | David Rappe | Kurt Hill | Brian Bickford, Steven W Becker, James C Gillespie | 11/30/2020 | CA Incident Prevention Confirmed | Medium | Hydraulic |  | No | No
358 | DR 53 Swing Gearbox Failure | Ready for Review | Evaluate and document the history of gearbox failures on the DR 53 and consult with engineering for permanent repair solutions. | Benjamin Tuffias | Brian Goetchius | Holt Hartung | Brian Bickford, Steven W Becker, James C Gillespie | 11/05/2020 | Not Started |  |  |  | No | No
358 | DR 53 Swing Gearbox Failure | Ready for Review | Review and update critical spare levels for both gearboxes and re-order all parts to correct levels. | Benjamin Tuffias | Brian Goetchius | Holt Hartung | Brian Bickford, Steven W Becker, James C Gillespie | 12/15/2020 | Not Started |  |  |  | No | No
358 | DR 53 Swing Gearbox Failure | Ready for Review | Establish a procedure to assign an SME prior to starting repairs through a pre-repair meeting in a RAM bulletin and designate that the SME will have ownership and ultimate authority over the repair and be responsible for documenting all QC requirements. | Brian Goetchius | Andrew Larkin | Holt Hartung | Brian Bickford, Steven W Becker, James C Gillespie | 11/05/2020 | Not Started |  |  |  | No | No
358 | DR 53 Swing Gearbox Failure | Ready for Review | Update gearbox drawings and NS hierarchy with correct measurements for both gearboxes. | Benjamin Tuffias | Brian Goetchius | Holt Hartung | Brian Bickford, Steven W Becker, James C Gillespie | 11/05/2020 | CA Incident Prevention Confirmed | High | Local Only |  | Yes | No
361 | Carolina Plugged Service water line | Ready for Edits | Replace pressure gauge on service water line with flow meter | Thomas Christenson | Tim Riehl | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie | 01/01/2021 | Not Started |  |  |  | No | No
361 | Carolina Plugged Service water line | Ready for Edits | Replace pressure switch on service water line with flow meter. Standard job to be created to check all shut down permissive switches. | Thomas Christenson | Tim Riehl | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie |  | Not Started |  |  |  | No | No
361 | Carolina Plugged Service water line | Ready for Edits | Install Check valve in service water line before hoses to the UWP | Tim Riehl | Scott Baumann | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie | 01/12/2022 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
361 | Carolina Plugged Service water line | Ready for Edits | Retraining of company policy and procedures for all Engine-room crew on board Dredge Carolina, stressing on proper JSA, and LOTO procedures | Thomas Christenson | Scott Baumann | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie | 08/23/2020 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
361 | Carolina Plugged Service water line | Ready for Edits | Retrain employees on the JSA requirements, Issue write up to task leader for not performing JSA prior to the task. | Thomas Christenson | Scott Baumann | Tim Riehl | Steven W Becker, Bill Baumann, James C Gillespie | 10/20/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
362 | Dr 54 - Holding Drum Brake | Ready for Edits | Install a single pin instead of two pins (allows visual and NDT testing of entire pin) | David Burlew | Brian Goetchius | Brian Goetchius | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie | 09/09/2020 | Not Started |  |  |  | No | No
362 | Dr 54 - Holding Drum Brake | Ready for Edits | Include cleaning and inspection of both live and dead end of brake bands in annual machine audit. | Alex Morris | Brian Goetchius | Brian Goetchius | Brian Bickford, Steven W Becker, Bill Baumann, James C Gillespie |  | Testing Underway | High |  |  | No | No
364 | 22694_Port Engine Gear Box Bearing Failure | Ready for Edits | Create appropriate SJ for unit inspection | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson | 01/23/2021 | Testing Underway | Medium |  |  | No | No
364 | 22694_Port Engine Gear Box Bearing Failure | Ready for Edits | Create appropriate SJ for unit inspection. Check if there are any already implemented SJ's on another Hopper Dredges | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson | 01/23/2021 | Testing Underway | Medium |  |  | No | No
364 | 22694_Port Engine Gear Box Bearing Failure | Ready for Edits | Implement early stage notification systems such as high temperature alarm. | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson | 01/23/2021 | Testing Underway | Medium |  |  | No | No
364 | 22694_Port Engine Gear Box Bearing Failure | Ready for Edits | Create detailed SJ with required measurements/readings to be taken during unit inspection. | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson | 01/23/2021 | Testing Underway | Medium |  |  | No | No
364 | 22694_Port Engine Gear Box Bearing Failure | Ready for Edits | SJ's and SP's to be implemented and utilized on daily basis | Alexanders Andrezens | Jose Gracia | Alexanders Andrezens | Jose Gracia, Christopher Gunsten, Garrett Gibson |  | Testing Underway | Medium |  |  | No | No
365 | Ohio Auxiliary Winch Damages | In Progress | Engineering and project Operation to review the vessel's limitations to weather conditions. | Sudhir Shroff | Kelly Briscoe | Jose Gracia | Brian Bickford, Steven W Becker, David Rappe, James C Gillespie | 10/10/2020 | Not Started |  |  |  | No | No
365 | Ohio Auxiliary Winch Damages | In Progress | Dredge captain and project manager to describe the operating conditions based on the wires broken and engineering to confirm possible upgrades. | Hector Gonzales | Sherif Abdelgafar | Jose Gracia | Brian Bickford, Steven W Becker, David Rappe, James C Gillespie | 10/10/2020 | Not Started |  |  |  | No | No
365 | Ohio Auxiliary Winch Damages | In Progress | Possible option to add wire potentiometers so that the levermen can see the actual line pull on all anchors. | Jacques Coetzee | DeVos Pieter | Jose Gracia | Brian Bickford, Steven W Becker, David Rappe, James C Gillespie |  | Not Started |  |  |  | No | No
368 | Alaska M/P Thrust Bearing Failure | Complete | Create SJ to inspect/clean the heat exchanger that will allow the crew to replace the Zinc anodes on a frequent basis. | Stephen Bugnaski | Tim Riehl | Jose Gracia | Brian Bickford, James C Gillespie | 09/09/2022 | Testing Underway | High |  | 100% complete | Yes | No
369 | Booster Jessie Starboard Gearbox Bearing Failure | Complete | Take coupling apart, inspect then reassemble after rear main thrust bearing has been moved. | Jose Gracia | Sherif Abdelgafar | Kurt Hill | Steven W Becker, David Rappe, James C Gillespie | 09/09/2022 | Not Started |  |  |  | No | No
369 | Booster Jessie Starboard Gearbox Bearing Failure | Complete | When putting back together ensure inserts a serviceable condition, replace if any cracks visible, lubricate, makes rue cover slide over coupling freely. | Jose Gracia | Sherif Abdelgafar | Kurt Hill | Steven W Becker, David Rappe, James C Gillespie | 09/09/2022 | Not Started |  |  |  | No | No
374 | Cape Girardeau Yard- Crane Boom Failure | Complete | Crane Operator will be required to attend NCCCO for re-training before operating another crane at GLDD. | Everett Reed | Christopher Charron | Christopher Charron | Steven Lane, Jason Campbell | 01/22/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 2. Replace the harnesses – at every second major overhaul (I.e. 60 to 80k hours) Add to Standard Job | Mike Kraljevic | Chris Roberts | Chris Roberts | James M Walker | 01/01/2022 | Not Started |  |  |  | No | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 6. Replace mature engine controls on 15 to 20 years Add to Standard Job – add to critical part (for year 12 review) | Mike Kraljevic | James M Walker | Chris Roberts | James M Walker | 01/01/2022 | Not Started |  |  |  | No | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 1. Schedule maintenance float before the environmental window, and two weeks after. | Mike Kraljevic | Chris Roberts | Chris Roberts | James M Walker | 10/15/2021 | CA did not solve the problem | Low |  |  | No | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 4. Modify / improve the new harness installation method with specific additional routing so that it is off the deck, and protected from weather / moisture | Mike Kraljevic | Chris Roberts | Chris Roberts | James M Walker | 11/05/2021 | Not Started | Low |  |  | No | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 5. Modify / improve the new harness installation method with specific additional routing so that it is off the deck, and protected from weather / moisture | Mike Kraljevic | James M Walker | Chris Roberts | James M Walker | 01/31/2022 | CA Incident Prevention Confirmed | Low | Local Only |  | No | No
375 | Liberty Is Uncommand Stops Gen + Main Eng | Ready for Edits | 3. Deploy CAT Technician after major overhaul on the project site for a time to QA check / once over in dredging operation | Chris Roberts | Mike Kraljevic | Chris Roberts | James M Walker | 11/16/2022 | CA did not solve the problem | Low |  |  | No | No
376 | Dredge Texas fuel tank vent plugs incident | Ready for Edits | Develop a policy / procedure to record the installation and removal of any temporary plugs, blanks, etc. | Steve Monson | Jose Gracia | Bill Baumann | Brian Bickford, James C Gillespie | 01/31/2021 | Not Started | Medium |  |  | No | No
376 | Dredge Texas fuel tank vent plugs incident | Ready for Edits | Develop a policy / procedure to address the closure of any tank top. To include a checklist of items such as plugs, vents, debris, tools, etc. The policy shall address the temporary closure of a tank and third party closures. | Steve Monson | Jose Gracia | Bill Baumann | Brian Bickford, James C Gillespie | 01/31/2021 | Not Started | Medium |  |  | No | No
378 | Terrapin Island-Deck Generator (Cat 3516) Failure | Complete | Have a new foundation engineered, procured and built. Ship and Install new foundation. Install original cat in the box that we own, check alignment in open and closed position, correct alignment, connect to vessel test run. Monitor loading. Periodically Check alignment condition to verify nothing has changed. | Mike Kraljevic | Chris Roberts | Chris Roberts | Mike Kraljevic, James M Walker, Chris Roberts | 10/15/2020 | CA Incident Prevention Confirmed | Low | Hopper | 100% complete | Yes | No
382 | GL 501 - Cylinder Failure | Ready for Review | Include in the cylinder overhaul standard job to NDT test all cylinder ears. | Brian Goetchius | Andrew Larkin | Brian Goetchius | Brian Bickford, Steven W Becker, James C Gillespie | 02/25/2021 | Not Started |  |  |  | No | No
382 | GL 501 - Cylinder Failure | Ready for Review | Include in the 5 year special survey dry docking specification to NDT test all cylinder ears on both the live and dead end of the cylinder. | Brian Goetchius | Andrew Larkin | Brian Goetchius | Brian Bickford, Steven W Becker, James C Gillespie | 02/25/2021 | Not Started |  |  |  | No | No
384 | Pass A'Loutre Survey | Complete | Write a technote regarding proper survey boat calibration techniques | Marlene Macron | William Bradshaw | William Bradshaw | David J Johanson, Christopher Gunsten, Garrett Gibson | 07/01/2021 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
384 | Pass A'Loutre Survey | Complete | Distribute technote to the engineering division. | Marlene Macron | William Bradshaw | William Bradshaw | David J Johanson, Christopher Gunsten, Garrett Gibson | 07/01/2021 | CA Incident Prevention Confirmed | Medium | Company All | 100% complete | Yes | No
386 | Scow 66 #1 Closing Cylinder Failure 210127 | In Progress | Preform Non-destructive testing for welds/padeyes at each drydock interval. | Brian Goetchius | Andrew Larkin | Robert Kelly | Andrew Larkin, Russell F. Zimmerman | 01/27/2022 | Not Started | Medium |  |  | No | No
389 | Crane Boom Failure | Complete | Crane operator must complete NCCCO certification for a Telescopic Boom Crane - Swing Cab (TLL) | Tim Cantwell | Christopher Charron | Chris Faught | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 09/30/2021 | CA Incident Prevention Confirmed | High | Rivers & Lakes | 100% complete | Yes | No
389 | Crane Boom Failure | Complete | A load indicator must be installed on the crane | Tim Cantwell | Christopher Charron | Chris Faught | Stan Ekren, Steven Lane, Christopher Charron, Jason Campbell | 07/05/2022 | CA Incident Prevention Confirmed | High | Rivers & Lakes | 100% complete | Yes | No
391 | Cutter Gear Box Input Shaft Bearing Failure | Complete | Limit the Cutter Motor RPM not to exceed the design specifications of the equipment | Scott Baumann | Dave Allen | Jose Gracia | Jose Gracia, Brian Bickford, Steven W Becker |  | Testing Underway | Medium |  |  | No | No
398 | GL10 Idler Barge | Ready for Review | Write a smart sheet for proper bearing assembly | Tim Riehl | Scott Baumann | Tim Riehl | Jose Gracia, Brian Bickford | 06/30/2021 | Not Started |  |  |  | No | No
398 | GL10 Idler Barge | Ready for Review | Write a smart sheet for proper bearing QC requirements | Tim Riehl | Scott Baumann | Tim Riehl | Jose Gracia, Brian Bickford | 06/30/2021 | Not Started |  |  |  | No | No
399 | Ellis Island Miss Dump | Complete | Draft change alarm added to Hopper Positioning. | Crystopher Barnett | Jeremy Remme | Crystopher Barnett | George Strawn, James M Walker, Chris Roberts, Garrett Gibson | 10/18/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
399 | Ellis Island Miss Dump | Complete | Discuss importance of not overriding alarms. Dragtenders to begin to keeping running log of outstanding VOSTA issues, including overrides. | Crystopher Barnett | Jeremy Remme | Crystopher Barnett | George Strawn, James M Walker, Chris Roberts, Garrett Gibson | 10/30/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
399 | Ellis Island Miss Dump | Complete | Pin bottom dump doors for dump runs for the rest of the MOBILE project | Crystopher Barnett | Jeremy Remme | Crystopher Barnett | George Strawn, James M Walker, Chris Roberts, Garrett Gibson | 10/18/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
401 | Liberty Island Main STBD Engine Turbo Failure | Complete | Ensure exhaust is clear of debris prior to install of turbos. | James M Walker | Chris Roberts | James M Walker | George Strawn, Mike Kraljevic, James M Walker, Chris Roberts | 05/10/2022 | Not Started | Low |  | 100% complete | Yes | No
405 | Pass A'Loutre GL 660 Dozer Sinking | Complete | Retrain all crew on the hazards of working in soft material | Mike Huebsch | William Bradshaw | William Bradshaw | David Rappe, Garrett Gibson, Dave Allen | 11/10/2021 | CA Incident Prevention Confirmed | High | Company All | 100% complete | Yes | No
405 | Pass A'Loutre GL 660 Dozer Sinking | Complete | Upgrade the equipment recovery plan to account for 20 ton snatch blocks with shackle type hooks | Mike Huebsch | William Bradshaw | William Bradshaw | David Rappe, Garrett Gibson, Dave Allen | 11/10/2021 | CA Incident Prevention Confirmed | Medium | Local Only | 100% complete | Yes | No
407 | Starboard Main Pump | Complete | Order new pressure sensors indictors | Thomas Christenson | Lupe Benavides | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl | 09/09/2022 | CA Incident Prevention Confirmed | High | Local Only |  | No | No
408 | Ladder Pump / Gear Box | In Progress | Use no less than 220 oil grade as per bearing manufacture | Thomas Christenson | Tim Riehl | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl |  | Not Started | Medium |  | 100% complete | Yes | No
409 | Main Pump Thrust Bearings Port side | In Progress | Member was written up for actions. | Gudalupe Benevides | Scott Baumann | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl |  | Testing Underway | Critical |  | 100% complete | Yes | No
409 | Main Pump Thrust Bearings Port side | In Progress | SOP was written for individuals for when they came on shift. | Thomas Christenson | Scott Baumann | Scott Baumann | Jose Gracia, Brian Bickford, Tim Riehl |  | Testing Underway | Critical |  | 100% complete | Yes | No
412 | Dredge Carolina MP Thrust Bearing Coupling | Complete | Not spending the time and money to broadcast the issue to make the decision. | Tim Riehl | Jose Gracia | Thomas Christenson | Jose Gracia, Brian Bickford, Steven W Becker |  | Testing Underway | Medium |  |  | No | No
419 | R032 Booster 3516 engine failure | In Progress | Insure adequate maintenance personnel are onsite during maintenance periods. | Eric Perez | Everett Reed | Terry Newberry |  |  | Not Started |  |  |  | No | No
419 | R032 Booster 3516 engine failure | In Progress | Adhere to the OEM recommended maintenance schedule. | Chad Bourg | Everett Reed | Terry Newberry |  |  | Not Started |  |  |  | No | No
419 | R032 Booster 3516 engine failure | In Progress | Adhere to the OEM recommended maintenance schedule. | Everett Reed |  | Terry Newberry |  |  | Not Started |  |  |  | No | No
419 | R032 Booster 3516 engine failure | In Progress | Suggest a different business model be instituted in accounting. | Everett Reed |  | Terry Newberry |  | 10/05/2022 | Not Started |  |  |  | No | No
425 | Ellis Island Overbow Elbow Failure | Complete | Review over the bow pipe design, Replace pipe with new pipe | Mike Kraljevic | David Dye | David Dye | George Strawn, Mike Kraljevic, James M Walker, Chris Roberts, David Rappe, Mark L. Reid, Dave Allen | 03/01/2022 | Not Started |  |  |  | Yes | No
432 | Dodge Island - Rudder Damage / Loss | Complete | Plan trailing to avoid the area. | Nicholas D Williams | Chris Roberts | Chris Roberts | Mike Kraljevic, James M Walker | 08/27/2021 | Not Started | High |  | 100% complete | Yes | No
436 | Ohio Plugged Subline | Complete | Need to coach the leverman on the proper procedure for when velocity drops down below minimum level. | Nick Yancy | Scott Baumann | Nick Yancy | Jose Gracia, David Rappe, David J Johanson, Scott Baumann, Dave Allen | 09/09/2022 | CA Incident Prevention Confirmed | Medium | Local Only |  | Yes | No
436 | Ohio Plugged Subline | Complete | Need to coach the Leverman on paying attention to dig pattern. | Nick Yancy | Scott Baumann | Nick Yancy | Jose Gracia, David Rappe, David J Johanson, Scott Baumann, Dave Allen | 09/09/2022 | CA Incident Prevention Confirmed | Medium | Local Only |  | Yes | No
436 | Ohio Plugged Subline | Complete | Coaching Leverman on being aware of what gauges are reading, and what to do when things don't look right. | Nick Yancy | Scott Baumann | Nick Yancy | Jose Gracia, David Rappe, David J Johanson, Scott Baumann, Dave Allen | 09/09/2022 | CA Incident Prevention Confirmed | Medium | Local Only |  | Yes | No

## Document (hidden)
Major Mech to view [Enter # from Data sheet column A]: | [5 empty] | 232 |  | Do not change cell dimensions, set to print on one page.
YEAR: | 2021 |  |  |  |  | HOURS: | 149.6619
DATE: | 2021-02-24 |  |  |  |  | CAT: | Cutter
VESSEL: | Illinois |  |  |  |  | SUBCAT: | Gear Box | Only enter data into blue shade block,
DIVISION: | Hydraulic |  |  |  |  | WO# | 4806414 | form will auto-populate from Data
MCIA # | 391
WO Title: | Replacement of Cutter gearbox HS input shaft bearings & HS Intermediate shaft bearings.
Notes from the Delay Log:
None | Gear Box | Gear Box | Gear Box | Gear Box | Gear Box | Gear Box | Gear Box
Work Order Notes / Findings:
No Findings entered
Contributing Factors: |  | Note: 0 indicates No Contributing Factors entered into Data sheet
0

## 2017 (hidden)
2017 Summary
Data Tab Ref | DREDGE | DATE | HRS | SYSTEM / SUBSYSTEM | WORK ORDER # | EDL Notes | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Status | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party
1 | Sugar Island | 2017-01-01 | 105.85 | Piping / Hoses / Deck Discharge Pipe | None | pipe broken | None
2 | Sugar Island | 2017-01-12 | 46.74 | Piping / Hoses / Hose Reel Repair | None | None | None
3 | Alaska | 2017-01-14 | 37.61 | Ladder Pump / Pump Leak | 4191620 | Ladder pump discharge elbow leak | None
4 | Illinois | 2017-02-03 | 69.24 | Main Pump / Engine/Motor | 4192535 | Turbo Stbd eng | None
5 | Illinois | 2017-02-18 | 291.83 | Cutter / Motor (Cutter Shaft) | 4192979 | None | None
6 | Alaska | 2017-03-11 | 649.58 | Other / Other | 1727123 | Cutter | None
7 | 54 | 2017-03-27 | 45.2 | Main / Aux. Generators / Main Generator Eng | 1699399 | None | None
8 | 55 | 2017-03-29 | 25.93 | Tagline / Tagline Winch | 4194401 | fire; burnt up | None
9 | 55 | 2017-03-30 | 33.52 | Crane Boom / Boom Winch | 4194405 | crack in fishplate of boom hoist support structure | None
10 | 55 | 2017-04-14 | 154.72 | Tagline / Tagline Winch | 4195045 | bucket falling; tagline motor burnt up | None
11 | Illinois | 2017-04-19 | 80.26 | Cutter / Gear Box (Cutter Shaft) | 4195518 | troubleshooting and disassembly | None
12 | Dodge Island | 2017-04-21 | 27.24 | Piping / Hoses / Pump Room Discharge Pipe | 4067460 / 4067458 | blew discharge piping in pumproom- dumping remainder of load 234 | None
13 | Illinois | 2017-04-23 | 150 | Cutter / Gear Box (Cutter Shaft) | 4195427 | reassembly | None
14 | Terrapin Island | 2017-04-24 | 62.51 | Other / Hopper | 1699368 | going inside to fix link on No. 7 hopper door | None
15 | 54 | 2017-05-02 | 46.92 | Spud System / Spud Structure | 1949226 | Stbd spud repairs | None
16 | Liberty Island | 2017-05-03 | 51.07 | Main Engine / Propulsion / Other | 0846068 | weakend strainer in lower engine room; off project | None
17 | Illinois | 2017-05-12 | 45.67 | Cutter / SCR Drive / MG Set | None | None | None
18 | Padre Island | 2017-05-15 | 65.64 | Other / Other Mechanical | 1987294 | inspecting tanks | None
19 | Texas | 2017-05-19 | 220 | Main Pump / Bearings/Shafts | 4196302 / 4196456 | replace bearings; rebuild main pump | None
20 | Terrapin Island | 2017-05-26 | 60.13 | Main Engine / Propulsion / Other | 4176910 | clutch | None
21 | Liberty Island | 2017-05-31 | 118.09 | Main Engine / Propulsion / Other | 4196753 | Port M/E vibration issues - to Lyons shipyard for repairs | None
22 | 55 | 2017-06-15 | 33.39 | Main / Aux. Generators / Main Generator Eng | 4197291 | Main eng oil cooler; fuel taken during down time | None
23 | Liberty Island | 2017-06-19 | 79.61 | Main Engine / Propulsion / Other | None | M/E malfunction | None
24 | 55 | 2017-07-08 | 48.26 | Spud System / Walking Mechanism | 4198364 | None | None
25 | Terrapin Island | 2017-07-11 | 38.22 | Dredge Pump / Impeller | 4177229 | impeller swap | None
26 | Alaska | 2017-07-12 | 70.06 | Main Pump / Pump rebuild | 1727700 | Pump Job - 36 hours | None
27 | Alaska | 2017-08-05 | 30.95 | Main Pump / Pump rebuild | 4201675 | pump job | None
28 | Illinois | 2017-08-17 | 27.24 | Swing System / Winch System | 4199603 | Swing winch drive not working | None
29 | Padre Island | 2017-08-31 | 98.99 | Dredge Pump Engine / Dredge Pump Engine | N/A | overheating | None
30 | 55 | 2017-09-08 | 58.02 | Main Hoist / Closer | 4200447 | hoist motor out | None
31 | Padre Island | 2017-09-17 | 46.57 | Piping / Hoses / Lower Drag Arm | 1987956 | sail to wilmington to replace broken lower port DA | None
32 | Alaska | 2017-09-19 | 110.73 | Main Pump / Pump rebuild | 1727560 | None | None
33 | 54 | 2017-10-21 | 55.33 | Main / Aux. Generators / Main Generator | 4201397 | standing by for main gen | None
34 | Alaska | 2017-11-02 | 77 | Main Pump / Pump rebuild | 1727498 | None | None
35 | 55 | 2017-11-06 | 26.31 | Buckets / Repair bucket | None | None | None
36 | Liberty Island | 2017-11-06 | 34.66 | Jet Pump / Pump Bearing | None | None | None
37 | Texas | 2017-11-06 | 73.08 | Main Pump / Pump rebuild | N/A | None | None
38 | Alaska | 2017-11-12 | 59.52 | Main Pump / Bearings/Shafts | 1703521 | Port Side | None
39 | Sugar Island | 2017-11-15 | 25.34 | Other / Other Mechanical | None | None | None
40 | Alaska | 2017-11-20 | 58.82 | Main Pump / Bearings/Shafts | 1727700 | overheating pedistal bearing | None
41 | Alaska | 2017-12-01 | 26.4 | Main Pump / Pump rebuild | 1727454 | front liner on main pump went bad; tow into Houma | None
42 | Alaska | 2017-12-15 | 144.79 | Cutter / Motor (Cutter Shaft) | 1727765 | None | None
43 | Alaska | 2017-12-28 | 30.79 | Generator / Main Generator Eng | 1704231 | main gen sparked flames, change 4 cutter teeth | None
44 | Sugar Island | 2017-12-29 | 36.31 | Other / Other Mechanical | 4063904 | lost compass heading; crack in bottom plate wing void | None
|  | Ed ODowd |  |  |  |  | 30 | Equipment Damage Survey Boat Hallets Point | 0 | 0 | Ed ODowd | 4 | 4 | Ed Tiearney
|  | Matt Ferrell |  |  |  |  | 31 | GL67 Boom Damage | 0 | 0 | Matt Ferrell | 2 | 2 | Matt Ferrell
|  | Manny Vianzon |  |  |  |  | 33 | MCIA 053 Dozer Sinking | 0 | 0 | Manny Vianzon | 4 | 3 | Bryan P Dast
|  | Armand F Riehl |  |  |  |  | 46 | MCIA 039 - Spider Barge Arm Break | 0 | 0 | Armand F Riehl
|  | Mike Hungerford |  |  |  |  | 64 | MCIA 005_2016 | 0 | 0 | James P Arias | 2 | 2 | Sheldon Brooks
|  | Dave Johanson |  |  |  |  | 71 | MCIA 001 - Crane Collision 72464 | 0 | 0 | Dave Johanson | 6 | 6 | David J Johanson
| Dredge-54 | Steve W Lawrence |  |  |  |  | 79 | Dredge 54 Boom Hoist - Philadelphia | 0 | 0 | Steve W Lawrence | 3 | 3 | Steve W Lawrence
| Padre Island | Paul C Lamourie |  |  |  |  | 81 | Padre Island dredge pump cleanout door failure | 0 | 0 | Paul C Lamourie | 2 | 2 | James M Walker
|  | Eugene Corey |  |  |  |  | 83 | FL MP Thrust Bearing Failure | 0 | 0 | Eugene Corey | 6 | 6 | Bill Baumann
| Ohio | Mike Hungerford |  |  |  |  | 95 | MCIA_012_2016_CSD Ohio Broken STBD Pump Shell | 0 | 0 | Rey Mart Taneo | 3 | 3 | Sheldon Brooks
|  | Stuart Hilgendorf |  |  |  |  | 99 | Derrick 65 - Bent Boom Chord and Lacing | 0 | 0 | Stuart Hilgendorf | 5 | 5 | Stuart Hilgendorf
|  | Rodney Fromenthal Jr. |  |  |  |  | 100 | MB1706 Derrick - Lifting Cube | 0 | 0 | Rodney Fromenthal Jr. | 3 | 0 | 0
|  | Sheldon Brooks |  |  |  |  | 105 | MCIA_003_2016_Lake Michigan Grounding | 0 | 0 | Joseph Sadiq | 2 | 2 | Ed Tiearney
| Dredge-55 | Andrew Larkin |  |  |  |  | 108 | DR 55 - Load Drop | 0 | 0 | Andrew Larkin | 7 | 7 | Christopher Gunsten
| Dredge-54 | Brian Goetchius |  |  |  |  | 110 | Dredge 54 Boom Dropped | 0 | 0 | Rene V Fernandez | 6 | 6 | Andrew Larkin
| Carolina | Mike Hungerford |  |  |  |  | 112 | MCIA_015_2016_UWP Knife Brook_CSD Carolina_161201 | 0 | 0 | Joseph Sadiq | 3 | 3 | Ed Tiearney
| Booster Jack | Mark V Outten |  |  |  |  | 114 | Booster Jack stern spud failure / drop | 0 | 0 | Bill Baumann | 4 | 4 | Mark V Outten
| Illinois | Terry Wright |  |  |  |  | 116 | Dredge Illinois Stbd Main Engine Turbo Failure | 0 | 0 | Terry Wright | 2 | 2 | Bill Baumann
|  | Robert pierce |  |  |  |  | 117 | MCIA_001_2017_Stern Swivel Vertical Inlet Broke | 0 | 0 | Joseph Sadiq | 2 | 2 | Ed Tiearney
|  | Sheldon Brooks |  |  |  |  | 120 | Equipment Damage - Boat Operator | 0 | 0 | James P Arias | 2 | 2 | Joseph Sadiq
|  | Terry Wright |  |  |  |  | 122 | Crane 63 Boom Damage | 0 | 0 | Brian C Puckett | 2 | 2 | David J Johanson
|  | Dave Allen |  |  |  |  | 123 | Subline tow - lost raft incident | 0 | 0 | Dave Allen | 2 | 2 | David J Johanson
| Columbia River | Eugene Corey |  |  |  |  | 124 | Columbia River Multi Beam Head Damage | 0 | 0 | Eugene Corey | 2 | 2 | Dave Allen
| New York | Jaclyn Abrams |  |  |  |  | 125 | Dredge New York Boom Assist Mid Platform | 0 | 0 | Jaclyn Abrams | 3 | 3 | Jaclyn Abrams
|  | Christopher Gunsten |  |  |  |  | 128 | GL702 Headlog Repairs | 0 | 0 | Christopher Gunsten | 4 | 4 | Christopher Gunsten
|  | William E Mitchell |  |  |  |  | 132 | Buried Bulldozer | 0 | 0 | William E Mitchell | 4 | 4 | Dave Allen
|  | Andrew Larkin |  |  |  |  | 133 | DR 55 Tagline Motor | 0 | 0 | Andrew Larkin | 5 | 5 | Bill Baumann
|  | Andrew Larkin |  |  |  |  | 136 | DR 55 - Gusset Crack | 0 | 0 | Andrew Larkin | 1 | 1 | Christopher Gunsten
|  | Kurt Hill |  |  |  |  | 137 | Unloader # 2 - CAT 398 Gasket | 0 | 0 | Andrew Larkin | 2 | 2 | Andrew Larkin
|  | Jacques Coetzee |  |  |  |  | 138 | MCIA_003_2017_CSD Ohio_Cutter Motor # 2 Failure | 0 | 0 | Joseph Sadiq | 3 | 3 | Sheldon Brooks
|  | Jacques Coetzee |  |  |  |  | 139 | MCIA_004_2017_Ohio_Cutter Motor # 6_Failure | 0 | 0 | Joseph Sadiq | 2 | 2 | Ed Tiearney
|  | Rene V Fernandez |  |  |  |  | 140 | CA Bucket 517 Puncturing a Hole in Scow Hull GL64 | 0 | 0 | Rene V Fernandez | 3 | 3 | Andrew Larkin
|  | Eugene Corey |  |  |  |  | 146 | Port Breast Winch Shaft Failure | 0 | 0 | Eugene Corey | 1 | 1 | Eugene Corey
|  | Chris Faught |  |  |  |  | 149 | Radial Bearing Failure on Pump Shaft | 0 | 0 | Chris Faught | 3 | 3 | Christopher Charron
|  | Chris Faught |  |  |  |  | 151 | R1244 Hydraulic Pump Failure | 0 | 0 | Chris Faught | 2 | 2 | Christopher Charron
|  | Chris Faught |  |  |  |  | 153 | Main Engine Failure | 0 | 0 | Garren Clegg | 1 | 1 | Christopher Charron
|  | Andrew Larkin |  |  |  |  | 154 | Unloader - Slurry Engine Fire | 0 | 0 | Andrew Larkin | 3 | 3 | Andrew Larkin
|  | Kurt Hill |  |  |  |  | 155 | Unloader #2 - Electrical Failure | 0 | 0 | Andrew Larkin | 3 | 3 | Andrew Larkin
|  | Terry Wright |  |  |  |  | 158 | Cutter Gear Box / Cutter Motor Noise | 0 | 0 | Terry Wright | 3 | 3 | Bill Baumann
|  | Mike Kraljevic |  |  |  |  | 161 | Liberty Island port main engine | 0 | 0 | Armand F Riehl | 2 | 0 | Steven W Becker
|  | Jacques Coetzee |  |  |  |  | 162 | MCIA_006_2017_CSD Ohio_ Cutter motor # 4 | 0 | 0 | Joseph Sadiq | 2 | 2 | Brian Bickford
|  | Sheldon Brooks |  |  |  |  | 167 | MCIA_007_2017_CSD Ohio_ Broken U.W.Pump Impeller | 0 | 0 | James P Arias | 2 | 2 | Manny Vianzon
|  | Washington Bryan |  |  |  |  | 171 | CRAB 3 Wheel Damage | 0 | 0 | Washington Bryan | 2 | 2 | Washington Bryan
|  | Bill Baumann |  |  |  |  | 173 | DR 55 Oil Cooler | 0 | 0 | Andrew Larkin | 4 | 4 | Bill Baumann
|  | Chris Faught |  |  |  |  | 178 | Memphis rental tow delay. | 0 | 0 | Robert Kelly | 1 | 1 | Christopher Charron
|  | Troy Booth |  |  |  |  | 180 | GL65 - Gasket Failure | 0 | 0 | Andrew Larkin | 1 | 1 | Bill Baumann
|  | Matt Ferrell |  |  |  |  | 182 | Liberty Island submerged pipeline sand plug | 0 | 0 | Armand F Riehl | 4 | 4 | Matt Ferrell
|  | Andrew Larkin |  |  |  |  | 183 | GL 65 - Pennant Line Failure | 0 | 0 | Andrew Larkin | 1 | 1 | Andrew Larkin
|  | Ed ODowd |  |  |  |  | 189 | Myrtle Beach 'Sink' Hose Failure | 0 | 0 | Chris Pomfret | 3 | 3 | James M Walker
|  | Tim Riehl |  |  |  |  | 190 | Alaska Swing Drive Issue | 0 | 0 | Tim Riehl | 6 | 6 | Tim Riehl
|  | Tim J Kremer |  |  |  |  | 191 | IL Swing Drive | 0 | 0 | Tim J Kremer | 2 | 2 | Bill Baumann
|  | Johan VanBladel |  |  |  |  | 194 | DR 55 Load Drop | 0 | 0 | Johan VanBladel | 6 | 6 | Christopher Gunsten
|  | Andrew Larkin |  |  |  |  | 197 | DR 55 #2 Hoist Motor Failure | 0 | 0 | Andrew Larkin | 2 | 2 | Christopher Gunsten
|  | William Bradshaw |  |  |  |  | 200 | Booster Reggie Dropped | 0 | 0 | William Bradshaw | 4 | 4 | Bill Baumann
|  | Armand F Riehl |  |  |  |  | 206 | MCIA - Dare county cube set up leak | 0 | 0 | Armand F Riehl | 1 | 1 | Jack Winn
|  | Kevin Holt |  |  |  |  | 207 | Crane Damage Cracked Boom | 0 | 0 | Robert Kelly | 2 | 2 | Christopher Charron
|  | Andrew Larkin |  |  |  |  | 209 | DR 54 Main Generator Failure | 0 | 0 | Andrew Larkin | 1 | 1 | Andrew Larkin
|  | Matt Jack |  |  |  |  | 211 | GL 65 Grounding | 0 | 0 | Michael Tester | 2 | 2 | Christopher Gunsten
|  | Jacques Coetzee |  |  |  |  | 214 | 22582_MCIA_009_CSD Carolina Cutter Motor No. 4 | 0 | 0 | James P Arias | 2 | 2 | Joseph Sadiq
|  | Wade Eldridge |  |  |  |  | 217 | Unloader 2, CAT 399 Failure | 0 | 0 | Matt Ferrell | 3 | 3 | Bill Baumann
|  | Brian C Puckett |  |  |  |  | 218 | Ohio River Engine Room Fire | 0 | 0 | Brian C Puckett | 5 | 5 | Brian C Puckett
|  | Armand F Riehl |  |  |  |  | 221 | Dredge Liberty Automation Failure Incident | 0 | 0 | Adolfo Lopez | 1 | 1 | Mike Kraljevic
|  | Brian Markey |  |  |  |  | 225 | Alaska Cutter Motor Failure 12/21/2017 | 0 | 0 | James C Towner | 4 | 4 | Bill Baumann
Formulas:
DATE = VLOOKUP([Data Tab Ref],Table1[['#]:[Date]],3,FALSE)

## 2018 (hidden)
2018 Summary
Data Tab Ref | DREDGE | DATE | HRS | SYSTEM / SUBSYSTEM | WORK ORDER # | EDL Notes | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Status | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party
45 | Terrapin Island | 2018-01-05 | 73.3 | Main Engine / Propulsion / Tail Shaft | 4178593 | Stbd M/E down due to leaking stern tube | None
46 | Alaska | 2018-01-11 | 84.71 | Main Pump / Pump rebuild | 1727803 | None | None
47 | Ellis Island | 2018-01-21 | 92.61 | Piping / Hoses / Pump Room Suction Pipe | N/A | Stbd slope tank flooded 15 feet of water in tank vessel at anchor ocsw | None
48 | Ellis Island | 2018-01-31 | 40.39 | Main Engine / Propulsion / Gearbox | N/A | None | None
49 | Alaska | 2018-02-01 | 86.73 | Cutter / Bearings/Shafts | 1727880 | None | None
50 | Ellis Island | 2018-02-02 | 421.95 | Main Engine / Propulsion / Gearbox | N/A | high speed aft clutch bearing failure | None
51 | Illinois | 2018-02-07 | 60.76 | Main Pump / Engine/Motor | 4204577 | Main Engine | None
52 | Dodge Island | 2018-02-09 | 35.88 | Dredge Pump / Other | 4068750 | Stbd dredge pump repairs | None
53 | Alaska | 2018-02-11 | 91.93 | Cutter / Motor (Cutter Shaft) | 1727914 | wash out to check cutter motor | None
54 | Alaska | 2018-02-16 | 65.62 | Cutter / Motor (Cutter Shaft) | 1727917 | None | None
55 | Alaska | 2018-02-23 | 67.8 | Main Pump / Pump rebuild | 1727908 | None | None
56 | Liberty Island | 2018-02-23 | 40 | Jet Pump / Other | 0847436 | repairs to jet pump pipe and stern tubes while at dock | None
57 | Liberty Island | 2018-02-26 | 72.89 | Generator Engine / Other | 0847488 | Generator not operating in safe parameters, since initial failure; many electronic systems have shown to be potenially compromised with mulitple fuses failing and vital systems not operating consistently | None
58 | Ellis Island | 2018-03-04 | 43.89 | Other / Electrical | N/A | Multidrive malfunction | None
59 | Illinois | 2018-03-05 | 24.01 | Spuds / Xmas Tree / Wires | N/A | Stern | None
60 | Alaska | 2018-03-23 | 25.63 | Main Pump / Pump rebuild | 1728032 | None | None
61 | Ellis Island | 2018-03-25 | 123.37 | Bow Thruster Engine / Other | N/A | bow thruster 1 down | None
62 | Carolina | 2018-04-02 | 91.61 | Main Pump / Bearings/Shafts | 4206218 | None | None
63 | 53 | 2018-04-03 | 29.52 | Main / Aux. Generators / Main Generator | 4206415 | None | 246 | Dredge 53 Boom Hoist Gear Box Failure | 0 | 0 | Michael Jimenez | 4 | 4 | Andrew Larkin
64 | Ellis Island | 2018-04-11 | 35.4 | Dredge Pump / Clutch | N/A | None | None
65 | Alaska | 2018-04-17 | 46.52 | Suction / Discharge Pipe / Dredge Pipeline | 1706604 | broken spool piece on Vosta | None
66 | 53 | 2018-04-21 | 59.1 | Electrical/Electronics / PLC | 4206760 | Holding brake wont release | 240 | DR 53 - Reactor Failure | 0 | 0 | Andrew Larkin | 2 | 2 | Andrew Larkin
67 | Padre Island | 2018-04-30 | 83.43 | Dredge Pump / Pump Bearing Assembly | 1988925 | line shaft bearing coupling | 242 | Padre Island Dredge Pump Coupling Failure | 0 | 0 | James M Walker | 1 | 0 | Mike Kraljevic
68 | Ellis Island | 2018-05-01 | 75.89 | Generator Engine / Other | N/A | None | None
69 | Carolina | 2018-05-02 | 514.2 | Cutter / Gear Box (Cutter Shaft) | 4038139 | None | 243 | Dredge Carolina cutter gearbox failure May 2018 | 0 | 0 | Bill Baumann | 4 | 4 | James C Gillespie
70 | 53 | 2018-05-17 | 401.61 | Crane Boom / Boom / Gantry Structure | 4207327 | Boom Collapse | None
71 | Padre Island | 2018-05-21 | 34.46 | Dredge Pump / Pump Bearing Assembly | 1989070 | None | None
72 | Liberty Island | 2018-05-22 | 532.27 | Main Engine / Propulsion / Propeller | None | None | None
73 | Terrapin Island | 2018-05-31 | 163.67 | Other / Other Mechanical | 1708024 | inbound for trunnion repairs at Lyons Shipyard | None
74 | 55 | 2018-06-01 | 54.42 | Electrical/Electronics / PLC | 1708167 | electrical problem | 248 | DR 55 - Hoist Generator #2 Breakdown | 0 | 0 | Andrew Larkin | 1 | 1 | Andrew Larkin
75 | Texas | 2018-06-01 | 77.31 | Idler / Spud Barge / 177 | None | None | None
76 | Terrapin Island | 2018-06-11 | 94.77 | Trunnion Hoist / Other | 1708024 | inbound for repairs | None
77 | Padre Island | 2018-06-21 | 46.07 | Dredge Pump / Other | 1989237 | coupling | None
78 | Liberty Island | 2018-07-02 | 99.47 | Main Engine / Propulsion / Other | N/A | engine shutdown on code red, turbo | 254 | 20180702 LI PME Turbo Catastrophic Failure | 0 | 0 | Jeremy Remme | 1 | 1 | Jeremy Remme
79 | Carolina | 2018-07-03 | 116.52 | Idler / Spud Barge / GL-10 | None | port connection pin | 253 | GL-10 Port Side Pin Connection Failure | 0 | 0 | Mike Hungerford | 3 | 3 | Bill Baumann
80 | Texas | 2018-07-05 | 42.2 | Spuds / Xmas Tree / Winch / Hoist System | 0791116 | spud winches won't start | None
81 | Ellis Island | 2018-07-08 | 135.95 | Other / Electrical | N/A | to anchor to assess INGETEAM system failure | None
82 | Liberty Island | 2018-07-10 | 47.98 | Main Engine / Propulsion / Other | 0848100 | pump out at reduced RPM and reduced density; port M/E turbo overheating | None
83 | Carolina | 2018-07-11 | 101.51 | Ladder Pump / Gearbox (Ladder Pump) | 4038173 | Gear box cooling system not working | None
84 | Ellis Island | 2018-07-28 | 379.92 | Other / Other Mechanical | N/A | Secure from dredge operations in preparation for yard period | None
85 | Illinois | 2018-07-29 | 114.9 | Ladder Pump / Motor / Engine | 0309370 | trip off; oil seal blew out; underway to rockaway 1413; arr 1645 | None
86 | Liberty Island | 2018-08-07 | 70.89 | Main Engine / Propulsion / Other | 0848286 | Oil in cooling water | None
87 | Carolina | 2018-08-08 | 55.68 | Cutter / Motor (Cutter Shaft) | 4038240 | change out port blower | None
88 | Texas | 2018-08-11 | 137.87 | Spuds / Xmas Tree / Winch / Hoist System | 0791277 | busted port breast winch | 258 | Texas Broken Port Spud Winch | 0 | 0 | James C Towner | 1 | 1 | James C Towner
89 | Carolina | 2018-08-12 | 63.5 | Cutter / Motor (Cutter Shaft) | 4038342 | replace cutter motor | None
90 | Carolina | 2018-08-17 | 38.5 | Spuds / Xmas Tree / Walking Spud | 4209697 | weld crack in GL-10 spud | None
91 | Padre Island | 2018-08-17 | 31 | Generator Engine / Other | 1989653 | Generator Timing issue | None
92 | Illinois | 2018-08-19 | 94.92 | Cutter / Gear Box (Cutter Shaft) | 4209827 | underway 1622; anchor 2011 | None
93 | Carolina | 2018-08-24 | 48.2 | Idler / Spud Barge / GL-10 | 4038551 | Spud roller | None
94 | Illinois | 2018-08-30 | 420.29 | Main Pump / Engine/Motor | 4210011 / 0309395 | None | None
95 | Padre Island | 2018-09-06 | 24.91 | Piping / Hoses / Lower Drag Arm | 1989760 | None | None
96 | 54 | 2018-09-15 | 123.72 | Spud System / Spud Structure | 4210372 | broken gear box | 263 | DR 54 - Stbd Spud Gear Box Shaft Failure | 0 | 0 | Andrew Larkin | 3 | 3 | Brian Goetchius
97 | Illinois | 2018-09-22 | 84.87 | Swing System / Winch System | 0309411 | None | None
98 | Texas | 2018-09-26 | 53.9 | Ladder Pump / Pump Leak | 0791412 | Replace rubber hose behind UWP | None
99 | Illinois | 2018-10-16 | 179.52 | Suction / Discharge Pipe / Dredge Pipeline | 4211146 | None | None
100 | Terrapin Island | 2018-10-17 | 224.43 | Main Engine / Propulsion / Other | 4180731 | None | None
101 | Ellis Island | 2018-10-20 | 45.89 | Dredge Pump / Other | N/A | dredge pumps clutch out during pump out | None
102 | Alaska | 2018-10-22 | 46.13 | Generators / Main Generator | 4211171 | ECM Main Gen | None
103 | Illinois | 2018-10-24 | 36.62 | Ladder / Ladder Winch | 0309443 | Ladder hoist computer | None
104 | Alaska | 2018-10-27 | 122.54 | Suction / Discharge Pipe / Dredge Pipeline | 1728360 | None | 235 | Broken Tail Shaft Coupling 2/1/2018 | 0 | 0 | James C Towner | 3 | 3 | Bill Baumann
105 | Dodge Island | 2018-10-29 | 116.77 | Dredge Pump Engine / Gearbox | 4069836 | None | None
106 | Liberty Island | 2018-11-05 | 72.99 | Other / Electrical | N/A | automation reset to correct skimmer issues | None
107 | Ellis Island | 2018-11-07 | 73.54 | Dredge Pump / Impeller | N/A | replace impeller with 80 inch trimmed impeller | None
108 | Carolina | 2018-12-12 | 36.52 | Ladder Pump / Bearings/Shafts | 4038336 | change 20 cutter teeth | None
109 | Terrapin Island | 2018-12-27 | 29.84 | Other / Hopper | 4180999 | No. 6 bottom door reach rod pulled away from cyl. rod | None
110 | Liberty Island | 2018-12-28 | 84.36 | Other / Other Mechanical | N/A | Dock - Pascagoula | None
111 | 55 | 2018-12-30 | 24.16 | Main Hoist / Holder | 4212279 | Holding friction will not disengage, Rep. Holding br. | None
|  | Brian Markey |  |  |  |  | 229 | STBD Cutter Motor Failure | 0 | 0 | Brian Markey | 1 | 1 | Bill Baumann
|  | Jose Gracia |  |  |  |  | 233 | Noon Island_Generator Engine Overspeed_02252018 | 0 | 0 | Alvin Reyes | 4 | 4 | Jose Gracia
|  | Mark V Outten |  |  |  |  | 238 | Cutter Gearbox Bearing Failure | 0 | 0 | Mark V Outten | 5 | 5 | Bill Baumann
|  | Alexanders Andrezens |  |  |  |  | 244 | 22711_180413_Ohio_DC Contactor | 0 | 0 | James P Arias | 5 | 5 | Jose Gracia
|  | Matt Ferrell |  |  |  |  | 259 | Cavalier State Grounding | 0 | 0 | Matt Ferrell | 3 | 3 | Matt Ferrell
|  | Jacques Coetzee |  |  |  |  | 261 | Booster 9 Generators | 0 | 0 | James P Arias | 2 | 2 | Jose Gracia
|  | Brian C Puckett |  |  |  |  | 270 | AB 118 Damage | 0 | 0 | Brian C Puckett | 4 | 4 | Jeremy Remme
|  | Tim J Kremer |  |  |  |  | 273 | Alaska anchor contact with hull | 0 | 0 | Tim J Kremer | 2 | 2 | Tim J Kremer
|  | Mathew Bishop |  |  |  |  | 274 | Booster Jack Spud Foot / Hull/ and hose Damage | 0 | 0 | Mathew Bishop | 2 | 0 | Sherif Abdelgafar
|  | Mike Hungerford |  |  |  |  | 278 | Dredge Carolina Suction Hose Failure | 0 | 0 | Mike Hungerford | 2 | 2 | Mike Hungerford
Formulas:
DATE = VLOOKUP([Data Tab Ref],Table1[['#]:[Date]],3,FALSE)

## 2019 (hidden)
2019 Summary
Data Tab Ref | DREDGE | DATE | HRS | SYSTEM / SUBSYSTEM | WORK ORDER # | EDL Notes | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Status | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party
112 | Alaska | 2019-01-01 | 95.14 | Ladder Pump / Motor/Engine | 1728433 | Oil leak | None
113 | Ellis Island | 2019-01-04 | 35.54 | Trunnion Hoist / Other | None | none | None
114 | Illinois | 2019-01-06 | 49.55 | Main Pump / Pump rebuild | 4212137 | None | None
115 | Dodge Island | 2019-01-13 | 129.65 | Main Engine / Propulsion / Other (repairs) | 4070010 | None | None
116 | Liberty Island | 2019-01-24 | 140.2 | Drag Head / Other | 0848934 | Parted PORT Draghead wire; at port for replace | None
117 | Terrapin Island | 2019-01-24 | 46 | Main Engine / Propulsion / Propeller | 4181088 | Removing 3 foot shell form STBD pump, replacing impellor and fix pump | None
118 | Carolina | 2019-01-26 | 26.11 | Main Pump / Bearings/Shafts | 4038374 | Change thrust bearing | None
119 | Dodge Island | 2019-01-27 | 58.27 | Main Engine / Propulsion / Other (repairs) | 4069968 | Main Engine | None
120 | Liberty Island | 2019-02-06 | 82.7 | Generator Engine / Other | 0848946 | Failure STBD Gen Eng; swapping generators | None
121 | Dodge Island | 2019-02-12 | 29.72 | Main Engine / Propulsion / Other (repairs) | 4070060 | Air in Jacket Water | None
122 | Ohio | 2019-02-17 | 95.92 | Main Pump / Pump rebuild | 4173127 | Continue maintenance program, change liner pump number one | None
123 | 55 | 2019-02-18 | 95.27 | Main / Aux Gen / Main Generator Eng | 4213134 | None | None
124 | 53 | 2019-02-26 | 123.75 | Main Hoist / Holder | N/A | Holder motor repair | 286 | DR 53 - Bucket Drop | 0 | 0 | Andrew Larkin | 6 | 2 | James C Gillespie
125 | Illinois | 2019-03-06 | 35.41 | Ladder Pump / Pump rebuild | 1578760 | Change runner out change 15 cutter teeth 5 bosses broke off 1 no good | None
126 | Carolina | 2019-03-14 | 40.2 | Spuds / Xmas Tree / Walking Spud | 4038414 | None | None
127 | 53 | 2019-03-24 | 101.08 | Main / Aux Gen. / Main Generator | 4213939 | Generator issues | None
128 | 53 | 2019-03-31 | 35.03 | Main Hoist / Closer Wire | None | Change jackline in 18yd bucket/change becket inside 18yd bucket (found broken ear on becket), cut back closer and holder hoist cables. Change tagline cable due to broken wires @ drum | None
129 | Ellis Island | 2019-03-31 | 31.76 | Drag Head / Other (repairs) | N/A | none | None
130 | Texas | 2019-04-02 | 49.47 | Cutter / Motor | 0791490 | None | None
131 | Liberty Island | 2019-04-09 | 167.7 | Jet Pump / Other | None | Drag Head blown out; unable to cont using jets | None
132 | Terrapin Island | 2019-04-09 | 28.08 | Other / Other mechanical | 4181401 | Hit by fishing vessel | None
133 | Texas | 2019-04-19 | 47.21 | Cutter / Cutter canister (cutter shaft) | 0791491 | None | None
134 | 53 | 2019-04-24 | 149.93 | Main Hoist / Holder | 4213300 | Troubleshoot holder | None
135 | Texas | 2019-04-26 | 79.09 | Cutter / Motor | 0791516 | None | 298 | Stbd Cutter Motors Overheating | 0 | 0 | William Bradshaw
136 | Texas | 2019-05-01 | 25.35 | Cutter / SCR Drive/MG Set | 4214929 | None | None
137 | 53 | 2019-05-05 | 45.96 | Spud System / Spud Structure | 1193339 | Cracked / Broken Stern Spud | None
138 | Ellis Island | 2019-05-12 | 190.34 | Drag Head / Other (repairs) | N/A | Hull ruptured from STBD Draghead casualty. Anchor for Inspection | None
139 | Illinois | 2019-06-09 | 83.23 | Cutter / Motor (Cutter Shaft) | 0309607 | None | None
140 | Terrapin Island | 2019-06-15 | 35.58 | Dredge Pump Engine / Other | 4181774 | Crank case High temp – Port Drag-arm down | None
141 | Liberty Island | 2019-06-25 | 27.9 | Drag Head / Other | 0849330 | Norfolk | None
142 | Ellis Island | 2019-07-02 | 26.52 | Main Engine / Propulsion / Other (repairs) | 4271273 | none | None
143 | Liberty Island | 2019-07-02 | 72.1 | Gimbal Hoist / Other | 0849382 | Fixing PORT side pad eyes | None
144 | Illinois | 2019-07-05 | 100.17 | Main Pump / Pump rebuild | 4214253 | None | None
145 | 54 | 2019-07-13 | 31.79 | Electrical/Electronics / PLC | 4251678 | PLC lost memory | None
146 | 53 | 2019-07-16 | 41.92 | Spud System / Spud Wires | 1193483 | STBD spud wire broke | None
147 | 55 | 2019-07-20 | 26.48 | Main / Aux Gen / Main Generator | 1725905 | Change governor | None
148 | 54 | 2019-07-29 | 32.97 | Spud System / Spud Structure | 4218307 | Stern Spud brake band foundation mount | None
149 | 55 | 2019-07-30 | 927.37 | Main / Aux Gen / Main Generator Eng | 4219354 | Shutdown | None
150 | Padre Island | 2019-08-02 | 30.18 | Generator Engine / Other (repairs) | 1726429 | Rear Seal | None
151 | 58 | 2019-09-01 | 315.49 | Main Hoist / Closer | 4218790 | Closing sheave damaged | None
152 | Texas | 2019-09-10 | 34.09 | Ladder Pump / Pump rebuild | 4219360 | None | None
153 | Carolina | 2019-09-13 | 60.51 | Main Pump / Bearings/Shafts | 4218765 | Main pump #2 thrust bearing getting hot | None
154 | Texas | 2019-09-13 | 498.2 | Spuds / Xmas Tree / Walking Spud | 4219453 | None | None
155 | 55 | 2019-09-29 | 90.25 | Spud System / Spud Winch | 4219808 | None | None
156 | 58 | 2019-09-29 | 70.25 | Electrical/Electronics / MCC/Switch Gear | 4219814 | Swing Tripped out. Blower motor for A/C to drive room burnt out; further inspection shows burn up electrical components in swing drive cabinet. | None
157 | 53 | 2019-09-30 | 33.59 | Crane Swing / Drive (motor, gear box) | 1193566 | Swing tripped | None
158 | Ellis Island | 2019-10-03 | 273.39 | Other / Other Mechanical (repairs) | N/A | Servicing articouple pads at dock | None
159 | Carolina | 2019-10-09 | 201.88 | Generators / Main Generator (Eng Rm) | 4219654 | None | None
160 | 53 | 2019-10-11 | 59.72 | Spud System / Walking Mechanism | 1193606 | None | None
161 | 53 | 2019-10-19 | 51.7 | Crane Boom / Boom Winch | 4795201 1730274 | Boom issue; won’t boom down | None
162 | Sugar Island | 2019-10-20 | 50.24 | Jet Pump Eng / Deck Gen. / Heat Exchanger | None | None | None
163 | Illinois | 2019-10-23 | 33.49 | Main Pump / Engine/Motor | 1730667 | None | None
164 | Terrapin Island | 2019-10-24 | 29.1 | Main Engine / Propulsion / Other | 4182054 | Engineers working on STBD Main Engine. Update: anchored in Alpha Anchorage to let engineersdo repairs on STBD cam shaft | None
165 | Sugar Island | 2019-10-30 | 147.28 | Jet Pump Eng / Deck Gen. / Other | None | None | None
166 | Ellis Island | 2019-10-31 | 614.48 | Other / Hopper | None | STBD #5 Hopper door let go from brackets | 319 | 191031 Ellis Bottom Dump Door #5 | 0 | 0 | Jeremy Remme | 1 | 1 | Jeremy Remme
167 | 58 | 2019-11-06 | 142.57 | Crane Swing / Drive (motor, gear box) | 1730905 | none | 320 | DRG 58 #2 Swing pinion shaft bearing failure | 0 | 0 | Armand F Riehl | 3 | 3 | Brian Goetchius
168 | Terrapin Island | 2019-11-18 | 77.43 | Hydraulics / Other | 4182079 | Aft Ram sprung leak | None
169 | Padre Island | 2019-11-23 | 52.84 | Other / Other Mechanical | N/A | Hole | None
170 | Illinois | 2019-12-08 | 94.08 | Main Pump / Pump rebuild | 4796036 | Tow to Atlantic City and perform main pump job | None
171 | Alaska | 2019-12-10 | 143.58 | Spuds/Xmas Tree / Sheaves | 4796445 | None | None
172 | Carolina | 2019-12-11 | 85.5 | Cutter / Motor (Cutter Shaft) | None | Replace PORT cutter motor | 326 | Carolina Port Cutter Motor | 0 | 0 | Scott Baumann | 2 | 0 | Jose Gracia
173 | 58 | 2019-12-21 | 59.57 | Main / Aux Gen. / Main Generator Eng | 4796635 | none | None
174 | Illinois | 2019-12-22 | 92 | Ladder Pump / Gland Seal | 0309740 | Underway 2200 | None
175 | Carolina | 2019-12-25 | 144.89 | Cutter / Motor (Cutter Shaft) | None | None | None
176 | Alaska | 2019-12-29 | 59.14 | Cutter / SCR Drive / MG Set | 4796684 | None | None
|  | Brian Goetchius |  |  |  |  | 279 | DR 55 - Brake Band Actuator Foundation Failure | 0 | 0 | Andrew Larkin | 1 | 1 | Brian Goetchius
|  | Mike Gerlach |  |  |  |  | 282 | DB 186 Hull/Deck Damage | 0 | 0 | Mike Gerlach | 2 | 0 | David Rappe
|  | Andrew Larkin |  |  |  |  | 283 | Apache Tower Damage | 0 | 0 | Andrew Larkin | 3 | 0 | Andrew Larkin
|  | Mike Kraljevic |  |  |  |  | 290 | DBM STBD M/E Foundation Failure | 0 | 0 | Jeremy Remme | 4 | 4 | Jeremy Remme
|  | Wade Eldridge |  |  |  |  | 291 | Dredge 53 Fire | 0 | 0 | Michael Jimenez | 4 | 4 | James C Gillespie
|  | Andrew Larkin |  |  |  |  | 293 | DR NY Main Engine PP1 Seal Failure | 0 | 0 | Andrew Larkin | 3 | 2 | Jose Gracia
|  | Jaclyn Abrams |  |  |  |  | 301 | Dredge New York A-frame Damage | 0 | 0 | Jaclyn Abrams | 4 | 4 | Andrew Larkin
| D.B. Mackie | James M Walker |  |  |  |  | 302 | 20190523 Ellis Island Hull Damage | 0 | 0 | James M Walker | 3 | 1 | James M Walker
|  | David Burlew |  |  |  |  | 308 | Dredge 54 - Boom Damage | 0 | 0 | Armand F Riehl | 2 | 1 | Andrew Larkin
|  | Christopher Latino |  |  |  |  | 311 | Calcasieu River Multibeam Head Damage | 0 | 0 | Claire Bradford | 6 | 5 | Armand F Riehl
| Dredge-58 | Brian Goetchius |  |  |  |  | 314 | DR 58 - Boom Point Sheave Bearing Failure | 0 | 0 | Andrew Larkin | 3 | 2 | Brian Goetchius
|  | Andrew Larkin |  |  |  |  | 316 | DR 54 - Broken Spud Adjustment Bolts | 0 | 0 | Andrew Larkin | 4 | 3 | Brian Goetchius
|  | Sherif Abdelgafar |  |  |  |  | 323 | Unloader 398 Failure | 0 | 0 | Andrew Larkin | 3 | 1 | Harold E Valentine
|  | Sherry Turner |  |  |  |  | 324 | Dredge Illinois Fuel Spill | 0 | 0 | Sherry Turner | 1 | 1 | Keith Pearse
| Alaska | Tim Riehl |  |  |  |  | 327 | Alaska Christmas Tree Failure | 0 | 0 | Tim Riehl | 1 | 1 | Tim Riehl
|  | Andrew Larkin |  |  |  |  | 328 | DR 55 Fuel Spill | 0 | 0 | Andrew Larkin | 3 | 1 | Brian Goetchius
|  | Terry Wright |  |  |  |  | 329 | UWP Blown Out Seal Dredge Illinois | 0 | 0 | Terry Wright | 1 | 0 | Terry Wright
|  | Bill Baumann |  |  |  |  | 331 | Carolina cutter tailshaft / coupling failure | 0 | 0 | Bill Baumann | 3 | 0 | Steven W Becker
|  | Terry Wright |  |  |  |  | 332 | Swing Motor Failure Dredge Illinois | 0 | 0 | Terry Wright | 1 | 0 | Jose Gracia
| Terrapin Island | Mike Kraljevic |  |  |  |  | 333 | Terrapin Trunnion slide | 0 | 0 | Mike Kraljevic
Formulas:
DATE = VLOOKUP([Data Tab Ref],Table1[['#]:[Date]],3,FALSE)

## 2020 (hidden)
2020 Summary
Data Tab Ref | DREDGE | INCIDENT DATE | HRS | SYSTEM / SUBSYSTEM | WORK ORDER # | EDL Notes | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Status | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party
177 | 55 | 2020-01-01 | 24.5 | Main / Aux. Generators / Main Generator | None | Crane Drive trip out, troubleshoot electrical crane | N
178 | Carolina | 2020-01-01 | 174.2 | Cutter / SCR Drive / MG Set | 1733897 | troubleshoot, replace SCR drive | N
179 | Illinois | 2020-01-01 | 194.5 | Swing System / Winch System | 0309750 | None | N
180 | Carolina | 2020-01-03 | 32.22 | Cutter / Motor (Cutter Shaft) | 4038564 | Replace PORT cutter motor | N
181 | 53 | 2020-01-05 | 31.35 | Spud System / Spud Winch | 4796836 | troubleshoot and repair motor on port spud | D
182 | Texas | 2020-01-07 | 70.9 | Swing System / SCR Drive | None | None | N
183 | Terrapin Island | 2020-01-07 | 44.51 | Trunnion Hoist / Other | 418315 | Port trunnion slide being taken off | D
184 | Carolina | 2020-01-23 | 48.22 | Cutter / SCR Drive / MG Set | 4038575 | port cutter drive | N
185 | Carolina | 2020-01-28 | 124.44 | Cutter / Bearings/Shafts | 4038583 | cutterhead coupling broke | 331 | Carolina cutter tailshaft / coupling failure | 0 | 0 | Bill Baumann | 3 | 0 | Steven W Becker
186 | Alaska | 2020-03-07 | 48.8 | Main Pump / Pump Leak | 1728652 | Leak on rock box | N
187 | Dodge Island | 2020-03-10 | 45.8 | Dredge Pump Engine / Other | None | Throttle Issues | D
188 | 55 | 2020-03-11 | 44.94 | Main / Aux. Generators / Main Generator Eng | None | electrical problem with main engine cooling water pump | N
189 | Ellis Island | 2020-03-11 | 29.1 | Drag Head Hoist / Brake Assembly | None | None | D
190 | Dodge Island | 2020-03-23 | 26.3 | Dredge Pump / Other | 4070790 | Wiring Harness | D
191 | Texas | 2020-04-27 | 42.03 | Main Pump / Engine/Motor | 0792089 | BOTH MAIN PUMP ENGINES SHUT DOWN DUE TO MAIN PUMP BEARING FAILURE | N
192 | Texas | 2020-05-01 | 40.91 | Main Pump / Bearings/Shafts | 0792090 | Repairing Main pump bearing shaft - underway for dig site at 19:50-arrived at dig site at 01:00.hauling gears malfunctioning. | N
193 | Carolina | 2020-05-13 | 101.66 | Cutter / SCR Drive / MG Set | None | Cutter drive running high temp | 347 | Dredge Carolina Cutter Thrust Bearing Failure | 0 | 0 | Bill Baumann | 7 | 6 | Bill Baumann
194 | 54 | 2020-05-14 | 29.91 | Crane Boom / Boom Winch | 4799710 | Shut down. Inspect boom hoist drum assembly. Realign gears and replace bolts | 366 | DR 54 - Boom Heel Pin | 0 | 0 | Andrew Larkin
195 | Carolina | 2020-06-03 | 47.29 | Ladder Pump / Shaft | None | None | 355 | Carolina UWPS coupling failure | 0 | 0 | Kurt Hill | 5 | 4 | Thomas C Hoag
196 | Carolina | 2020-06-19 | 143.19 | Main Pump / Bearings/Shafts | None | None | 354 | Carolina Port Main pump drive coupling failure | 0 | 0 | Kurt Hill | 5 | 3 | Jose Gracia
197 | Texas | 2020-07-26 | 67.1989 | Ladder Pump / Pump Leak | 4801646 | None | N
198 | Carolina | 2020-08-07 | 46.0775 | Electrical System / PLC / Automation | 4038753 | None | N
199 | 53 | 2020-08-18 | 23.9997 | Crane Swing / Swing Circle (rollers, etc.) | None | down for swinging bush repairs | N
200 | Ellis Island | 2020-08-20 | 201.77 | Main Engine / Propulsion / Gearbox | None | Gearbox Troubleshooting | N
201 | Texas | 2020-08-22 | 40.0625 | Cutter / Motor | 792338 | tow dredge in for repairs- Cutter mottor cooler | N
202 | Carolina | 2020-08-22 | 27.0664 | Cutter / Bearing / Shaft | 4038781 | lost service water | 361 | Carolina Plugged Service water line | 0 | 0 | Scott Baumann | 5 | 3 | Tim Riehl
203 | 54 | 2020-08-23 | 117.2964 | Main Hoist / Holder | 4251786 | going to S I yard for repairs | N
204 | Texas | 2020-08-28 | 31.6697 | Ladder Pump / Pump Rebuild | 4802045 | pump shell cracked - change pump shell | N
205 | Ellis Island | 2020-08-29 | 201.77 | Main Engine / Propulsion / Gearbox | None | Gearbox Troubleshooting | N
206 | 53 | 2020-09-03 | 27.0581 | Main / Aux. Generators / Main Generator | None | None | N
207 | Alaska | 2020-09-24 | 243.1528 | Main Pump / Bearings / Shafts | 4802724 | thurst bearing temp high | 368 | Alaska M/P Thrust Bearing Failure | 0 | 0 | Jose Gracia | 1 | 1 | Tim Riehl
208 | Liberty Island | 2020-10-13 | 130.53 | Main Engine / Propulsion / Other | 850561 | M/E shutdown; troubleshooting | 375 | Liberty Is Uncommand Stops Gen + Main Eng | 0 | 0 | Chris Roberts | 6 | 0 | Chris Roberts
209 | Carolina | 2020-10-15 | 61.4994 | Main Pump / Bearings / Shafts | 4803118 | None | N
210 | Ohio | 2020-10-18 | 62.895 | Electrical System / PLC / Automation | None | UWP is tripping out on the main board | N
211 | 54 | 2020-10-21 | 94.3867 | Crane Swing / Drive (motor, gear box, etc.) | None | stbd swing gear bushing went bad | N
212 | Alaska | 2020-10-22 | 67.4458 | Main Pump / Bearings / Shafts | 1747550 | thrust bearing heated up and the machine unclutched on its own | N
213 | Ohio | 2020-11-05 | 72.4706 | Ladder Pump / Bearings / Shafts | 4803593 | None | N
214 | Ohio | 2020-11-08 | 29.8925 | Generators / Main Generator | None | None | N
215 | Liberty Island | 2020-11-11 | 30.64 | Other / Other Mechanical | None | None | N
216 | Alaska | 2020-11-17 | 33.3906 | Ladder Pump / Gland Seal | 1728852 | None | N
217 | Liberty Island | 2020-11-22 | 34.72 | Dredge Pump / Clutch | 850650 | Port clutch won't disengage. Stbd engine showing two ECM alarms | N
218 | Liberty Island | 2020-11-22 | 51.76 | Main Engine / Propulsion / Clutch | None | None | N
219 | Ohio | 2020-11-24 | 87.835 | Ladder Pump / Gearbox | None | broken bolts on shaft meets coupling,metal sceen stuck in numer 2 pummp,bad seals on gearbox. assistant chief and engineer with have futher info on the gearbox issues | N
220 | Liberty Island | 2020-11-28 | 25.13 | Drag Head / Other | None | breakaway flange repair | N
221 | Terrapin Island | 2020-12-01 | 43.6925 | Drag Head / Other | Need specific category, other no idea. | change out port & stbd | N
222 | New York | 2020-12-08 | 26.1653 | Main Hoist/Main Hydraulics / Excavator Hydraulics | None | block on stick cylinder leaking | D
223 | Ohio | 2020-12-17 | 25.9833 | Main Pump / Pump Rebuild | None | None | N
224 | New York | 2020-12-27 | 43.7275 | Crane Boom / Boom Structure | None | CYLINDER ISSUE | 383 | DR New York Boom Cylinder Failure | 0 | 0 | Andrew Larkin
|  | Brian Goetchius |  |  |  |  | 336 | Dredge New York Generator Failure | 0 | 0 | Brian Goetchius | 2 | 0 | Brian Goetchius
|  | James M Walker |  |  |  |  | 345 | 20200510 Terrapin Island Hopper Open/Close Damage | 0 | 0 | James M Walker | 2 | 2 | James M Walker
|  | Nathan Stevick |  |  |  |  | 346 | Columbia River Main Engines Damage | 0 | 0 | Nathan Stevick | 3 | 3 | Nathan Stevick
|  | Alexanders Andrezens |  |  |  |  | 352 | BOOSTER 9 GEAR BOX EQUIPMENT DAMAGE | 0 | 0 | Sheldon Brooks | 7 | 0 | Jose Gracia
|  | Holt Hartung |  |  |  |  | 358 | DR 53 Swing Gearbox Failure | 0 | 0 | Andrew Larkin | 4 | 1 | Brian Goetchius
|  | Brian Goetchius |  |  |  |  | 362 | Dr 54 - Holding Drum Brake | 0 | 0 | Andrew Larkin | 2 | 0 | Brian Goetchius
|  | Jose Gracia |  |  |  |  | 363 | Ohio Cutter Gearbox Contamination | 0 | 0 | Jose Gracia
|  | Alexanders Andrezens |  |  |  |  | 364 | 22694_Port Engine Gear Box Bearing Failure | 0 | 0 | Sheldon Brooks | 5 | 0 | Jose Gracia
|  | Jose Gracia |  |  |  |  | 365 | Ohio Auxiliary Winch Damages | 0 | 0 | Jose Gracia | 3 | 0 | Kelly Briscoe
|  | Kurt Hill |  |  |  |  | 369 | Booster Jessie Starboard Gearbox Bearing Failure | 0 | 0 | Nicholas D Williams | 2 | 0 | Sherif Abdelgafar
|  | Andrew Larkin |  |  |  |  | 371 | Unloader Snorkel Drift | 0 | 0 | Andrew Larkin
|  | Christopher Charron |  |  |  |  | 374 | Cape Girardeau Yard- Crane Boom Failure | 0 | 0 | Christopher Charron | 1 | 1 | Christopher Charron
| Texas | Bill Baumann |  |  |  |  | 376 | Dredge Texas fuel tank vent plugs incident | 0 | 0 | Jose Gracia | 2 | 0 | Jose Gracia
| Texas | Bill Baumann |  |  |  |  | 377 | Dredge Texas internal fuel leak incident | 0 | 0 | Robert Kelly
|  | Chris Roberts |  |  |  |  | 378 | Terrapin Island-Deck Generator (Cat 3516) Failure | 0 | 0 | Nilene Brunslik | 1 | 1 | Chris Roberts
|  | Brian Goetchius |  |  |  |  | 382 | GL 501 - Cylinder Failure | 0 | 0 | Andrew Larkin | 2 | 0 | Andrew Larkin
Formulas:
INCIDENT DATE = VLOOKUP([Data Tab Ref],Table1[['#]:[Date]],3,FALSE)

## 2021 (hidden)
2021 Summary
EDL Data Tab Ref | DREDGE | INCIDENT DATE | HRS | SYSTEM / SUBSYSTEM | EDL Notes | WORK ORDER # | Work Order Title | MCIA Status | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party | RAM Steering Committee comments | CA count | EDL | MCIA | check
225 | 53 | 2021-01-03 | 24.0642 | Main / Aux. Generators / Main Generator | # 2 generator shutdown. Reverse power/electrical trip. Inspected resistor bank on top of crane. One bank is cooler than the other 2. also found one wire chaffed and tapped up/secured wires | 1750884 | Work Order not found |  | N | [9 empty] | 1 | 0 | 0
226 | 54 | 2021-01-17 | 33.9333 | Main Hoist / Holder | None | None |  |  | 385 | [6 empty] | Andy Larkin / Brian Goetchius |  |  | 1 | 0 | 0
227 | Texas | 2021-01-30 | 27.2611 | Cutter / Motor | cooler leaking on cutter motor | None |  |  | N | [9 empty] | 1 | 0 | 0
228 | Ellis Island | 2021-02-05 | 50.22 | Other / Other Mechanical | to dock for plate cooler repair and other maintenance | None |  |  | N | [9 empty] | 1 | 0 | 0
229 | 58 | 2021-02-06 | 32.375 | Main Hoist / Holder | HOLDER WIRE BROKE | 4420100 | Broken Holder wire |  | N | [9 empty] | 1 | 0 | 0
230 | 53 | 2021-02-08 | 26.0025 | Auxiliary Systems / Heating, Ventilation, A/C | None | None |  |  | N | [9 empty] | 1 | 0 | 0
231 | Texas | 2021-02-08 | 40.7892 | Spuds / Xmass Tree / Wires | stb breast wire broke an lost stb bottom sheve on x-mas tree take dredge in to repair | None |  |  | N | [9 empty] | 1 | 0 | 0
232 | Illinois | 2021-02-24 | 149.6619 | Cutter / Gear Box | None | 4806414 | Replacement of Cutter gearbox HS input shaft bearings & HS Intermediate shaft bearings. | Complete | 391 | Cutter Gear Box Input Shaft Bearing Failure | 02/24/2021 | Terry Wright | 1 | 0 | Dave Allen | Dave Allen / Joe Gracia |  | 1 | 1 | 1 | 1
233 | Dodge Island | 2021-02-25 | 25.2733 | Generator Engine / Other | port generator change head | 4071215 | Port Generator - Troubleshoot high exhaust temps |  | N | [9 empty] | 1 | 0 | 0
234 | Terrapin Island | 2021-02-28 | 29.5911 | Dredge Pump / Gland Seal | fuel | 4182524 | Rebuild Pump |  | N | [9 empty] | 1 | 0 | 0
235 | Liberty Island | 2021-03-07 | 47.34 | Jet Pump / Pump Bearing | Line Shaft Bearing | 850890 | Replace stbd jet pump line shaft bearing and install the spare |  | N | [9 empty] | 1 | 0 | 0
236 | 53 | 2021-03-14 | 145.21 | Crane Swing / Swing Circle (rollers, etc.) | the cracks on the bow at the tub base are flexing and opening up. also excessive movement in the rail and popping sounds. Welding | None |  |  | N | [9 empty] | 1 | 0 | 0
237 | New York | 2021-03-15 | 33.8339 | Tagline/Boom Assist / A-Frame (Wires, Winch, etc) | Structural damage/cracks on hog wire anchors | 4806683 | Quotes to remove and install new back stay dead end deck |  | N | [9 empty] | 1 | 0 | 0
238 | 54 | 2021-03-18 | 27.3458 | Main Hoist / Holder | brake pins damaged | 4806741 | change inboard brake band ( working brake band) |  | N | [9 empty] | 1 | 0 | 0
239 | 54 | 2021-03-29 | 27.75 | Crane Boom / Boom Winch | None | 4807069 | Trouble-shoot boom motor getting hot / smoking |  | N | [9 empty] | 1 | 0 | 0
240 | Illinois | 2021-04-05 | 42.0783 | Cutter / Gear Box | None | 4806414 | Replacement of Cutter gearbox HS input shaft bearings & HS Intermediate shaft bearings. |  | N | [6 empty] | Dave Allen / Joe Gracia | Taken care of as MCIA case # 391 |  | 1 | 0 | 0
241 | 53 | 2021-04-06 | 40.0828 | Electrical/Electronics / MCC / Switch Gear | bucket fell in scow (full load) drives tripped. troubleshooting. changed 2 blown fuses on closer, test. issue with holder drum not turning/inspected and found broken shaft on holder gearbox | None |  |  | Y | [6 empty] | Andy Larkin / Brian Goetchius | Determined MCIA is required; MCIA has not been started yet |  | 1 | 0 | 0
242 | 54 | 2021-04-21 | 67.9831 | Spud System / Spud Wires | Stern spud wire broke | 4807689 | Spud (Stern) Bottom Wire Change |  | N | [9 empty] | 1 | 0 | 0
243 | Ohio | 2021-04-23 | 27.9039 | Main Pump / Pump Rebuild | pump liner wore out | 4807705 | Install new liner in #2 pump / Oak Island N.C. |  | Y | [6 empty] | Dave Allen / Joe Gracia | Determined MCIA is required; MCIA has not been started yet |  | 1 | 0 | 0
244 | Carolina | 2021-04-26 | 50.7189 | Ladder Pump / Gearbox | None | 4038883 | Remove and reinstall UWP gear case top cover | In Progress | 408 | Ladder Pump / Gear Box | 04/26/2021 | Wade Smith | 1 | 1 | Tim Riehl | Dave Allen / Joe Gracia |  | 0 | 1 | 1 | 1
245 | Carolina | 2021-05-05 | 117.1581 | Idler / Spud Barge / GL10 | winch issues | None |  | Ready for Review | 398 | GL10 Idler Barge | 05/05/2021 | Shawn Boynton | 2 | 0 | Scott Baumann | Dave Allen / Joe Gracia |  | 2 | 1 | 1 | 1
246 | Carolina | 2021-05-19 | 156.3961 | Ladder Pump / Gearbox | Gearbox repair. | None |  |  | N | [6 empty] | Dave Allen / Joe Gracia | Mechanical Seal / Packing will be fixed when new one arrives |  | 1 | 0 | 0
247 | Carolina | 2021-05-28 | 88.8417 | Main Pump / Bearings / Shafts | None | None |  | In Progress | 409 | Main Pump Thrust Bearings Port side | 05/28/2021 | Wade Smith | 2 | 2 | Scott Baumann | Dave Allen / Joe Gracia |  | 0 | 1 | 1 | 1
248 | Liberty Island | 2021-06-04 | 42.96 | Other / Other Mechanical (repairs) | None | None |  |  | N | [9 empty] | 1 | 0 | 0
249 | 54 | 2021-06-06 | 40.0117 | Spud System / Spud Wires | None | 4251870 | Change top spud wire |  | N | [6 empty] | Andy Larkin / Brian Goetchius | all wires failed sooner than expected. Have not asked the question about manufacturing. Southwest Wire Rope. |  | 1 | 0 | 0
250 | Illinois | 2021-06-07 | 34.7061 | Main Pump / Engine / Motor | spring bearing | 4808652 | Install new spring bearing insert |  | N | [9 empty] | 1 | 0 | 0
251 | Liberty Island | 2021-06-08 | 67.89 | Main Engine / Propulsion / Other (repairs) | engine overheated and shut down again. Replace Stbd Turbo | 851132 | REPLACE SME INBOARD TURBO CHARGER | Complete | 401 | Liberty Island Main STBD Engine Turbo Failure | 06/08/2021 | Chris Pomfret | 1 | 1 | Chris Roberts | Chris Roberts / Mike Kraljevic |  | 0 | 1 | 1 | 1
252 | Carolina | 2021-06-15 | 24.8903 | Main Pump / Pump Rebuild | None | 4808746 | Dredge Pump (Stbd) remove and replace crack shell |  | N | [9 empty] | 1 | 0 | 0
253 | Carolina | 2021-06-19 | 116.1406 | Main Pump / Pump Leak | None | 4808866 | Dredge Pump (Stbd) Replace shell |  | N | [9 empty] | 1 | 0 | 0
254 | Illinois | 2021-06-23 | 67.9808 | Main Pump / Pump Rebuild | None | None |  |  | N | [9 empty] | 1 | 0 | 0
255 | Illinois | 2021-06-26 | 42.6 | Main Pump / Bearings / Shafts | Thrust Bearing | 309837 | Inspect and clean thrust bearing & add 2nd heat exchanger |  | N | [6 empty] | Dave Allen / Joe Gracia | Failed Heat Exchanger - if repaired twice, needs replacing. Only applicable to ALASKA and ILLINOIS. Add step to SJ, determine number of times failed prior, at second, replace vice repair. Check in December if added to SJ. |  | 1 | 0 | 0
256 | 54 | 2021-06-29 | 87.1125 | Electrical/Electronics / MCC / Switch Gear | None | 4251884 | Trouble Shoot Hoist Generator |  | N | [6 empty] | Andy Larkin / Brian Goetchius | Proposal in to replace next SY period - |  | 1 | 0 | 0
257 | 54 | 2021-07-03 | 29.9428 | Electrical/Electronics / PLC | None | 4251884 | Trouble Shoot Hoist Generator |  | N | [6 empty] | Andy Larkin / Brian Goetchius | Related to above. |  | 1 | 0 | 0
258 | 55 | 2021-07-09 | 26.2706 | Main / Aux. Generators / Main Generator Engine | governor repair | 4809140 | Troubleshoot Governor Issues |  | N | [6 empty] | Andy Larkin / Brian Goetchius | Found to be failed linkage on rack to injectors; lack of experience on EMD to recognize |  | 1 | 0 | 0
259 | Liberty Island | 2021-07-09 | 52.7453 | Other / Other Mechanical | @ DOCK FOR MAINT. & REPAIRS | 0851204/0851205 | Manually open D8 dredge valve. / Troubleshoot why dredge valve D8 isn't opening. |  | N | [6 empty] | Chris Roberts / Mike Kraljevic | TCR - The only item I have for this date is that it corresponds to the trunnion repair after the Mate ran into the pumpout barge, impacted by strong St. Johns River current, while digging on the Mayport, FL project. We do not need an MCIA as it was a repair of self-induced damage. |  | 1 | 0 | 0
260 | Carolina | 2021-07-11 | 26.2233 | Main Pump / Pump Rebuild | None | 4809309 | Dredge Pump (Port) Rebuild | [8 empty] | Dave Allen / Joe Gracia | Is this related to MCIA #407 below? Incident dates are off a few weeks from each other. |  | 1 | 0 | 0
261 | 58 | 2021-07-15 | 51.5431 | Electrical/Electronics / MCC / Switch Gear | None | 4420132 | Install upgraded Avid Extreme 550 Inverters |  | N | [6 empty] | Andy Larkin / Brian Goetchius |  |  | 1 | 0 | 0
262 | Texas | 2021-07-21 | 33.4239 | Ladder Pump / Motor / Engine | Replace UWP motor | 4809535 | Replace ladder pump motor | [8 empty] | Dave Allen / Joe Gracia |  |  | 1 | 0 | 0
263 | 54 | 2021-07-28 | 221.0078 | Hull / Hull / House Repair | coast guard inspecting the hull | 1761278 | Work Order not found |  | N | [9 empty] | 1 | 0 | 0
264 | 58 | 2021-08-01 | 573.0697 | Crane Boom / Boom Winch | After lightning storm , boom up to swing off deck. Come around to start digging. Had to make a move, after making move went to boom down and boom would not stop. | 4420181 | Repair Boom Cords |  | N | [9 empty] | 1 | 0 | 0
265 | Ellis Island | 2021-08-03 | 44.5497 | Other / Other Mechanical | at dock | None |  |  | N | [7 empty] | TCR - This down time corresponds with a repair / investigation visit from MAK and Beier. MAK was performing a firmware upgrade and Beier was reviewing the DP/DT - ECDIS interface |  | 1 | 0 | 0
266 | Iowa | 2021-08-05 | 23.9997 | Swing System / Winch System | Major Mech. Repair to swing wire hydraulics | None | [12 empty] | 1 | 0 | 0
267 | Texas | 2021-08-15 | 33.8492 | Swing System / Swing Sheaves | None | None | [12 empty] | 1 | 0 | 0
268 | 54 | 2021-08-17 | 100.7683 | Main / Aux. Generators / Main Generator Engine | None | 4810115 | Replace Thrush Washers / Inspect engine components |  | N | [9 empty] | 1 | 0 | 0
269 | Texas | 2021-08-19 | 24.1561 | Spuds / Xmass Tree / Tree Structure | None | None | [12 empty] | 1 | 0 | 0
270 | Dodge Island | 2021-08-25 | 173.5103 | Steering / Rudder | None | None |  | Complete | 432 | Dodge Island - Rudder Damage / Loss | 08/25/2021 | Chris Roberts | 1 | 1 |  |  | TCR - I think this already has an MCIA from the project site. Can we check? If not the root cause was running agounr in a shallow dig area - See the Damage Report - and the analysis findings from the rudder shop that examined the threads. | 0 | 1 | 1 | 1
271 | Liberty Island | 2021-09-01 | 23.9997 | Hydraulics / Other | Dredge at Dock for STB Main HYD Repairs | None |  |  | N | [7 empty] | TCR - This was a planned repair period after we sprung leaks in the leelson jet piping. We took the 2-3 days to perform many repair items. This also occurred while were at the Mayport, FL project |  | 1 | 0 | 0
272 | New York | 2021-09-02 | 32.5981 | Tagline/Boom Assist / A-Frame (Wires, Winch, etc) | moving to office location for repairs | 4810395 | Change Stay Wires |  | N | [9 empty] | 1 | 0 | 0
273 | Carolina | 2021-09-03 | 59.0297 | Main Pump / Gearbox | coupler to thrust bearing broke | 4038962 | Repair stbd pump coupling & Thrust bear replacement | Complete | 412 | Dredge Carolina MP Thrust Bearing Coupling | 09/03/2021 | Wade Smith | 1 | 0 |  |  |  |  | 1 | 1 | 1
274 | Ohio | 2021-09-05 | 30.7736 | Ladder / Wire | Ladder wire strarting to part. Changing wire. All stop oder due to lighting | None |  |  | N | [9 empty] | 1 | 0 | 0
275 | Dodge Island | 2021-09-07 | 35.4375 | Hydraulics / Other | None | 4071556 | Port Hyd. Service System: Repair Leak in Piping |  | N | [7 empty] | TCR - This delay lasted 36 hours. The first 24-hours was the time it took to get another (replacement) O2 meter from the landside support. The space where the leaking pipe occurred was in a Confined Space so there was no action until the meter was received. The last 12 hours was the actual mechanical repair. It did not meet the MCIA level, however, the Division worked with the Safety Department and they are now supplying two o2 meters for each vessel in a set rotation so that 2x units are on hand for at least 10 months out of a year. |  | 1 | 0 | 0
276 | Ohio | 2021-09-18 | 95.7069 | Ladder Pump / SCR Drive | underwater pump wont start back up. Waiting on parts. | None | [12 empty] | 1 | 0 | 0
277 | 54 | 2021-09-25 | 26.3153 | Spud System / Spud Structure | None | None |  |  | N | [9 empty] | 1 | 0 | 0
278 | New York | 2021-09-29 | 51.2067 | Crane Swing / Drive (Motor, Gear Box, etc) | CHECKING ON NOISE FFROM ONE OF THE SWINGS ON 996 TAKE SWING MOTOR OFF SWING PLANATERY #111 TO CKECK SUN GEAR | 4811009 | Troubleshoot Swing Gear - Install new Swing gear | [11 empty] | 1 | 0 | 0
279 | New York | 2021-10-02 | 24.8617 | Crane Swing / Drive (Motor, Gear Box, etc) | problem with new swing hydralic going into gear oil | 4811214 | Replace Hydraulic Motor | [11 empty] | 1 | 0 | 0
280 | Alaska | 2021-10-04 | 58.5 | Spuds / Xmass Tree / SCR Drive | None | 4811264 | Troubeshoot and repair spud drive | [11 empty] | 1 | 0 | 0
281 | New York | 2021-10-05 | 68.4847 | Main/Aux Generators / PP1 | spudded down in inner harbor for work to PP1 and Gen 1/inspections | 4811241 | Weld up cracking on bucket | [11 empty] | 1 | 0 | 0
282 | Sandpiper | 2021-10-06 | 24.4239 | Swing System / Winch System | SWING WINCH HYDRAULIC PUMP ISSUES | None | [12 empty] | 1 | 0 | 0
283 | 54 | 2021-10-10 | 35.8581 | Spud System / Spud Wires | Stern spud wire about to break | 4811448 | Change bottom spud wire | [11 empty] | 1 | 0 | 0
284 | Liberty Island | 2021-10-15 | 23.9997 | Main Engine/Propulsion / Other | None | 851480 | Port Main Engine inboard and outboard turbo failure | Ready for Edits | 418 | Liberty Island Turbo Failure | 10/14/2021 | Mike Gerlach | [6 empty] | 1 | 1 | 1
285 | Ellis Island | 2021-10-21 | 68.9667 | Gimbal Hoist / Wires | None | 4272235 | Stbd gimbal wire retrieval | [11 empty] | 1 | 0 | 0
286 | Ellis Island | 2021-10-29 | 69.6831 | Other / Electrical | Ellis Drag Head Computer Fried - Needs to be remoted into | None | [12 empty] | 1 | 0 | 0
287 | Carolina | 2021-10-29 | 35.5508 | Swing System / Winch System | None | None | [12 empty] | 1 | 0 | 0
288 | Liberty Island | 2021-10-30 | 232.4 | Steering / Rudder | STB rudder non-responsive | 851525 | Troubleshooting P/S Steering Gear Systems rudder control | [11 empty] | 1 | 0 | 0
289 | Alaska | 2021-11-13 | 145.4464 | Ladder Pump / Motor / Engine | TRIPPING | 1729030 | Remove the UWP Motor | [11 empty] | 1 | 0 | 0
290 | Terrapin Island | 2021-11-15 | 61.1567 | Dredge Pump / Gland Seal | port pump gland seal, went to dock for repairs | 4184180 | Impeller - Port dredge pump - Remove & install for gland seal replacement | [11 empty] | 1 | 0 | 0
291 | Carolina | 2021-11-15 | 55.0117 | Swing System / Swing Sheaves | stardboard side | 4038991 | Make repairs to swing winch frame | [11 empty] | 1 | 0 | 0
292 | Sandpiper | 2021-11-19 | 28.2 | Main Pump / Engine / Motor | was cleaning out line when steel engine coolant fitting cracked causing antifreeze to leak in engine room. reweld fitting and get back to running | None | [12 empty] | 1 | 0 | 0
293 | Iowa | 2021-11-20 | 23.9994 | Ladder Pump / Bearings / Shafts | None | None | [12 empty] | 1 | 0 | 0
294 | New York | 2021-11-24 | 83.2533 | Spud System / Spud Wires | Port spud repair | 4812674 | Change Wire | [11 empty] | 1 | 0 | 0
295 | Ohio | 2021-11-24 | 27.6658 | Spuds / Xmass Tree / Wires | Starboard breast wire broke while moving anchors. | None | [12 empty] | 1 | 0 | 0
296 | Sandpiper | 2021-11-27 | 47.9997 | Main Pump / Engine / Motor | replace 3 heads on main engine 3516 | None | [12 empty] | 1 | 0 | 0
297 | Ohio | 2021-12-05 | 51.4 | Ladder Pump / Pump Rebuild | fracture in underwater pump | 4812866 | Replace impeller UWP. | [11 empty] | 1 | 0 | 0
298 | New York | 2021-12-08 | 131.1494 | Main/Aux Generators / Generator #1 | LOST GENERATOR DUE TO ELECTRICAL TRIP @00:20,SWITCH GENERATOR. BLOWER FOR BOOM ASSIST KEEPS TRIPPING OUT | 4812901 | replace boom assist blower motor | [11 empty] | 1 | 0 | 0
299 | Sandpiper | 2021-12-08 | 32.215 | Swing System / Winch System | GEARBOX WENT DOWN | 4812886 | HPU Gear Hydraulic Failure | [11 empty] | 1 | 0 | 0
300 | Sandpiper | 2021-12-14 | 53.8594 | Main Pump / Engine / Motor | replace head on main engine | 4813019 | Dredge Main engine mechanical failure | [11 empty] | 1 | 0 | 0
301 | New York | 2021-12-14 | 32.9833 | Tagline/Boom Assist / Boom Assist Wire | Boom assist wire broke | 4813001 | change boom assist wire | [11 empty] | 1 | 0 | 0
302 | New York | 2021-12-17 | 39.1667 | Spud System / Spud Wires | Replace stern spud wire | 4813043 | change stern spud wire | [11 empty] | 1 | 0 | 0
303 | Texas | 2021-12-18 | 47.5331 | Cutter / Motor | None | 792854 | No Work Order entered | [11 empty] | 1 | 0 | 0
304 | Sandpiper | 2021-12-20 | 55.2 | Main Pump / Engine / Motor | None | 4813490 | No Work Order entered | [11 empty] | 1 | 0 | 0
305 | 53 | 2021-12-22 | 216 | Tagline / Tagline Winch (motor, gearbox, etc.) | Tagline gearbox repair | 4813071 | Tagline gearbox repairs | [11 empty] | 1 | 0 | 0
306 | New York | 2021-12-27 | 79.5 | Crane Boom / Boom Structure | Working on Welding repairs in Boom. Spudded down in Inner Harbor near office. | 4813504 | No Work Order entered | [11 empty] | 1 | 0 | 0
307
SAFELYNCS DATA ONLY:
| Dredge-58 | [7 empty] | 381 | [6 empty] | Andy Larkin / Brian Goetchius | Not related to EDL delay |  | 0 | 0 | 0
|  | William Bradshaw | [5 empty] | 01/15/2021 | 384 | Pass A'Loutre Survey | 0 | William Bradshaw | 2 | 2 | William Bradshaw |  |  | 0 | 0 | 1 | 0
|  | Robert Kelly | [5 empty] | 01/27/2021 | 386 | Scow 66 #1 Closing Cylinder Failure 210127 | 0 | Jeremy Remme | 1 | 0 | Andrew Larkin | Andy Larkin / Brian Goetchius | Not related to EDL delay | 1 | 0 | 1 | 0
|  | Chris Faught | [5 empty] | 03/05/2021 | 389 | Crane Boom Failure | 0 | Terreo Hathorn | 2 | 2 | Christopher Charron | Terry Newberry |  | 0 | 0 | 1 | 0
|  | Steve W Lawrence | [5 empty] | 04/02/2021 | 394 | Jax Yard Marina Damage | 0 | Steve W Lawrence | [6 empty] | 0 | 1 | 0
|  | Crystopher Barnett | [5 empty] | 05/21/2021 | 399 | Ellis Island Miss Dump | 0 | Nicholas D Williams | 3 | 3 | Jeremy Remme |  |  | 0 | 0 | 1 | 0
|  | William Bradshaw | [5 empty] | 07/01/2021 | 405 | Pass A'Loutre GL 660 Dozer Sinking | 0 | William Bradshaw | 2 | 2 | William Bradshaw |  |  | 0 | 0 | 1 | 0
| Carolina | 06/15/2021 | [5 empty] | Complete | 407 | Starboard Main Pump | 06/15/2021 | Wade Smith | 1 | 0 | Lupe Benavides |  |  | 1 | 0 | 1 | 0
| Booster 32-20 | 10/25/2021 | [5 empty] | In Progress | 419 | R032 Booster 3516 engine failure | 10/25/2021 | Terry Newberry | 4 | 0 | Everett Reed |  |  | 4 | 0 | 1 | 0
| #N/A | [7 empty] | 420 | [9 empty] | 0 | 0 | 0
| #N/A | [7 empty] | 421
EDL / NS ENTERPRISE DATA
SAFELYNCS DATA
CORRELATED EDL & SAFELYNCS DATA
[8 empty] | RAM STEERING COMMITTEE DECISION-MAKING | [9 empty] | Calculations - Do not alter
|  | # |  | Data Point |  |  | Reference | [7 empty] | #REF!
|  | 10 |  | # MCIA's started |  |  | SafeLyncs - Cases
|  | 3 |  | # MCIA's in progress |  |  | SafeLyncs - Cases
|  | 1 |  | # MCIA's Ready for Edits |  |  | SafeLyncs - Cases
|  | 1 |  | # MCIA's Ready for Review |  |  | SafeLyncs - Cases
|  | 5 |  | # MCIA's completed |  |  | SafeLyncs - Cases
|  | -2 |  | # MCIA's requiring Corrective Actions Validated |  |  | SafeLyncs - Corrective Actions
| * | 82 |  | # EDL MM entries (>24hrs) |  |  | EDL Data
|  | 54 |  | # EDL MM w/ WO#'s |  |  | EDL Data
|  | 28 |  | # EDL MM w/o WO#'s |  |  | EDL Data
| * | 8 |  | # EDL MM w/ MCIA coorelation |  |  | EDL v. SafeLyncs
| * | 37 |  | # EDL MM determined "No" MCIA required |  |  | RAM Steering Committee
| * | 2 |  | # EDL MM determined "Yes" MCIA required, not started |  |  | RAM Steering Committee
| * | 34 |  | # EDL MM still requiring determination |  |  | RAM Steering Committee
81
Formulas:
INCIDENT DATE = VLOOKUP([EDL Data Tab Ref],Table1[['#]:[Date]],3,FALSE)

## 2022
2022 Summary
EDL Data Tab Ref | DREDGE | INCIDENT DATE | HRS | SYSTEM / SUBSYSTEM | EDL Notes | WORK ORDER # | Work Order Title | MCIA Status | MCIA Case ID (#/N/D) | MCIA Case Title | MCIA Start Date | MCIA Scribe | # of Corrective Actions | # of Corrective Actions Validated | MCIA Verification Manager | RAM Committee Responsible Party | RAM Steering Committee comments | CA count | EDL | MCIA | check
307 | 55 | 2022-01-11 | 25.6711 | Auxiliary Systems / Compressed Air | Water froze in air lines | N/A | No Work Order entered |  | N | [7 empty] | N |  | 1 | 0 | 0
308 | Carolina | 2022-01-15 | 110.8522 | Ladder Pump / Bearings / Shafts | None | 4813489 | Thrust bearing replacement |  | N | [7 empty] | We knew we needed to changed based on earlier inspection but decision was made to not take down time until end of job, which resulted in failure. |  | 1 | 0 | 0
309 | Terrapin Island | 2022-01-17 | 58.625 | Dredge Pump / Gland Seal | None | 4184362 | Replace the gland seal - Stbd Pump - Leaking too much water |  | N | [7 empty] | No. This is a known issue that occurs every 6/8 weeks. This a 3 day downtime to repair. Parts are on backorder with a long lead time. |  | 1 | 0 | 0
310 | New York | 2022-01-21 | 26.1942 | Main/Aux Generators / PP1 | Work on PP1; Moved to Spud down location outside of office to finish repairs | 1769537 | Work Order not found |  | Brian G looking into this. | [7 empty] | Brian G looking into this. |  | 1 | 0 | 0
311 | Carolina | 2022-01-26 | 48.7569 | Idler / Spud Barge / GL10 | None | 4813835 | Replace Sprockets and Drive Chain on GL10 Spud Winch |  | N | [7 empty] | No. Allignment checking rolers , moved shieve over. All encompassing. |  | 1 | 0 | 0
312 | New York | 2022-02-09 | 25.2 | Main/Aux Generators / PP1 | CHANGE OIL AND FILTERS | 4814066 | Troubleshoot boom drift and stick float issues |  | N | [7 empty] | No. |  | 1 | 0 | 0
313 | 53 | 2022-02-10 | 69 | Tagline / Tagline Winch (motor, gearbox, etc.) | None | 1770611 | Work Order not found |  | N | [7 empty] | No. Increase cooling by installing a secondary blower |  | 1 | 0 | 0
314 | Sandpiper | 2022-02-13 | 81.9167 | Cutter / Motor | replaced k27 pump, pilot pump, and 2 saffer pumps on ladderffer | 4814293 | K27 pump failure & Removal |  | N | [7 empty] | No. BBI investigared, a design flaw Capital request in submitted. |  | 1 | 0 | 0
315 | Terrapin Island | 2022-02-15 | 121 | Other / Other Mechanical | Vessel at anchor surveying the vessel to find the sounce of water and and follw up repairs to the hull. | 4814218 | Services for Repairs |  | N | [7 empty] | No. Hole in the hull repaired in the SY. |  | 1 | 0 | 0
316 | Sandpiper | 2022-02-17 | 26.6167 | Cutter / Motor | hydraulic pump | None |  |  | N | [7 empty] | No. BBI investigared, a design flaw Capital request in submitted. |  | 1 | 0 | 0
317 | Ellis Island | 2022-02-18 | 163.1831 | Piping/Hoses / Pump Room Discharge Pipe | Repair Bow Connection Elbow Pipe | None |  | Complete | 425 | Ellis Island Overbow Elbow Failure | 02/18/2022 | David Dye | 1 | 1 |  |  | 425 | 0 | 1 | 1 | 1
318 | Sandpiper | 2022-02-21 | 35.5331 | Main Pump / Pump Rebuild | replace booster pump impeller | 4814402 | Repairs to Booster Pump |  | N | [7 empty] | No. Damage due to trash. |  | 1 | 0 | 0
319 | Carolina | 2022-02-24 | 139.6969 | Main Pump / Pump Rebuild | Scheduled Maintenance. Opportunity tasks - replace sleeve | 4814445, 4814426 | Stuffing box R&R / Sleave replacement |  | N | [7 empty] | No. Scheduled downtime for suction pumping. |  | 1 | 0 | 0
320 | 55 | 2022-02-27 | 36.2261 | Main Hoist / Holder | None | 4814843 | Aft Hoist Motor Replaced |  | N | [7 empty] | No. We have an annual machine audit. Hoist drum brake failure. |  | 1 | 0 | 0
321 | 55 | 2022-03-10 | 53.6492 | Main Hoist / Holder | aft hoist motor failed | 4814744 | # 2 Hoist DC Motor Removal and Replacement Style Old Style # 27N8958 New Style # 27N8959 |  | N | [7 empty] | No. They wer overdue for replacement. Replace during a major SY period. We elected not to service them. Action do we have an adequate inspection (SJ) on other vessels |  | 1 | 0 | 0
322 | Texas | 2022-03-15 | 76.3906 | Spuds / Xmass Tree / Tree Structure | None | 4814743 | Xtree Inspection (ILM) |  | Y | [7 empty] | x-mas tree repair, QC issues with welds with pins/sheaves on x-mas tree. Yes to MCIA, requested vessel/project to start MCIA. |  | 1 | 0 | 0
323 | Dodge Island | 2022-04-02 | 37.0994 | Dredge Pump Engine / Other | None | 4071941 | Stbd Dredge Engine - Troubleshoot Shutdowns |  | N | [9 empty] | 1 | 0 | 0
324 | 55 | 2022-04-07 | 36.1831 | Main Hoist / Holder | CRANE TRIPPED, TROUBLE SHOOTING | 4815483 | C/O Hoist Motor FWD #1 Drive Transformer |  | N | [7 empty] | Component Failure / replaced with onboard spare |  | 1 | 0 | 0
325 | Texas | 2022-04-13 | 89.8072 | Ladder Pump / Motor / Engine | wire shorted out | 792995 | Replace Ladder Pump Motor |  | Y | [7 empty] | replace UWP motor, motor had a bad leg – burned up all 3 conductor wires. Yes to MCIA, requested vessel/project to start MCIA. |  | 1 | 0 | 0
326 | 53 | 2022-04-20 | 28.7194 | Main / Aux. Generators / Main Generator Engine | None | 4815650 | Change out idler pulley pillar block #2 engine |  | Y | [7 empty] | Brian G looking into this. |  | 1 | 0 | 0
327 | Padre Island | 2022-04-25 | 135.9994 | Dredge Pump / Shafting | While adjusting the impellor pump, the shaft and bearings in the gear box assembly broke. | 4815725 | Dredge Pump Line Shaft and bearing repair |  | Y | [7 empty] | Crack in shaft / Flinger ring hid the crack / Add shear wave inspection ?? NDT Test / Smart Sheet Engineering Research / Critical Spare addition - Bearing - Add Serialized Part for assembly - Oil Analysis indicated a problem. The "spare" bearing assembly was thrown away by mistake. |  | 1 | 0 | 0
328 | Texas | 2022-04-26 | 24.4667 | Spuds / Xmass Tree / Wires | broke stern wire | 4815889 | replace D03 ) bone crusher hose (ILM) |  | N | [7 empty] | broken into two, should be removed as MM |  | 1 | 0 | 0
329 | 54 | 2022-04-27 | 332.8331 | Spud System / Spud Structure | Leak in spud well | 4815856 | DryDocking for Repairs to Side Shell of Starboard Spudwell |  | N | [9 empty] | 1 | 0 | 0
330 | New York | 2022-04-30 | 64.3133 | Spud System / Spud Wires | lifting stern spud to take a step back.....spud started freefalling down... Bottom wire broke | 4815925 | Pick and secure |  | N | [7 empty] | Failure - broken wire on stern spud, no MCIA |  | 1 | 0 | 0
331 | 58 | 2022-05-26 | 62.25 | Tagline / Tagline Winch (motor, gearbox, etc.) | drum shifted on shaft | 4816345 | Repair Drum |  | Y | [7 empty] | add SJ to inspect |  | 1 | 0 | 0
332 | Ohio | 2022-05-31 | 151.4167 | Ladder Pump / Gearbox | None | 4816439 | UWP gearbox oil leak | In Progress | 437 | Ohio UWP Gearbox & Thrust Bearing Failures | 05/31/2022 | Brandon Suire | [6 empty] | 1 | 1 | 1
333 | 54 | 2022-05-31 | 108.4833 | Crane Boom / Boom Wires | remove broken wire rubber rest on boom | 4816411 | Crop and renew Lacing on Boom |  | y | [9 empty] | 1 | 0 | 0
334 | 53 | 2022-06-05 | 31.5664 | Crane Swing / Swing Circle (rollers, etc.) | Crane rail tabs breaking off | 1776468 | Work Order not found |  | N | [7 empty] | Check WO for time period if it pertains |  | 1 | 0 | 0
335 | 53 | 2022-06-07 | 72.15 | Main / Aux. Generators / Main Generator Engine | Planned CAT engine work | 1776476 | Work Order not found |  | N | [7 empty] | Check WO for time period if it pertains |  | 1 | 0 | 0
336 | 54 | 2022-06-12 | 82.7167 | Crane Boom / Boom / Gantry Sheaves | Bearing on holding wire tip sheave failed | 4251945 | Boom Point Sheave asem removal |  | Y | [7 empty] | Sheave assembly disassembled by SY, no drawings at that time. |  | 1 | 0 | 0
337 | 53 | 2022-06-12 | 45.9 | Electrical/Electronics / PLC | None | 4816621 | Troubleshoot closing drive tripping |  | N | [7 empty] | Slimmer/Bill English - |  | 1 | 0 | 0
339 | 54 | 2022-06-20 | 25.5833 | Crane Swing / Drive (motor, gear box, etc.) | AC Drive Motor, check end time. | 4251951 | Benshaw 2400 repair |  | N | [7 empty] | New part failure - |  | 1 | 0 | 0
340 | Ohio | 2022-06-25 | 124.2667 | Ladder Pump / Gearbox | None | 4816439 | UWP gearbox oil leak | In Progress | 438 | Ohio UWP GB Intermediate Bearing Failure | 06/25/2022 | Brandon Suire | [6 empty] | 1 | 1 | 1
341 | 53 | 2022-06-25 | 62.7333 | Electrical/Electronics / MCC / Switch Gear | Choke coil burnt up | 4816907 | Change out burnt up coil on Closer phase |  | N | [7 empty] | New part failure - choke coil, added to critical spares list for onboard |  | 1 | 0 | 0
342 | Ohio | 2022-07-09 | 195 | Ladder Pump / Motor / Engine | None | 4532599 | Ladder Pump Gearbox Quarterly PM/Inspection | In Progress | 438 | Ohio UWP GB Intermediate Bearing Failure | 06/25/2022 | Brandon Suire | [6 empty] | 1 | 1 | 1
343 | Dodge Island | 2022-07-20 | 28.5 | Generator Engine / Other | None | 4072127 | Port Generator - Replace air starter |  | N | [7 empty] | broken into two, should be removed as MM |  | 1 | 0 | 0
344 | 54 | 2022-07-26 | 116.2 | Crane Boom / Boom Winch | Boom motor failure | 4817452 | Complete Inspection of all DC Motors / Generators brushes/holders and commutators associated with Crane Boom Operation | [11 empty] | 1 | 0 | 0
345 | Ohio | 2022-08-05 | 46.8167 | Main Pump / Engine / Motor | None | 4817827 | Inspect and repair vibration in STBD pump Driveline | [11 empty] | 1 | 0 | 0
346 | Alaska | 2022-08-08 | 169.8833 | Spuds / Xmass Tree / Tree Structure | Installing xmas tree before starting up | 1779011 | Work Order not found | [11 empty] | 1 | 0 | 0
347 | Ohio | 2022-08-11 | 78.1333 | Generators / Main Generator | None | 4817430 | Condut the UT Survey as Required for ABS LL Renewal | [11 empty] | 1 | 0 | 0
348 | Liberty Island | 2022-08-13 | 44.15 | Main Engine/Propulsion / Other | Starboard Turbo Overheated/Failure - Repair | 851900 | Stbd Propulsion engine inboard turbo failure and Exhaust bellows | [11 empty] | 1 | 0 | 0
349 | Liberty Island | 2022-08-17 | 34.2667 | Gimbal Hoist / Other | Gimbal bolts sheared | 851907 | Remove and replace stbd gimble from damage | [11 empty] | 1 | 0 | 0
350 | Ohio | 2022-08-27 | 35.5667 | Ladder / Ladder Structure | None | 4818043 | Damaged ladder service water lines and air lines | In Progress | 446 | Ohio Ladder Damage from Swing Wire | 08/27/2022 | Wade Smith | [6 empty] | 1 | 1 | 1
351 | Alaska | 2022-08-28 | 25.05 | Generators / Main Generator | changing the power pack | 1729214 | Change Out EMD Injector #1 cylinder on main gen. | [11 empty] | 1 | 0 | 0
0
[18 empty] | 0 | 0 | 1 | 0
|  |  |  | SAFELYNCS DATA ONLY: | [13 empty] | 0 | 0 | 1 | 0
| Ohio | 06/17/2022 | [5 empty] | Complete | 436 | Ohio Plugged Subline | 06/17/2022 | Brandon Suire | 3 | 3 | Scott Baumann |  |  | 0 | 0 | 1 | 0
[18 empty] | 0 | 0 | 1 | 0
EDL / NS ENTERPRISE DATA
SAFELYNCS DATA
CORRELATED EDL & SAFELYNCS DATA
RAM STEERING COMMITTEE DECISION-MAKING
|  | # |  | Data Point |  |  | Reference
|  | 6 |  | # MCIA's started |  |  | SafeLyncs - Cases
|  | 4 |  | # MCIA's in progress |  |  | SafeLyncs - Cases
|  | 0 |  | # MCIA's Ready for Edits |  |  | SafeLyncs - Cases
|  | 0 |  | # MCIA's Ready for Review |  |  | SafeLyncs - Cases
|  | 2 |  | # MCIA's completed |  |  | SafeLyncs - Cases
|  | 0 |  | # MCIA's requiring Corrective Actions Validated |  |  | SafeLyncs - Corrective Actions
| * | 44 |  | # EDL MM entries (>24hrs) |  |  | EDL Data
|  | 40 |  | # EDL MM w/ WO#'s |  |  | EDL Data
|  | 4 |  | # EDL MM w/o WO#'s |  |  | EDL Data
| * | 3 |  | # EDL MM w/ MCIA coorelation |  |  | EDL v. SafeLyncs
| * | 24 |  | # EDL MM determined "No" MCIA required |  |  | RAM Steering Committee
| * | 7 |  | # EDL MM determined "Yes" MCIA required, not started |  |  | RAM Steering Committee
| * | 7 |  | # EDL MM still requiring determination |  |  | RAM Steering Committee
41
[7 empty] | Year: | 2022
# > 24hrs
[8 empty] | Mechanical | Hours
[7 empty] | 53 | 6 | 310.0692
[7 empty] | 54 | 6 | 692.5331
[7 empty] | 55 | 4 | 151.7294
[7 empty] | 58 | 1 | 62.25
[7 empty] | New York | 3 | 115.7075
[7 empty] | Mechanical Division | 20 | 1332.2892
[7 empty] | Alaska | 2 | 194.9333
[7 empty] | Carolina | 3 | 299.3061
[7 empty] | Illinois | 1 | 120.9667
[7 empty] | Ohio | 8 | 690.55
[7 empty] | Texas | 3 | 190.6644
[7 empty] | Hydraulic Division | 17 | 1496.4206
[7 empty] | Dodge Island | 2 | 65.5994
[7 empty] | Ellis Island | 1 | 163.1831
[7 empty] | Liberty Island | 2 | 78.4167
[7 empty] | Padre Island | 1 | 135.9994
[7 empty] | Terrapin Island | 2 | 179.625
[7 empty] | Hopper Division | 8 | 622.8236
[7 empty] | Iowa | 1 | 70.85
[7 empty] | Sandpiper | 3 | 144.0664
[7 empty] | Rivers & Lakes Division | 4 | 214.9164
[7 empty] | All Vessels | 49 | 3666.4497
[7 empty] | Dredge | Count | Hours
[7 empty] | 53 | 6 | 310.0692
[7 empty] | 54 | 6 | 692.5331
[7 empty] | 55 | 4 | 151.7294
[7 empty] | 58 | 1 | 62.25
[7 empty] | New York | 3 | 115.7075
[7 empty] | Alaska | 2 | 194.9333
[7 empty] | Carolina | 3 | 299.3061
[7 empty] | Illinois | 1 | 120.9667
[7 empty] | Ohio | 8 | 690.55
[7 empty] | Texas | 3 | 190.6644
[7 empty] | Dodge Island | 2 | 65.5994
[7 empty] | Ellis Island | 1 | 163.1831
[7 empty] | Liberty Island | 2 | 78.4167
[7 empty] | Padre Island | 1 | 135.9994
[7 empty] | Terrapin Island | 2 | 179.625
[7 empty] | Iowa | 1 | 70.85
[7 empty] | Sandpiper | 3 | 144.0664
Formulas:
INCIDENT DATE = VLOOKUP([EDL Data Tab Ref],Table1[['#]:[Date]],3,FALSE)